## Sheet1
Project Initiaition | Hrs | Days
Stakeholders workshop | 16 | 2 |  |  | Resources | days | total
Research customer insights | 16 | 2 |  | BA | 1 | 12 | 12
Persona development and user journey | 16 | 2 |  | UI/UX | 1 | 16 | 16
Information architecture | 16 | 2 |  | pm | 1 | 6.3 | 6.3
Wireframes & FSD | 32 | 4 |  | Documentation | 1 | 10 | 10
Prototype and testing with the users | 32 | 4 |  | Jr Developer | 1.5 | 21.3333 | 32 | 63 | 64
Develop content | 32 | 4 |  | Sr Developer | 1.5 | 21.3333 | 32
Visual design and UI guide | 32 | 4 |  | QA | 1.5 | 18.0333 | 27.05
page customizations (nightmode, colorbling, font size) | 32 | 4 |  | Total |  |  | 135.35
Project Management | 50.4 | 6.3 |  |  | days | months
Documentation | 80 | 10 |  | Delivery Timeline | 67.3667 | 3.3683
Implement the requirments |  |  |  | Total effort | 135.35 | 6.7675
Installing and configuring the CMS | 48 | 6
About Ministry | 8 | 1 |  | Mobile app development |  | 3 months / 2 developers
Media - events, news | 8 | 1 |  | (includes design development & testing)
Surveys | 8 | 1
Polls | 8 | 1 |  | API Development | 20 | 1
Presskit | 8 | 1
Investment dashboard | 16 | 2
FDI Dashboard | 16 | 2
Ecosystem magazine | 8 | 1
Initiatives | 8 | 1
statistical reports | 16 | 2
trade exchange statistics | 12 | 1.5
Tourism promotion | 8 | 1
Investment portal | 16 | 2
covid-19 portal | 8 | 1
trade promotions | 8 | 1
trade map | 8 | 1
sustainable development goals | 8 | 1
Portal login | 8 | 1
Apply for jobs | 8 | 1
customer login | 8 | 1
FAQ | 8 | 1
archives | 8 | 1
laws and regulations | 8 | 1
Text to speech | 12 | 1.5
night mode | 0 | 0
color blind | 8 | 1
font size | 0 | 0
economic substance | 8 | 1
WTO portal | 16 | 2
Integrations
Zendesk | 16 | 2
UAE pass | 8 | 1
SMS | 8 | 1
Twilio | 24 | 3
e-dirham | 8 | 1
Qmatic | 16 | 2
Khadamati | 16 | 2
eparticipation | 16 | 2 | 160 | 20
Mobile API development | 0 | 0
Arabic / RTL | 80 | 10
QA
QA testing | 176.4 | 22.05
UAT Signoff | 40 | 5
total | 1074.8 | 134.35