## Web
CSI Hub 21 September2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 5 | 5
Business analysis | 32 | 4 | BA | 1 | 4 | 4
Project Management | 81.74 | 10.2175 | Tech Writer | 1 | 4 | 4
SRS,User Manual,weekly report | 32 | 4 | PM | 1 | 10.2175 | 10.2175
Design and Prototype (mobile & Web) | 40 | 5 | Sr Developer | 1 | 37 | 37 | 74 | 74.75
Development |  |  | Jr Developer | 1 | 37 | 37
Application Basic setup | 0 | 0 | QA | 2 | 11.2125 | 22.425
Information & Resources |  |  | Total |  |  | 119.6425
Home page | 16 | 2
Publicly available Information and Resources |  | 0 |  | Days | Months
General information on HIB, CSI & Ma’an | 6 | 0.75 | Total Effort | 119.6425 | 5.9821
Eligibility & Incentives | 8 | 1 | Delivery Timeline | 57.2125 | 2.8606
Dashboard | 12 | 1.5
Links to other Ma’an platforms | 4 | 0.5
Stakeholder specific information & Resources |  | 0
Current status of assessed companies (Strength & weakness) drill down report | 8 | 1
Reccomendation and Insight on users performance | 6 | 0.75
Tools, toolkits & guidelines | 8 | 1
Meetups and training schedules | 8 | 1
Assessment & Label
Signup / Registration |  | 0
Eligibility Questionairre & Eligibility guidelines | 16 | 2
Registration details (Name, domicile, registration # etc) | 12 | 1.5
Upload documents to verify legal status and other requirments | 4 | 0.5
Validation process(private/registered) | 8 | 1
Third party integrations for verifications | 6 | 0.75
Assign credentials & email upon successful verification | 4 | 0.5
SignIn (using assigned credentials) |  | 0
Sign in using credentials | 4 | 0.5
track application status | 6 | 0.75
Self Assessment |  | 0
Answer predefined questions (multiple choice,yes/No, Open text) | 0 | 0
Compute results based on responses | 0 | 0
View preliminary assessment results (Results may include reccomendadtions & guides) | 0 | 0
Information and resources eligible for companies completing self assessment | 0
Option to move to administered assessment /application process | 0 | 0
Administered Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 20 | 2.5
Upload documents | 4 | 0.5
Payment for application | 6 | 0.75
View status of application and time for assessment results | 4 | 0.5
Apply for label based on administered results | 8 | 1
Assess information and resources based on administered results | 8 | 1
Payment for Label | 6 | 0.75
Schedule Meetups & training | 12 | 1.5
Donate fund | 6 | 0.75
Receive notification when the labels expires | 6 | 0.75
Reapply for label | 8 | 1
Awards,Incentives & Recognition (Passes Administered assessment & applied for labels)
Highlights of awarded companies | 6 | 0.75
Contributions of awarded companies | 6 | 0.75
Awards | 6 | 0.75
Incentives | 6 | 0.75
Recognition | 6 | 0.75
Live calls and online collaboration | 0 | 0
Notification dashboard | 12 | 1.5
Admin
Review,Validate & assess answers of administered Assessment | 12 | 1.5
Review documents | 6 | 0.75
Approve/reject new User registration | 6 | 0.75
Dashboard | 12 | 1.5
Master data management | 16 | 2
User Role management | 6 | 0.75
Add/modify/delete training schedule | 16 | 2
Login/Logout | 2 | 0.25
Manage toolkits | 4 | 0.5
Manage guidelines | 4 | 0.5
Schedule Meetups & training | 4 | 0.5
Manage status | 4 | 0.5
System Features
Authentication, Authorization | 8 | 1
Exception Handling and Error logging | 4 | 0.5
Automated self assessment validation | 12 | 1.5
Payment Integration | 20 | 2.5
Notification Management | 16 | 2
Data Integration with govt/private database | 0 | 0 | 8 hrs per integration
Integration with database of the chamber of commerce for validation | 16 | 2
Integrate LIVE calls | 0 | 0 | 8 days | Based on twillio – May be excluded from the estimate
Integration with Ma'an websites | 8 | 1
Bilingual Site (Arabic / English) | 64 | 8
Third party integrations | 32 | 4
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
Auditing & Logging | 6 | 0.75
Reccomendation engine for toolkits, guidelines, awards, incentives etc based on company status | 12 | 1.5
Workflow engine | 12 | 1.5
SQA
QA & Bug fixing | 179.4 | 22.425
UAT | 40 | 5
Deployment | 8 | 1
Total | 1011.14 | 126.3925
Comments/Assumptions
The effort may change after a detailed system study and also after receiving the details of the external componets to be integrated
Payment gateway details would be shared by the client
Live calls SDK/API would be shared by the client
Only english languages is considered for the application
Automated self assessment validations would be based on the objective type questions. Descriptive answers need to be manually verified.
The details of the external APIs for validating the comapany would be shared by the client [Eg:- Other government or private data-base (API)]

## FastTrack
CSI Hub 21 September2020
Module | Hours | Man Days | Resources | # | Days | Total
Project Initiation |  |  | UI / UX | 1 | 3 | 3
Business analysis | 20 | 2.5 | BA | 1 | 2.5 | 2.5
Project Management | 45.82 | 5.7275 | Tech Writer | 1 | 4 | 4
SRS,User Manual,weekly report | 32 | 4 | PM | 1 | 5.7275 | 5.7275
Design and Prototype (mobile & Web) | 24 | 3 | Sr Developer | 1 | 21 | 21 | 42 | 41.75
Development |  |  | Jr Developer | 1 | 21 | 21
Application Basic setup | 0 | 0 | QA | 2 | 6.2625 | 12.525
Information & Resources |  |  | Total |  |  | 69.7525
Home page | 16 | 2
Publicly available Information and Resources |  | 0 |  | Days | Months
General information on HIB, CSI & Ma’an | 6 | 0.75 | Total Effort | 69.7525 | 3.4876
Eligibility & Incentives | 8 | 1 | Delivery Timeline | 32.7625 | 1.6381
Dashboard | 12 | 1.5
Links to other Ma’an platforms | 4 | 0.5
Stakeholder specific information & Resources |  | 0
Current status of assessed companies (Strength & weakness) drill down report | 0 | 0
Reccomendation and Insight on users performance | 0 | 0
Tools, toolkits & guidelines | 0 | 0
Meetups and training schedules | 0 | 0
Assessment & Label
Signup / Registration |  | 0
Eligibility Questionairre & Eligibility guidelines | 16 | 2
Registration details (Name, domicile, registration # etc) | 12 | 1.5
Upload documents to verify legal status and other requirments | 4 | 0.5
Validation process(private/registered) | 8 | 1
Third party integrations for verifications | 6 | 0.75
Assign credentials & email upon successful verification | 4 | 0.5
SignIn (using assigned credentials) |  | 0
Sign in using credentials | 4 | 0.5
track application status | 6 | 0.75
Self Assessment |  | 0
Answer predefined questions (multiple choice,yes/No, Open text) | 0 | 0
Compute results based on responses | 0 | 0
View preliminary assessment results (Results may include reccomendadtions & guides) | 0 | 0
Information and resources eligible for companies completing self assessment | 0
Option to move to administered assessment /application process | 0 | 0
Administered Assessment |  | 0
Answer questions(multiple choice,yes/No, Open text) | 20 | 2.5
Upload documents | 4 | 0.5
Payment for application | 6 | 0.75
View status of application and time for assessment results | 4 | 0.5
Apply for label based on administered results | 8 | 1
Assess information and resources based on administered results | 8 | 1
Payment for Label | 6 | 0.75
Schedule Meetups & training | 0 | 0
Donate fund | 0 | 0
Receive notification when the labels expires | 0 | 0
Reapply for label | 0 | 0
Awards,Incentives & Recognition (Passes Administered assessment & applied for labels)
Highlights of awarded companies | 0 | 0
Contributions of awarded companies | 0 | 0
Awards | 0 | 0
Incentives | 0 | 0
Recognition | 0 | 0
Live calls and online collaboration | 0 | 0
Notification dashboard | 0 | 0
Admin
Review,Validate & assess answers of administered Assessment | 12 | 1.5
Review documents | 6 | 0.75
Approve/reject new User registration | 6 | 0.75
Dashboard | 12 | 1.5
Master data management | 16 | 2
User Role management | 6 | 0.75
Add/modify/delete training schedule | 0 | 0
Login/Logout | 2 | 0.25
Manage toolkits | 0 | 0
Manage guidelines | 0 | 0
Schedule Meetups & training | 0 | 0
Manage status | 0 | 0
System Features
Authentication, Authorization | 8 | 1
Exception Handling and Error logging | 4 | 0.5
Automated self assessment validation | 12 | 1.5
Payment Integration | 20 | 2.5
Notification Management | 16 | 2
Data Integration with govt/private database | 0 | 0 | 8 days | Based on twillio – May be excluded from the estimate
Integration with database of the chamber of commerce for validation | 16 | 2
Integrate LIVE calls | 0 | 0
Integration with Ma'an websites | 0 | 0
Bilingual Site (Arabic / English) | 0 | 0
Third party integrations | 0 | 0
Protection against injection attacks (SQL, CRLF) | 6 | 0.75
URL encoding, Input validation | 6 | 0.75
Cookie Encryption, Cookie replay attacks | 6 | 0.75
Session hijacking prevention | 6 | 0.75
Cross site scripting and session management | 6 | 0.75
Auditing & Logging | 6 | 0.75
Reccomendation engine for toolkits, guidelines, awards, incentives etc based on company status | 0 | 0
Workflow engine | 0 | 0
SQA
QA & Bug fixing | 100.2 | 12.525
UAT | 20 | 2.5
Deployment | 4 | 0.5
Total | 580.02 | 72.5025
Comments/Assumptions
The effort may change after a detailed system study and also after receiving the details of the external componets to be integrated
Payment gateway details would be shared by the client
Live calls SDK/API would be shared by the client
Only english languages is considered for the application
Automated self assessment validations would be based on the objective type questions. Descriptive answers need to be manually verified.
The details of the external APIs for validating the comapany would be shared by the client [Eg:- Other government or private data-base (API)]

## Sheet1
Phase 1 | Phase 2
Business analysis | Business analysis
Project Management | Project Management
SRS,User Manual,weekly report | User Manual,weekly report
Design and Prototype (mobile) | Design and Prototype ( Web)
Development
Application Basic setup
Information & Resources | Information & Resources
Home page
Publicly available Information and Resources
General information on HIB, CSI & Ma’an
Eligibility & Incentives
Dashboard
Links to other Ma’an platforms
Stakeholder specific information & Resources
Current status of assessed companies (Strength & weakness) drill down report
Reccomendation and Insight on users performance
Tools, toolkits & guidelines
Meetups and training schedules
Assessment & Label | Assessment & Label
Signup / Registration
Eligibility Questionairre & Eligibility guidelines
Registration details (Name, domicile, registration # etc)
Upload documents to verify legal status and other requirments
Validation process(private/registered)
Third party integrations for verifications - 1 Integration
Assign credentials & email upon successful verification
SignIn (using assigned credentials)
Sign in using credentials
track application status
Self Assessment
Answer predefined questions (multiple choice,yes/No, Open text)
Compute results based on responses
View preliminary assessment results (Results may include reccomendadtions & guides)
Information and resources eligible for companies completing self assessment
Option to move to administered assessment /application process
Administered Assessment
Answer questions(multiple choice,yes/No, Open text)
Upload documents
Payment for application
View status of application and time for assessment results
Apply for label based on administered results
Assess information and resources based on administered results
Payment for Label
Schedule Meetups & training
Donate fund
Receive notification when the labels expires
Reapply for label
Awards,Incentives & Recognition (Passes Administered assessment & applied for labels) | Awards,Incentives & Recognition (Passes Administered assessment & applied for labels)
Highlights of awarded companies
Contributions of awarded companies
Awards
Incentives
Recognition
Live calls and online collaboration
Notification dashboard
Admin | Admin
Review,Validate & assess answers of administered Assessment
Review documents
Approve/reject new User registration
Dashboard
Master data management
User Role management
Add/modify/delete training schedule
Login/Logout
Manage toolkits
Manage guidelines
Schedule Meetups & training
Manage status
System Features | System Features
Authentication, Authorization
Exception Handling and Error logging
Automated self assessment validation
Payment Integration
Notification Management
Data Integration with govt/private database - 1 Integration for company validation | Data Integration with govt/private database
Integration with database of the chamber of commerce for validation - 1 Integration for company validation
Integrate LIVE calls
Integration with Ma'an websites
Bilingual Site (Arabic / English)
Third party integrations
Protection against injection attacks (SQL, CRLF)
URL encoding, Input validation
Cookie Encryption, Cookie replay attacks
Session hijacking prevention
Cross site scripting and session management
Auditing & Logging
Reccomendation engine for toolkits, guidelines, awards, incentives etc based on company status
Workflow engine
SQA | SQA
QA & Bug fixing | QA & Bug fixing
UAT | UAT
Deployment | Deployment

## Sheet2
Scope | Phase
Information and Resources
 Home Page (Publicly available Information) | 1
o Sign up/Sign in/Register | 1
o CSI and Ma'an Corporate Information and General Information on the Hub | 1
o Information on the Label, the Eligibility and the Incentives | 1
o Data & Dashboard on best practices in CSR, top performing companies & global insights | 1
o Links to other Ma'an platforms for making donations. | 1
Stakeholder Login / Registered User Login | 1
o Dashboard (Current status of assessed companies, areas of strengths weakness based on Assessment results) | 1
o View Guidelines, Hand books, Best Practices, Articles as published by Admins | 2
o Meet ups, Training Scheduling | 2
o Live Video Conference Calls | 2
Assessment and Label
 Sign Up | 1
o Identify Company Type (Private, Registered in Abu Dhabi or other) | 1
o Enter the details of Company | 1
o Upload Documents | 1
o Company Identity Validation | 2 | Can it be handled manually for Phase 1
Sign In | 1
o Sign in using credentials | 1
o Track application Process & Status | 1
 Self-Assessment | 1
o Attend detailed self-assessment (Multiple Choice, Yes/No, Open Text) | 1
o View Automated results from Backend | 1
o Hover some of the platform’s information and resources | 1
o Option to move to Administered Assessment /Application Process once qualified | 1
Administered Assessment - Scale down Version | 1
o Attend detailed Administered Assessment (Multiple choice, Yes/No, Open Text) | 1
o Upload Files/Documents | 1
o Option to make Payment for Application Submission | 1
o View Application Status and time for receiving the Assessment Results | 1
o View results from Backend (Automated & Manual) | 1
o Apply for Label based on Administered Assessment Result | 2
o Option to make Online Payment for Label Request Application | 2
o Assess Additional Information and Resources based on Administered Assessment Result | 1
o Meet ups, Training & Live Video Conference calls | 2
o Donate fund (Link will be provided to other government/private websites where user can make their contributions) | 2
o Receive notification on labels expiry | 2
o Option to submit request for label Renewal | 2
Awards, Incentives & Recognition | 2
 Highlights of Awarded Companies | 2
 Contributions of Awarded Companies | 2
 Awards | 2
 Incentives | 2
 Recognition | 2
Administrator
 Review, Validate & assess answers of administered Assessment | 1
 Review Documents | 1
 Uploading of Assessment Results | 1
 Approve/Reject New User Registration | 1
 Dashboard | 1
 Master Data Management | 1
 User Role Management | 1
 Add/Modify/Delete Training Schedule | 2
 Login/Logout | 1
System Features
 Authentication, Authorization | 1
 Exception Handling and Error logging | 1
 Automated Self-Assessment Validation | 1
 Payment Integration | 1
 Notification Management (Windows Service) | 1
 Integration with the database of third party entities (e.g. Chamber of Commerce) for company identity validation. Only 2 such integrations have been considered in the scope of this project. | 2 | Can it be handled manually for Phase 1?
 Integrate LIVE calls (Using third party tools) | 2
 Links to other Ma'an websites for users to donate fund at any time. | 2
Arabic Interface | 2
Workkflows (if any) | 2
SRS separate for each Phase