## AGMC Project
AGMC PROJECT ESTIMATE
June 9 2018 ¦ Estimate done by: Sharath/Siva/Ajeesh/Rikhil/Dyana
Page |  | Design | HTML | PHP-Open Cart | App Proto | Android | iOS
|  | Hours | [7 empty] | Resources | Hours | Days | Total
Basic Custom Theme Creation |  |  |  | 115 |  |  |  |  | UI/UX | 1 | 53 | 6.625 | 6.625
Home |  | 12 | 20 |  | 8 | 16 | 16 |  | Prototype | 1 | 188 | 23.5 | 23.5
[9 empty] | PHP Dev 1 | 1 | 268 | 33.5 | 33.5 | 268 | 33.5
Find BMW | Car Listing | 4 | 8 |  | 2 | 6 | 6 |  | PHP Dev 2 | 1 |  |  | 0
| Car Details | 8 | 16 |  | 6 | 8 | 8 |  | Mobile App Proto | 1 | 40 | 5 | 5
| Customization (interior / exterior) |  | 40 | [5 empty] | Android | 1 | 205 | 25.625 | 25.625
| Leasing / Financing |  | 4 | 25 |  |  |  |  | IOS | 1 | 205 | 25.625 | 25.625
| Quotation with photos (with QR Code)(Print / Email) |  | 8 | 20 | [7 empty] | Total | 119.875
| Payment gateway for down payment |  |  | 25 | [5 empty] | Man days
[9 empty] | Total Effort | 119.875
My BMW | Landing page | 6 | 6 |  | 4 |  |  |  | Delivery Days (Web) | 63.625
| Register | 2 | 4 |  | 2 | 6 | 6 |  | Delivery Days (Mobile) | 30.625
| Login | 1 | 2 |  | 1 | 4 | 4
| Make an Appointment | 4 | 4 | 15 | 3 | 6 | 6
| Appointment Details | 2 | 4 | 6 | 2 | 8 | 8
| Authorized Service Center | 1 | 6 | 12 | 1 | 8 | 8
| Campaigns | 6 | 8 | 15 | 4 | 8 | 8
| Feedback Form | 1 | 2 |  | 1 | 8 | 8
BMW Used Cars | Car Listing | 0 | 0 |  | 0 | 4 | 4
| Car Details | 0 | 0 |  | 0 | 4 | 4
Footer | Contact Us | 1 | 4 |  | 1 | 4 | 4
| Test Drive | 2 | 3 |  | 2 | 6 | 6
| BMW Emergency Road Assistance | 1 | 2 |  | 1 | 8 | 8
| FAQ | 1 | 4 |  | 1 | 8 | 8
| Legal Disclaimer | 1 | 2 |  | 1 | 8 | 8
| Cookie Policy | 0 | 1 |  | 0
Arabic |  |  | 40 |  |  | 59 | 59
Mobile API |  |  |  | 35
logout | [5 empty] | 2 | 2
User information popup | [5 empty] | 8 | 8
Basic Setup | [5 empty] | 8 | 8
Developer side testing | [5 empty] | 8 | 8
QA |  |  |  | 70
Total |  | 53 | 188 | 268 | 40 | 205 | 205
| Grand Total Hours | [5 empty] | 959 | 119.875
Notes | [6 empty] | +/- 20% Contingency
Phase 2 (shopping) not included
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode
This estimation can vary based on the complexity of the design
Please note:
Unable to check following modules: Login , Register, Appointments