## Adam Vital
| Adam Vital |  | 15/01/2018
Monday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 5 | 5
| Business analysis | 24 | 3 | Sr Developer | 1 | 14 | 14 | 38.75 | 39 | 38.75 | 39
| Project Management | 42.7 | 5.3375 | Jr Developer | 1 | 25 | 25
| Design and Prototype | 40 | 5 | PM | 1 | 5.3375 | 5.3375
| Development |  |  | BA | 1 | 3 | 3
| Application basic setup | 8 | 1 | QA | 2 | 6.8125 | 13.625
| Admin Module |  |  | Total |  |  | 65.9625
| Manage School departments or sections | 6 | 0.75
| Manage Exercise categories for each department | 6 | 0.75
| User Management | 12 | 1.5 | Total Delivery days | 39.8125
| User Groups | 6 | 0.75 | Total Effort | 65.9625 | (+1 Day deployment)
| Manage user entitlements and access rights | 8 | 1
| Manage Exercises | 12 | 1.5
| upload Photos, Videos, Image, Text | 12 | 1.5 | Hosting and Backup | INR / Year
| Add exercise tags for searching and indexing | 12 | 1.5 | Open source Soln' | 89229
| Link Departments, staff, users etc | 6 | 0.75 | Microsoft Soln' | 250086
| Exercise Content editor | 16 | 2 | Subdomaining cost | Free
| Exercise content templates | 16 | 2 | New Domain registration | Market Price
| Approve new exercises (video, image, text etc) uploaded by staff | 6 | 0.75
| Receptionist module |  |  | Note:
| Login, Forgot password | 6 | 0.75 | "+" or "-" 10 days (Total effort)
| register patient | 8 | 1
| Register extenal patients | 8 | 1
| Manage patient database | 8 | 1 | Server Configuration | Open Source | Microsoft
| Staff Module |  |  | CPU | 2 cores | 2 cores
| Login, Forgot password | 6 | 0.75 | RAM | 4 GB | 4 GB
| Add / manage new training videos, images and text | 6 | 0.75 | Disk Space | 200 GB | 200 GB
| Staff uploaded excercises available on staff dashboard | 6 | 0.75 | Data Transfer | 200 GB | 200 GB
| Share excercises with other staff or external patients | 4 | 0.5 | OS | Cent OS | Windows server 2012 |  | -10
| Mark excersices as favourite | 4 | 0.5 | Database | MySQL | MSSQL
| Share as links with patients via SMS | 8 | 1 | Backup | 200 GB | 200 GB
| Print Excercises with print preview | 16 | 2 | No of IP's | 1 | 1
| Add Excersise notes while printing or sharing | 4 | 0.5
General application features
| Simpple search & advanced search | 16 | 2
| Send Feedback | 6 | 0.75
| dashboard for staff, receptionist, admins (Fav, Viewed, History, Shared, recommended excersises, Excersice charts etc.) | 32 | 4
| Intranet Manual | 16 | 2
System features
| Authentication & authorization | 6 | 0.75
| Auditing & logging | 6 | 0.75
| Exception handling | 6 | 0.75
| Manage files and folders | 6 | 0.75
| Generate thumbnail for videos and images | 6 | 0.75
| Automatic backup |  | 0
| Subdomaining or domaining |  | 0
Quality Assurance
| QA & Bug Fixing | 93 | 11.625
| UAT | 16 | 2
| Deployment per instance | 8 | 1
| Total Effort | 533.7 | 66.7125
Assumptions
Pre defined format for print and format will be designed in HTML and printed on plain paper
SMS gateway will be procured by client
Responsive web application
Does not include payment gateway integration
Application will be deployed once
Additional cost for redeployment to new domain (Domain registration+ deployment charges)
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118