## Survey Application
| Ajman Port and Customs |  | 2018-02-20
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 48 | 48 | 100 | 96
2 | Project Management | 80 | 10 | Jr Developer | 1 | 48 | 48
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 10 | 10
4 | Complete running prototype | 32 | 4 | BA | 1 | 10 | 10
| Functional Spec | 24 | 3 | Tech writer | 0 | 4 | 0
| Development |  |  | QA | 2 | 18 | 36
|  |  |  | Total |  |  | 156
1 | SMS and Email Notifications on certain checkpoints and movement | 16 | 2
2 | Optical Character Recognition, enabling customers to upload documents and based on intelligent label identification technologies will auto-fill defined fields in the e-declaration web-form | 88 | 11 |  |  |  |  | <--- This would be the minimum time required
3 | Customer Registration page, enabling a new user to register and submit all the necessary requirements online. | 16 | 2 | Total Delivery days | 80 | 4
4 | Auto validation, for every declaration type will auto validate and define mandatory fields, mandatory documents and ad-hoc documents that need to be submitted to the authorities to avoid unforeseeable delays in releasing cargo/shipment | 80 | 10 | Total Effort | 156 | (+1 Day deployment)
5 | Internal task assigning, tracking, and monitoring | 40 | 5
6 | E-Invoicing (automated charges) | 40 | 5
7 | Payment Gateway integration | 24 | 3
8 | Security Modules for OTP | 24 | 3
9 | API Integration and transaction encryption | 40 | 5
10 | Content Management System | 64 | 8
11 | Integrate-able platform with different systems | 64 | 8
12 | EDI uploads | 40 | 5
13 | User Management | 32 | 4
14 | Master Tables (Customer, Charge, Supplier, Contracts, etc) | 48 | 6
15 | Service Masters | 6 | 0.75
16 | Tariff Master | 6 | 0.75
17 | HS Codes Master | 6 | 0.75
18 | Port Master | 6 | 0.75
19 | Country Master | 6 | 0.75
20 | Currency Master | 6 | 0.75
21 | Freight Master | 6 | 0.75
22 | Voyage Master | 6 | 0.75
23 | Container Master | 6 | 0.75
24 | Insurance Master | 6 | 0.75
25 | Document Master | 12 | 1.5
26 | Document Repository | 12 | 1.5
27 | Workflow based System | 48 | 6
28 | BI reporting | 40 | 5
3 | Exception handling | 4 | 0.5
| User Manual | 0 | 0
| Document Archival | 8 | 1
Quality Assurance
| QA & Bug Fixing | 280 | 35
| UAT | 8 | 1
| Deployment | 8 | 1
| Total Effort | 1288 | 161 | 8.05
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions

## Sheet1
SMS and Email Notifications on certain checkpoints and movement
Optical Character Recognition, enabling customers to upload documents and based on intelligent label identification technologies will auto-fill defined fields in the e-declaration web-form
Customer Registration page, enabling a new user to register and submit all the necessary requirements online.
Auto validation, for every declaration type will auto validate and define mandatory fields, mandatory documents and ad-hoc documents that need to be submitted to the authorities to avoid unforeseeable delays in releasing cargo/shipment
Internal task assigning, tracking, and monitoring
E-Invoicing (automated charges)
Payment Gateway integration
Security Modules for OTP
API Integration and transaction encryption
Content Management System
Integrate-able platform with different systems
EDI uploads
User Management
Master Tables (Customer, Charge, Supplier, Contracts, etc)
Service Masters
Tariff Master
HS Codes Master
Port Master
Country Master
Currency Master
Freight Master
Voyage Master
Container Master
Insurance Master
Document Master
Document Repository
Workflow based System
BI reporting