## Survey Application
| Ajman Port and Customs |  | 2018-02-20
Tuesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 8
1 | Business analysis | 32 | 4 | Sr Developer | 1 | 69 | 69 | 138.25 | 139
2 | Project Management | 110.6 | 13.825 | Jr Developer | 1 | 70 | 70
3 | Project Documentation (SRS, Scope, WBS etc.) | 24 | 3 | PM | 1 | 13.825 | 13.825
4 | Complete running prototype with branding guidelines | 64 | 8 | BA | 1 | 10 | 10
| User manuals, help etc | 32 | 4 | Tech writer | 1 | 4 | 4
| Functional Spec | 24 | 3 | QA | 2 | 24.6937 | 49.3875
| Development |  |  | Total |  |  | 224.2125
1 | SMS and Email Notifications on certain checkpoints and movement | 16 | 2 |  |  |  |  | <--- This would be the minimum time required
2 | Optical Character Recognition, enabling customers to upload documents and based on intelligent label identification technologies will auto-fill defined fields in the e-declaration web-form | 88 | 11 | Total Delivery days | 112.6937 | 5.6347
3 | Customer Registration page, enabling a new user to register and submit all the necessary requirements online. | 16 | 2 | Total Effort | 224.2125 | (+1 Day deployment)
4 | Auto validation, for every declaration type will auto validate and define mandatory fields, mandatory documents and ad-hoc documents that need to be submitted to the authorities to avoid unforeseeable delays in releasing cargo/shipment | 80 | 10
5 | Internal task assigning, tracking, and monitoring | 40 | 5
6 | E-Invoicing (automated charges) | 40 | 5
7 | Payment Gateway integration | 24 | 3
8 | Security Modules for OTP | 24 | 3
9 | API Integration and transaction encryption | 40 | 5
10 | Content Management System | 64 | 8
11 | Integrate-able platform with different systems | 64 | 8
12 | EDI uploads | 40 | 5
13 | User Management | 32 | 4
14 | Master Tables (Customer, Charge, Supplier, Contracts, etc) | 48 | 6
15 | Service Masters | 6 | 0.75
16 | Tariff Master | 6 | 0.75
17 | HS Codes Master | 6 | 0.75
18 | Port Master | 6 | 0.75
19 | Country Master | 6 | 0.75
20 | Currency Master | 6 | 0.75
21 | Freight Master | 6 | 0.75
22 | Voyage Master | 6 | 0.75
23 | Container Master | 6 | 0.75
24 | Insurance Master | 6 | 0.75
25 | Document Master | 12 | 1.5
26 | Document Repository | 12 | 1.5 |  |  | .
27 | Workflow based System | 48 | 6 |  |  | Transaction corrections, adjustments and cancellations
28 | certification Requirments (Bill of Lading, Delivery Order, Packing list, Invoice, Certificate of Origin | 0 | 0 |  |  | Certification requirments
29 | Document Archival | 8 | 1 |  |  | Legal & Regulatory requirment
30 | BI reporting | 40 | 5 |  |  | Billing and warehousing systems
31 | Customer | 12 | 1.5 |  |  | ntegration with Orbits System, WMS, FTA, Municipality, TOS, Oracle 11g Database
32 | Internal User | 12 | 1.5
33 | Management | 12 | 1.5
34 | Administration | 12 | 1.5
35 | Declarations submitted by customer | 12 | 1.5 | 11.2231
36 | Declarations submitted by date range | 12 | 1.5
37 | Declarations submitted by bill type | 12 | 1.5
38 | Declarations submitted by country | 12 | 1.5
39 | Declarations submitted by HS Code | 12 | 1.5
40 | Declarations submitted by Shipping Line | 12 | 1.5
41 | Declarations submitted by Feeder | 12 | 1.5
42 | Declarations submitted by a combination of xx categories | 12 | 1.5
43 | Other reports | 24 | 3
44 | BI Like Charts and Graphs | 24 | 3
| System Features |  | 0
45 | Exceptions | 6 | 0.75
46 | Auditing and logging | 8 | 1
47 | OTP | 8 | 1
48 | Security (SQL, SSL etc…) | 16 | 2
| Authentication and authorization | 8 | 1
| ntegration with Orbits System, WMS, FTA, Municipality, TOS, Oracle 11g Database | 40 | 5
| Encryption | 32 | 4 |  |  | -
Quality Assurance
| QA & Bug Fixing | 387.1 | 48.3875
| UAT | 8 | 1
| Deployment | 8 | 1
| Total Effort | 1795.7 | 224.4625
All the forms and a sample set of questions should be shared to get a more accurate estimate
Assumptions
-
-
-
-

## Sheet1
SMS and Email Notifications on certain checkpoints and movement
Optical Character Recognition, enabling customers to upload documents and based on intelligent label identification technologies will auto-fill defined fields in the e-declaration web-form
Customer Registration page, enabling a new user to register and submit all the necessary requirements online.
Auto validation, for every declaration type will auto validate and define mandatory fields, mandatory documents and ad-hoc documents that need to be submitted to the authorities to avoid unforeseeable delays in releasing cargo/shipment
Internal task assigning, tracking, and monitoring
E-Invoicing (automated charges)
Payment Gateway integration
Security Modules for OTP
API Integration and transaction encryption
Content Management System
Integrate-able platform with different systems
EDI uploads
User Management
Master Tables (Customer, Charge, Supplier, Contracts, etc)
Service Masters
Tariff Master
HS Codes Master
Port Master
Country Master
Currency Master
Freight Master
Voyage Master
Container Master
Insurance Master
Document Master
Document Repository
Workflow based System
BI reporting