## Alxandre
| Alexandre |  | Sep 27 2017
Wednesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 1.5 | 1.5
2 | Functional Specification | 8 | 1 | Sr Developer | 1 | 13.5 | 13.5 | 13.5 | 13.5
3 | Project Management | 10.8 | 1.35 | Jr Developer | 1 | 0 | 0
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) |  | 0 | PM | 1 | 1.35 | 1.35
5 | Complete running prototype | 12 | 1.5 | BA | 1 | 2 | 2
| Development |  |  | QA | 2 | 2.525 | 5.05
| Admin |  |  | Total |  |  | 23.4
6 | Manage product type | 4 | 0.5
7 | Manage product lines | 4 | 0.5 | Total Delivery days | 19.525
8 | Manage products | 4 | 0.5 | Total Effort | 23.4 | +1 deployment
9 | manage Countries | 4 | 0.5
10 | Manage Shops | 8 | 1
11 | Manage Distributors | 12 | 1.5 | [6 empty] | #REF!
| Manage users within distributors | 8 | 1 | [5 empty] | 0
12 | Manage distributor Supplies (product type, line, month, product-Qty, Shop name) | 12 | 1.5
| Distributor |  | 0
13 | Login, Forgot password, email validation | 8 | 1
14 | Record monthly sales using pdt type, line & pdt, month, qty sold, shop, country etc | 16 | 2
| Report |  | 0
15 | monthly report by product (distributed, sold etc) | 8 | 1
16 | monthly report by distributor | 8 | 1
17 | Other reports (@ 4hrs per report X 6) | 0 | 0
Systems
18 | Roles / Entitlements | 6 | 0.75
19 | Logging / Auditing | 6 | 0.75 | [5 empty] | 0
Testing & Deployment
20 | Testing | 32.4 | 4.05
21 | UAT | 8 | 1
22 | Deployment | 8 | 1
| Total Effort | 195.2 | 24.4
Estimate Assumptions:
Out of Scope