## Anit Doping Web App
| UK Anti Doping |  | 2018-08-29
Wednesday
Sl. No. | Module | Man Hours | Man Days |  | No | Man Days | Total Effort
| WEB APPLICATION |  |  | Designer | 1 | 7 | 7
1 | Analysis and Planning | 20 | 2.5 | Designer HTML | 2 | 15 | 30
2 | SRS | 20 | 2.5 | Sr Developer | 1 | 14 | 14
3 | Functional Specification | 20 | 2.5 | Jr Developer | 1 | 30 | 30
4 | HTML Prototype | 32 | 4 | Hybrid Mobile App | 1 | 29 | 29
5 | UIUX - Logo Creation (3 versions - 3edits only) | 40 | 5 | PM | 1 | 8 | 8
6 | Development and Production |  |  | BA | 1 | 2.5 | 2.5
7 | Set up development environment and server - php codeigniter | 0 | 0 | Tech writer | 1 | 5 | 5
8 | Super Admin - |  |  | QA | 2 | 12 | 24
9 | Dashboard | 4 | 0.5 | Total |  |  | 149.5
10 | Manage Roles & Permissions | 6 | 0.75
11 | Manage Users | 8 | 1
12 | Manage Logs | 4 | 0.5
13 | Manage Masters | 12 | 1.5 | Total Delivery days | 64
14 | Reports (3) | 20 | 2.5 | Total Effort | 149.5 | (+1 Day deployment)
15 | Management |  | 0
16 | Dashboard | 4 | 0.5 | implementing AMP | Not sutable for our application |  |  | JavaScript & CSS Limitations, Implementation Is Not Straightforward
17 | Manage Clubs | 8 | 1 | implementing CDN | 4 Days Extra |  |  | Only for Static content images
18 | Manage Doctors | 12 | 1.5
19 | Manage Inspectors | 12 | 1.5
20 | Manage TUE Requests | 4 | 0.5
21 | Manage Clubs/Player DB | 4 | 0.5
22 | Reports (3) | 4 | 0.5
23 | Clubs |  | 0
24 | Dashboard | 4 | 0.5
25 | Manage Players | 8 | 1
26 | Reports (3) | 4 | 0.5
27 | TUE Module |  | 0
28 | View TUE Requests | 5 | 0.625
29 | Approve/Reject Requests | 4 | 0.5
30 | Inspection |  | 0
31 | View Players Whereabout | 4 | 0.5
32 | Conduct Inspection | 4 | 0.5
33 | Doctors |  | 0
34 | View TUE Requests | 4 | 0.5
35 | Update Medical Reports for TUE | 5 | 0.625
36 | API Development ( Mobile Application) | 20 | 2.5
37 | Work Flow |  | 0
38 | TUE Module | 25 | 3.125
39 | Whereabouts | 20 | 2.5
40 | Testing and training |  | 0
41 | Test for full functionality on all major and active browsers | 110 | 13.75
40 | PM | 40 | 5
42 | Total | 491 | 61.375
Assumptions
Languages : English only
Template will be purchased by the client
The above estimation can be change based on the detailed requirement

## Website
| UK Anti Doping |  | 2018-08-29
Wednesday
Sl. No. | Module | Man Hours | Man Days
WEBSITE
1 | Analysis and Planning | 0 | 0
2 | SRS | 16 | 2
3 | Functional Specification | 16 | 2
4 | HTML Prototype from purchased template (English & Arabic) | 205 | 25.625 | Please check the "Design UIUX" tab for more details
5 | Development and Production |  | 0
6 | Set up development environment and server - PHP - Codeignitor | 0
7 | Super Admin - |  | 0
8 | Dashboard | 4
9 | Manage Content | 16 | 2
10 | About US |  | 0
11 | Anti-doping Rule Violations |  | 0
12 | Medication & Substances |  | 0
13 | Therapeutic Usage Exemptions |  | 0
14 | Anti-doping |  | 0
15 | Awareness & Training Mtrls |  | 0
16 | Privacy Policy |  | 0
17 | Manage News | 8 | 1
18 | Manage Events | 6 | 0.75
19 | Manage Gallery | 8 | 1
20 | Manage FAQ | 6 | 0.75
21 | Manage Webinar (Youtube URL) | 4 | 0.5
22 | Manage Home Slider | 8 | 1
23 | Contact Us | 8 | 1
24 | Cilent Area |  | 0
25 | Home | 8 | 1
26 | News | 6 | 0.75
27 | Gallery | 6 | 0.75
28 | Contact Us | 4 | 0.5
29 | FAQ | 4 | 0.5
30 | Content Pages | 12 | 1.5
31 | About US |  | 0
32 | Anti-doping Rule Violations |  | 0
33 | Medication & Substances |  | 0
34 | Therapeutic Usage Exemptions |  | 0
35 | Anti-doping |  | 0
36 | Awareness & Training Mtrls |  | 0
37 | Privacy Policy |  | 0
38 | Webinar | 4 | 0.5
39 | Footer Links | 4 | 0.5
40 | Multi Language (Arabic) | 40 | 5
41 | Testing and training |  | 0
42 | Test for full functionality on all major and active browsers | 30 | 3.75
43 | Total | 423 | 52.875
Assumptions
No Sign Up Form
All the content pages have only one image & one page Content area.
Languages : English & Arabic only
Template will be purchased by Client
The above estimation can be change based on the detailed requirement

## Mobile -hybrid
| UK Anti-Doping Project |  | 2018-08-29
Wednesday
# | Module | Hours | Man Days
4 | Development |  | 0
5 | Basic Setup | 6 | 0.75
25 | Home | 10 | 1.25
26 | News | 8 | 1
27 | Gallery | 8 | 1
28 | Contact Us | 6 | 0.75
29 | FAQ | 4 | 0.5
30 | Content Pages | 20 | 2.5
31 | About US |  | 0
32 | Anti-doping Rule Violations |  | 0
33 | Medication & Substances |  | 0
34 | Therapeutic Usage Exemptions |  | 0
35 | Anti-doping |  | 0
36 | Awareness & Training Mtrls |  | 0
37 | Privacy Policy |  | 0
38 | Webinar | 4 | 0.5
6 | Login Page | 8 | 1
7 | Create TUE Request | 8 | 1
8 | Online Payment | 42 | 5.25
9 | View TUE Status | 8 | 1
10 | Define Whereabouts | 8 | 1
11 | App Creation
12 | Android App | 20 | 2.5
13 | IOS App | 24 | 3
14 | Testing |  | 0
15 | Testing | 48 | 6
| Total effort(Android & IOS) | 232 | 29
Assumptions
Languages : English only
The above estimation can be change based on the detailed requirement
All the content pages have only one image & one page Content area.
Cons of Building a Hybrid App
Potential Lagging
Only Online Access

## Design UIUX
UK Anti-Doping Project
2018-08-29
Wednesday
Sl. No. | Module | Hours | Man Days
CMS Module
1 | Admin Module |  | 0
2 | Login |  | 0
3 | Login | 2 | 0.25
4 | Registration Verification |  | 0
5 | Search, No. of Users, View user details | 6 | 0.75
6 | Allotment of Doctors for Players Request
7 | List of Request, View Doctors Profile | 4 | 0
8 | Website Module
9 | Home | 12 | 1.5
10 | About Us |  | 0
11 | About UAE AD committee | 6 | 0.75
12 | Governance | 4 | 0.5
13 | Policies | 4 | 0.5
14 | Strategic objectives | 2 | 0.25
15 | Global frame ware | 2 | 0.25
16 | Services | 4 | 0.5
17 | News |  | 0
18 | Display, Categorization and Filtering | 12 | 1.5
19 | Gallery |  | 0
20 | Listing, Filtering, play video/Audio on Selection | 8 | 1
21 | FAQs |  | 0
22 | FAQ (Display only) | 2 | 0.25
23 | Contact Us | 4 | 0.5
24 | Anti-Doping Rule Violations |  | 0
25 | About ADRVs | 2 | 0.25
26 | Current Sanction (Table)(Main listing,Sub listing,Filtering) | 6 | 0.75
27 | Rule Violation Process (Main listing,Sub listing,Filtering) | 6 | 0.75
28 | Athlete Counseling(Main listing,Sub listing,Filtering) | 6 | 0.75
29 | World Anti-Doping Code(Main listing,Sub listing,Filtering) | 6 | 0.75
30 | Medications & Substances | 6 | 0.75
31 | Medication & substances list(display only) |  | 0
32 | Supplements(display only) |  | 0
33 | Prohibited list(display only) |  | 0
34 | TUE (Therapeutic usage exemptions) | 10 | 1.25
35 | About TOE (In-page Hyperlinks) |  | 0
36 | TUE Application form & Payment page |  | 0
37 | Check TUE status |  | 0
38 | Anti-Doping | 8 | 1
39 | Code |  | 0
40 | Testing |  | 0
41 | Whereabout |  | 0
42 | Awareness & Training Materials (Video, brochure, photos, text) | 12 | 1.5
43 | Authalic Zone |  | 0
44 | Coaches |  | 0
45 | Parents |  | 0
46 | Resources (Links) |  | 0
47 | Webinar | 12 | 1.5
48 | Discussion board |  | 0
49 | Programs |  | 0
50 | Events |  | 0
51 | User Profile | 12 | 1.5
52 | Basic Details |  | 0
53 | Location Submission (only for Athlete) |  | 0
54 | Request Submission to Admin for approval of medicines/treatment (only for Athlete) |  | 0
55 | Total Effort | 158 | 19.75
Note:-
The effort is based on template(Theme)
For Arabic layout: 30% effort of English
56 | Total Effort | 205.4 | 25.675