## Supplier Portal
Balmer Lawrie | Nov 27 2017
Mon
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 40 | 5 | 5
Functional Specification | 32 | 4 | Jr Developer | 1 | 272 | 34 | 34 | 68 | 68
Project Management | 50.4 | 6.3 | Sr Developer | 1 | 272 | 34 | 34
UI/UX/Prototype | 40 | 5 | PM | 1 | 50.4 | 6.3 | 6.3
Development |  |  | QA | 2 | 108.8 | 13.6 | 27.2
BL UAE Supplier Portal |  |  | BA | 1 | 64 | 8 | 8 | 916
Omega Portal Dashboard |  |  | Total |  | 743.2 |  | 114.5
Purchase Module
Generate Requirement from Omega | 8 | 1 | Total Delivery days | 55.6
Import PO to Omega from portal | 8 | 1 | Total Man day Effort | 114.5
Make GRN in Omega | 8 | 1
P.O revision in Omega | 8 | 1 |  |  |  |  | 9160
Revised P.O approval in Omega | 8 | 1
Payment in Omega | 16 | 2
Supplier evaluation in Omega | 8 | 1
Additional Info to supplier in same enquiry | 8 | 1
Supplier Portal Dashboard for all users
BL Admin
BL Purchase login | 4 | 0.5
Templates for uploading enquiry | 16 | 2
Reuse Previous templates | 6 | 0.75
Floating Enquiry in portal (in predefined template) | 8 | 1
Enquiry assignment and intimation to clients | 8 | 1
Supplier credential verification & Registration in portal | 8 | 1
Supplier master | 8 | 1
Import Supplier evaluation from Omega | 8 | 1
Evaluation Subjective part in portal | 8 | 1
Enquiry Response evaluation & Finalisation
Enquiry responses from all suppliers ( in prescribed format) | 8 | 1
Repository of responses | 8 | 1
Comparative analysis / reports by portal | 8 | 1
Price negotiaion with short listed suppliers | 8 | 1
Portal for reverse auction | 8 | 1
View the status for reverse auction | 8 | 1
Suppliers responses of reverse auction | 8 | 1
Close reverse auction | 8 | 1
Confirm price & supplier | 8 | 1
Update Final price in supplier portal | 8 | 1
Convert to PO in BL purchase portal | 8 | 1
Multiple P.O to different suppliers in same enquiry | 8 | 1
Price revision | 8 | 1
P.O revision in portla due to price variation | 8 | 1
Shipment / Documentation / Clearing
Shipment details in portal | 8 | 1
Import documents to claim duty exemption in portal | 8 | 1
Enter legalisation, Insurance, Clearing document details | 16 | 2
Material clearing at port | 12 | 1.5
Material transportation to warehouse | 12 | 1.5
BL UAE warehouse
Receive materials at warehouse | 12 | 1.5
GRN update in supplier portals | 10 | 1.25
Variation in received quantity / rejections | 12 | 1.5
P.O revision in portal due to material variation | 12 | 1.5
Payment
Upload payment details in portal | 8 | 1
Supplier Portal for supplier
Supplier Registration / Login
Access to enquiries | 8 | 1
Supplier response to enquiry | 8 | 1
View and confirm P.O by supplier | 8 | 1
Confirm shipment in portal | 8 | 1
Upload export/ shipment document in portal | 8 | 1
Upload invoice in portal by supplier | 8 | 1
View payment details | 8 | 1
System Admin (Users, Roles, authorization, entitlements) | 40 | 5
System services ( logging, auditing, exception handling etc.) | 40 | 5
Reporting and analytics | 40 | 5
Testing & Deployment
Testing | 201.6 | 25.2
UAT | 16 | 2
Deployment | 8 | 1
Total Effort | 924 | 115.5

## Customer Portal
Balmer Lawrie | Nov 27 2017
Mon
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 12 | 1.5 | 1.5
Functional Specification | 8 | 1 | Jr Developer | 1 | 72 | 9 | 9 | 10 | 9
Project Management | 8 | 1 | Sr Developer | 0 | 8 | 1 | 0
UI/UX/Prototype | 12 | 1.5 | PM | 1 | 8 | 1 | 1
Development |  |  | QA | 2 | 16 | 2 | 4
BL UAE Customer Portal |  |  | BA | 1 | 24 | 3 | 3 | 148
|  |  | Total |  | 116 |  | 18.5
Manage customer | 8 | 1
Customer Login | 8 | 1 | Total Delivery days | 14
Select Purchase order | 8 | 1 | Total Man day Effort | 18.5
Display Items for purchase order | 8 | 1
Place qty, date and time for order | 8 | 1 |  |  |  |  | 1480
Update system with order placement | 8 | 1
Reconcile order placement screens (Placed vs Actual) | 8 | 1
Notifications | 8 | 1
Purchase order history | 8 | 1
Application management | 8 | 1
Testing & Deployment
Testing | 24 | 3
UAT | 8 | 1
Deployment | 8 | 1
Total Effort | 164 | 20.5