## EMIS
Educational Management Information System |  | Nov 16 2017
| Somalialand | Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 0 | 0 | 0 | 0 | 0
Project Management | 0 | 0 | Mobile developer | 1 | 0 | 0 | 0
Graphic Design | 16 | 2 | PM | 1 | 16 | 2 | 2
Working Prototype | 16 | 2 | QA | 2 | 2 | 0.25 | 0.5
Development |  |  | Total |  | 50 |  | 6.5 | 52
User Mnagement
Manage User |  |  | Total Delivery days | 4.25
Manage Student Module |  | 0 | Total Man day Effort | 6.5
Basic Details |  | 0
Guardian Details |  | 0
Innediate contact |  | 0
Previous Institutions
Additional details |  | 0
Genarate Transfer Certificate |  | 0
Manage Exam results |  | 0
Manage Student Fees |  | 0
Find Student |  | 0
Course and Batch Module
Settings
Manage Course
Manage Batch
Assign Course
List Batch, Students, Exams
Assign Tutor
Assign Subjects
Promote students
Grade Students
Manage Subjects
Add Normal Subject
Add elective Subject
Exams Module
Set Grading levels
Ranking levels
Class designations
CCE Settings (Continuous and Comprehensive Evaluation)
Basic + Co-Scholastic + Scholastics settings
Create exam
Publish Schedule
Enter marks and publish results
Generate reports
Human Resources Module
0
Testing & Deployment
Testing | 0 | 0
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 60 | 7.5
Assumptions
The application will be a responsive web application
Survey Template | Design | Development