## EMIS
Educational Management Information System |  | Nov 16 2017
| Somalialand | Thursday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 40 | 5 | Designer | 1 | 72 | 9 | 9
Functional Specification | 40 | 5 | Web Developer | 1 | 240 | 30 | 30 | 59.25 | 59.25
Project Management | 47.4 | 5.925 | Sr. developer | 1 | 234 | 29.25 | 29.25 |  |  | 0
Graphic Design | 40 | 5 | PM | 1 | 47.4 | 5.925 | 5.925
Working Prototype | 32 | 4 | BA | 1 | 80 | 10 | 10
Development |  |  | QA | 2 | 89.32 | 11.165 | 22.33 | 852.04
Course and Batch management |  |  | Total |  | 762.72 |  | 106.505
Manage Course (Add, Edit, Delete, View) | 8 | 1
Manage Batch | 8 | 1 | Total Delivery days | 60.165
Select Course | 3 | 0.375 | Total Man day Effort | 106.505
View Batch List -> Select Batch | 3 | 0.375 |  |  |  |  | 6784 | 440960
View Student List -> View Student Profile | 3 | 0.375
View Batch Exams | 3 | 0.375
Create Exams, Connect Exam | 8 | 1
Edit batch | 3 | 0.375
Manage Batch (add subjects & electives, assign tutors) | 8 | 1
Batch Transfer for graduation | 8 | 1
Subject Management
Manage Subjects (Add, Edit, del, view) | 8 | 1
Manage Elective groups | 8 | 1
Add subjects to electives | 3 | 0.375
Assign students | 3 | 0.375
Examination Management
Set Grading Levels | 3 | 0.375
Create Exam | 4 | 0.5
Publish Exam | 4 | 0.5
Enter marks | 3 | 0.375
Publish Results | 3 | 0.375
Connect Exams | 3 | 0.375
Generate Reports | 8 | 1
Ranking Levels | 3 | 0.375
Class Designations | 8 | 1
CCE Settings (Continous & Comprehensive Evaluation) | 8 | 1
Basic Settings, Sholastic Settings, Co-scholastic settings | 8 | 1
Human Resources
Manage Employee | 3 | 0.375
Grade, category, position, department | 3 | 0.375
Add Employee bank | 3 | 0.375
Add Payroll category | 3 | 0.375
Employee Search, View profile | 3 | 0.375
Employee Addmission/ subject Allocation | 3 | 0.375
Emploee attendance , Leave types | 3 | 0.375
Attendance Register | 3 | 0.375
Create Payslip & employee slip | 3 | 0.375
Employee Admission | 3 | 0.375
Basic details, Address details, Bank , Additional Details, Assign roles | 3 | 0.375
Time Table Management
Create TimeTable | 4 | 0.5
Set Class timings & week days | 4 | 0.5
Set Time period, Start and end date, Assign hours | 4 | 0.5
Work Allotment (Assign subjects to teachers) | 4 | 0.5
Create / Edit timetable structure | 4 | 0.5
Teacher Timetable | 4 | 0.5
Institution Time Table (entire timetable for a day) | 4 | 0.5
View Timetables | 4 | 0.5
Create Week Days | 4 | 0.5
Finance Management
Create Fees | 4 | 0.5
Create Master fee category | 4 | 0.5
Particluar for master fee | 3 | 0.375
Fee Discounts | 3 | 0.375
Fee Collection | 3 | 0.375
Fee Defaulters | 3 | 0.375
Fee Submission | 3 | 0.375
Create Fee Structure | 3 | 0.375
Manage Donations | 8 | 1
Asset & Liability Management (Create, delete, edit, view) | 3 | 0.375
Payslip Management | 3 | 0.375
Manage Category | 8 | 1
Auto Transactions | 8 | 1
manual Transactions | 4 | 0.5
Transactions : Add Expense /Income | 4 | 0.5
Reports | 6 | 0.75
Dashboards
Admin Dashboard
Admission | 2 | 0.25
Student Details | 2 | 0.25
Manage Users | 2 | 0.25
Manage News | 2 | 0.25
Manage Exams | 2 | 0.25
Manage Timetable | 2 | 0.25
Manage Attendance | 2 | 0.25
Application Settings | 2 | 0.25
Dashboard Settings | 2 | 0.25
Human Resources | 2 | 0.25
Finance | 2 | 0.25
Employee Dashboard
My Profile | 2 | 0.25
News | 2 | 0.25
leaves | 2 | 0.25
Reminders | 2 | 0.25
Examinations | 2 | 0.25
Human Resources | 2 | 0.25
Library | 2 | 0.25
Student Dashboard
My Profile | 2 | 0.25
campus News | 2 | 0.25
Timetable | 2 | 0.25
Reminders | 2 | 0.25
Academics | 2 | 0.25
Library | 2 | 0.25
Exam Dashboard
Exam Settings (Grading levels, Ranking levels, class designations etc.) | 2 | 0.25
Exam Management (Create exams, enter results, Connect Exams etc.) | 2 | 0.25
Generate Reports | 2 | 0.25
reports center | 2 | 0.25
Messaging System
Inbox | 8 | 1
Compose message | 8 | 1
Create Reminders | 8 | 1
Leave Management
Apply for leave | 8 | 1
Leave approval | 8 | 1
Leave status | 8 | 1
My Leaves | 3 | 0.375
Calender & Events
Create Events | 3 | 0.375
Calender view | 3 | 0.375
Payslip Management
Payslip generator | 3 | 0.375
Payslip reverter | 3 | 0.375
Payslip Approval | 3 | 0.375
DepartmentWise Payslip | 3 | 0.375
Personal Payslip | 3 | 0.375
Reject Payslip | 3 | 0.375
Analytics and Reports
Exam Wise Reports | 4 | 0.5
Subjectwise report | 4 | 0.5
Grouped exam reports | 4 | 0.5
Archived student reports | 4 | 0.5
Student Rankings per subject | 4 | 0.5
Student Rankings per batch | 4 | 0.5
Student rankings per course | 4 | 0.5
Student rankings per school | 4 | 0.5
Student rankings per attendance | 4 | 0.5
Ranking level reports | 4 | 0.5
View Transcripts | 4 | 0.5
Combined reports | 4 | 0.5
Exam Workflow
Configure general settings( School info, Attendance, Financial yr etc.) | 8 | 1
Add course, subject with credit hours | 8 | 1
GPA/CGPA,/CWA calculation algorithm | 8 | 1
Quality Analysis
Testing & Bug Fixing | 170.64 | 21.33
Business Validation | 8 | 1
Deployment | 8 | 1
Total Effort | 860.04 | 107.505