## Bayara
| Bayara |  | 20/12/2017
Tuesday
| Module | Hours | Man Days |  | No | Man hours | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 1 | 1
1 | Business analysis | 8 | 1 | Sr Developer | 0 | 0 | 0 | 0 | 13 | 13
2 | Project Management | 10.4 | 1.3 | Jr Developer | 1 | 104 | 13 | 13
3 | Project Documentation (SRS.) | 8 | 1 | PM | 1 | 10.4 | 1.3 | 1.3
4 | Complete running prototype | 8 | 1 | BA | 1 | 16 | 2 | 2
| Development |  | 0 | QA | 2 | 19.6 | 2.45 | 4.9
1 |  |  | 0 | Total |  |  |  | 22.2
2 | Upload Large documents on intranet | 12 | 1.5 | [6 empty] | 0
3 | User Management | 12 | 1.5
4 | Document Metadata | 12 | 1.5 | Total Delivery days | 18.45
5 | Document History ( Access logs, changes, notes, comments etc.) | 12 | 1.5 | Total Effort (in man days) | 22.2 | (+1 Day deployment)
6 | email reminders, SMS etc | 12 | 1.5
7 | Document archival | 12 | 1.5
8 | System features |  | 0
9 | Authentication & authorization | 8 | 1
10 | Auditing & logging | 8 | 1 |  |  | ~$@10 | 1776
11 | Exception handling | 8 | 1
12 | Scheduled jobs | 8 | 1
13 | Workflow management (Review , approval) : Phase 2 | 0 | 0
24 | Quality Assurance
25 | QA & Bug Fixing | 31.2 | 3.9
26 | UAT | 8 | 1
27 | Deployment | 4 | 0.5
28 | Total Effort | 181.6 | 22.7
29
30
31
32
33
34
35
36
37
38 |  |  |  | #REF!
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118