## ForeEver
| Bonus Voucher |  | 2018-08-01
Monday
| Module | Hours | Man Days |  | No | Man hours | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 8 | 1 | 1
1 | Business analysis | 8 | 1 | Sr Developer | 0 | 8 | 1 | 0 | 8.5 | 8.5
2 | Project Management | 8 | 1 | Jr Developer | 1 | 60 | 7.5 | 7.5
3 | Project Documentation (SRS.) | 8 | 1 | PM | 1 | 8 | 1 | 1
4 | Complete running prototype | 8 | 1 | BA | 1 | 16 | 2 | 2
| Development |  |  | QA | 1 | 32 | 4 | 4
| Admin |  |  | Total |  |  |  | 15.5
5 | Create & Manage Users | 8 | 1 | [6 empty] | 0
6 | Import Distributers (upload Excell) | 8 | 1
7 | Create Locations | 6 | 0.75 | Total Delivery days | 14.5
8 | Assign Locations to Cashiers | 4 | 0.5 | Total Effort (in man days) | 15.5 | (+1 Day deployment)
9 | Manage Distributors | 6 | 0.75
System features
10 | Authentication & authorization | 8 | 1
11 | Auditing & logging | 4 | 0.5
12 | Exception handling | 6 | 0.75
Cashier
13 | Login | 4 | 0.5
14 | Lookup distributor | 6 | 0.75
15 | Release amount and print bonus voucher | 8 | 1
16 | Report (various) | 12 | 1.5
Quality Assurance
17 | QA & Bug Fixing | 24 | 3
18 | UAT | 8 | 1
19 | Deployment | 4 | 0.5
| Total Effort | 148 | 18.5
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118