## LMS-Web
| LMS Web |  | April 24 2017
Monday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 10 | 10
2 | Functional Specification | 32 | 4 | Sr Developer | 1 | 22 | 22 | 95 | 96
3 | Project Management | 56 | 7 | Jr Developer | 2 | 37 | 74
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) | 0 | 0 | PM | 1 | 7 | 7
5 | Complete running prototype | 80 | 10 | BA | 1 | 8 | 8
| Development | 0 |  | QA | 2 | 19 | 38
| Registration | 16 | 2 | Total |  |  | 159
6 | Student profile | 0
7 | instructor Profile | 0 |  | Total Delivery days | 73
8 | Admin profile | 0 |  | Total Effort | 159
| Student Workflow | 104 | 13
9 | Student Quick Guide (~6 screens) | 0 |  | Tablet Development
10 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) | 0 |  |  | No | Man Days | Total Effort |  |  | 0
11 | Class Selection (Request for class) | 0 |  | Designer | 1 | 5 | 5 | 50 | 48
12 | instructor Selection (request for instructor) | 0 |  | Sr Developer | 1 | 40 | 40
13 | instructor ratings (Comments and stars) | 0 |  | Jr Developer | 1 | 8 | 8
14 | Submit request | 0 |  | PM | 1 | 7 | 7
15 | Request Timeout | 0 |  | BA | 1 | 4 | 4
16 | Request escalation (to admin and then superadmin) | 0 |  | QA | 2 | 10 | 20
17 | Make payment online via payment processor | 0 |  | Total |  |  | 84
18 | Create calender entry and reminders | 0
19 | Send specific information to instructor | 0 |  | Total Delivery days | 55 | X2 | (IOS+Android)
20 | Attend class online (Record class) | 0 |  | Total Effort | 84
21 | Request clarification or post questions to instructor | 0
22 | Rate instructor & add instructor as favourite | 0 |  | Phone Development |  |  |  | 79 | 79
23 | Access assignment ( Attachments) | 0 |  |  | No | Man Days | Total Effort
24 | Submit assignment (upload assignments, take quizz etc) | 0 |  | Designer | 1 | 5 | 5
25 | Assignment history with grades | 0 |  | Sr Developer | 1 | 25 | 25
26 | Receive Course certificates | 0 |  | Jr Developer | 1 | 54 | 54
| Instructor Workflow | 176 | 22 | PM | 1 | 7 | 7
27 | instructors Quick Guide (~6 screens) | 0 |  | BA | 1 | 8 | 8
28 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating) | 0 |  | QA | 2 | 15.8 | 31.6
29 | CV builder | 0 |  | Total |  |  | 130.6
30 | Billing information | 0
31 | References | 0 |  | Total Delivery days | 74.8 | X2 | (IOS+Android)
32 | Specialization | 0 |  | Total Effort | 130.6
33 | Set availability and calendar | 0
34 | Upload Course content | 0 |  | Cumulative Total for Development (Web, IOS: Phone + iPad, Android: Phone + Tablet)
35 | Links to external sites for reference material | 0 |  | Delivery Days | 80
36 | Accept Student request | 0 |  | Effort | 588.2 | 575
37 | Cancel Request | 0
38 | Update calendar & create reminders | 0
39 | Conduct classes (one on One) | 0 |  | Solution Using Zoom.US
40 | Answer student questions or doubts | 0 |  | Bandwidth Requirement (Per Teacher-Student Pair)
41 | Upload assignments or create quizzes | 0 |  | Instructor-student session in HQ Video | 600 kBPS
42 | Review assigments and assign grade | 0 |  | Instructor-Student Session using VOIP Audio | 80 KBPS
43 | Receive payment | 0 |  | Total Bandwidth | ~800 KBPS
| Admin (principal) Workflow | 64 | 8
44 | Admin Quickguide (~6 screens) | 0 |  | ZOOM API Charges | $100 for 4000 Mins
45 | Upload CV | 0 |  |  | *Better plans available for $500 per month (upwards of 20,000 mins)
46 | Add refernces | 0 |  | *Zoom Supports seamless integration with web and mobile clients
47 | Add billing information | 0
48 | Access and manage student, instructor calenders. | 0 |  | Mobile System requirements for Android
49 | Reassign instructors | 0 |  | ARM processor
50 | Reschedule instructor and student classes | 0 |  | 1 GB RAM
51 | Approve Review | 0 |  | Android 4.0 and above
52 | resolve instructor student issues | 0 |  | Internet Connection
| Super Admin | 64 | 8 | Mobile System requirements for IOS
53 | Manage students | 0 |  | >1 GHZ processor
54 | Manage instructors | 0 |  | IOS 7.0 or later
55 | Manage Admins (principals) | 0 |  | Internet Connection (high Speed Wi-Fi or 4G-LTE)
56 | Manage Courses | 0
57 | re-associate instructors to courses | 0 |  | Cloud recording of Zoom Meetings: $100 /month for 500GB
58 | Dashboard (Active Students, Active instructors, Active courses, edit profile, Messages-pending reviews, Latest ratings) | 0
59 | Post site wide messages or to individuals | 0 |  | Estimated time for integration with mobile or Web app (per instance): 2 - 4 days
60 | Blacklist instructors | 0
61 | Quizz management* | 0
| Parent Workflow | 48 | 6 | Min Monthly recurring charges for using Zoom
62 | register Student | 0 |  | API charges | $100 for 4000 mins
63 | Review grades | 0 |  | Cloud storage option for Video recording | $100 / 500 GB
64 | View student course schedule | 0 |  | Bandwidth Charges | Depends on the Hosting provider
65 | View Messages from Admin, superadmin, instructor | 0
66 | View student calendar | 0 |  | Additional charges to consider
| System Features | 96 | 12 | SSL Certificates
67 | Authentication and authorization | 0 |  | Templates and themes for development
68 | Logging and auditing with notifications | 0 |  | Payment Processor
69 | Payment processing | 0 |  | Templates for reporting & analytics (Ex. HiCharts)
70 | File management | 0
71 | Roles and permissions | 0
72 | Password salting | 0
73 | Email authentication and management | 0
74 | SMS authentication (mobile devices) | 0
75 | Password policy | 0
76 | Cron Jobs for scheduling | 0
77 | Export or email reports | 0
| Reports and Analytics | 80 | 10
78 | Student demographics | 0
79 | Inactive users | 0
80 | Student Activity Summary (Most Active Students) | 0
81 | Student grades Compared to Course Average (Compared to Course Average) | 0
82 | Revenue Generation | 0
83 | Demographic report | 0
84 | Revenue by student | 0
85 | Revenue by instructors | 0
86 | Login statistics (by students and instructors) | 0
87 | Available courses and student enrollment | 0
88 | Available courses and staffing | 0
89 | File utilization by student and instructor | 0
90 | Activity stats summary (logins, total course time spent) | 0
91 | Past due assignments | 0
92 | Course utilization report | 0
93 | Incomplete student teacher sessions | 0
94 | Student-teacher reassignments | 0
95 | Teacher review | 0
96 | Mobile API Development | 112 | 14
97 | Create Deployable installshield solution | 0
| Testing & Deployment | 0
| Testing | 304 | 38
| UAT | 0
| Deployment | 0
| Total Effort | 1264 | 158
| Estimate Assumptions: |  | 1. Recording will not be a column for the report (student , Teacher & Admin), not included in filter. 2. Tutorial for Admin, Teachers & Students - static content 3. Request (teacher) workflow escalation period is hardcoded in DB 4. "Wait for the review different admin to receive the fees" in the admin worflow - Need clarification 5. Technology not considered 6. Customer will procure templates, SSL certificates & Payement processor 7. UI development is 2-4 hrs per screen 8. Effort for deployment not considered 9. Reporting and analytics for mobile devices will be imported from the web 10. Both mobile and tablet have similar design 11. Estimated with default Android and IOS design, Custom design will take more effort 12. Testing will be done in 2 Android Mobiles 13. Testing will be done in 2 Android Tablets 14. Testing will be done in latest versions of Google Chrome, Mozilla Firefox & IE web browsers only 15. Verbat will capture billing information, but will not process the salary payment for tutors or admins
| Out of Scope |  | 1. Zoom integration 2. Payment processing for Teacher 3. Quiz assignmets for students by teacher 4. Documentation & Project planning

## Sheet1
Resource/Skill | June | July | Aug | Sept
Proj. Manager | 42 | 42 | 42 | 42
Architect | 80
Business Analyst | 80 | 15 | 15 | 30
User Experience | 120 | 20 | 20
Team Lead Web | 120 | 100 | 80 | 120
Web Developer | 124 | 160 | 160 | 160 | 1024 | 760
Team Lead Android | 120 | 86 | 80 | 120
Android Developer | 168 | 180 | 180 | 168 | 1102 | 1040 | 336
Team Lead iOS | 120 | 100 | 80 | 120
iOS Developer | 168 | 180 | 180 | 168
Test Lead | 80 | 50 | 80 | 100
QA | 70 | 150 | 150 | 150 | 830 | 720 | 180
sum |  |  |  | 4620 |  |  |  | 920
4600

## LMS-Tablet
| LMS - Tablet |  | April 24 2017
Monday
Sl. No. | Module | Hours | Man Days | Tablet Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 5 | 5
2 | Functional Specification | 16 | 2 | Sr Developer | 1 | 26 | 26 | 50 | 78
3 | Project Management | 56 | 7 | Jr Developer | 1 | 52 | 52
4 | Complete running prototype | 40 | 5 | QA | 2 | 10 | 20
| Development | 0 |  | Total |  |  | 103
| Registration | 0
5 | Student profile | 8 | 1 | Total Delivery days | 67
6 | instructor Profile | 8 | 1 | Total Effort | 103
7 | Admin profile | 8 | 1
| Student Workflow | 0
8 | Student Quick Guide (~6 screens) | 8 | 1
9 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) | 8 | 1
10 | Class Selection (Request for class) | 8 | 1
11 | instructor Selection (request for instructor) | 8 | 1
12 | instructor ratings (Comments and stars) | 8 | 1
13 | Submit request | 8 | 1
14 | Request Timeout | 8 | 1
15 | Request escalation (to admin and then superadmin) | 8 | 1
16 | Make payment online via payment processor | 8 | 1
17 | Create calender entry and reminders | 8 | 1
18 | Send specific information to instructor | 8 | 1
19 | Attend class online (Record class) | 8 | 1
20 | Request clarification or post questions to instructor | 8 | 1
21 | Rate instructor & add instructor as favourite | 8 | 1
22 | Access assignment ( Qizz, Attachments) | 8 | 1
23 | Submit assignment (upload assignments, take quizz etc) | 8 | 1
24 | Assignment history with grades | 8 | 1
25 | Receive Course certificates | 8 | 1
| Instructor Workflow | 0
27 | instructors Quick Guide (~6 screens) | 8 | 1
28 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating) | 8 | 1
29 | CV builder | 8 | 1
30 | Billing information | 8 | 1
31 | References | 4 | 0.5
32 | Specialization | 4 | 0.5
33 | Set availability and calendar | 8 | 1
34 | Upload Course content | 8 | 1
35 | Links to external sites for reference material | 4 | 0.5
36 | Upload Course Video | 8 | 1
37 | Accept Student request | 8 | 1
38 | Cancel Request | 8 | 1
39 | Update calendar & create reminders | 8 | 1
40 | Conduct classes (one on One) | 8 | 1
41 | Answer student questions or doubts | 8 | 1
42 | Upload assignments or create quizzes | 8 | 1
43 | Review assigments and assign grade | 8 | 1
44 | Receive payment | 4 | 0.5
| Admin (principal) Workflow | 0
45 | Admin Quickguide (~6 screens) | 8 | 1
46 | Upload CV | 4 | 0.5
47 | Add refernces | 8 | 1
48 | Add billing information | 8 | 1
49 | Access and manage student, instructor calenders. | 8 | 1
50 | Reassign instructors | 16 | 2
51 | Reschedule instructor and student classes | 8 | 1
52 | Approve Review | 8 | 1
53 | resolve instructor student issues | 8 | 1
| Parent Workflow | 0
54 | register Student | 4 | 0.5
55 | Review grades | 8 | 1
56 | View student course schedule | 4 | 0.5
57 | View Messages from Admin, superadmin, instructor | 8 | 1
58 | View student calendar | 4 | 0.5
| Reports and Analytics | 0
59 | Student demographics | 0
60 | Inactive users | 0
61 | Student Activity Summary (Most Active Students) | 0
62 | Student grades Compared to Course Average (Compared to Course Average) | 0
63 | Revenue Generation | 0
64 | Demographic report | 0
65 | Revenue by student | 0
66 | Revenue by instructors | 0
67 | Login statistics (by students and instructors) | 0
68 | Available courses and student enrollment | 0
69 | Available courses and staffing | 0
70 | File utilization by student and instructor | 0
71 | Activity stats summary (logins, total course time spent) | 0
72 | Past due assignments | 0
73 | Course utilization report | 0
74 | Incomplete student teacher sessions | 0
75 | Student-teacher reassignments | 0
76 | Teacher review | 0
77 | Create Deployable installshield solution | 0
| Testing & Deployment | 0
78 | Testing | 160 | 20
79 | UAT
80 | Deployment | 0
| Total Effort | 688 | 86
Assumptions
Both mobile and tablet are in same design
Reports and Analytics will be taken care in web part
Live streaming is not considered
Estimated with android default design, Custom design will take more effort

## LMS-Phone
| LMS - Phone |  | April 24 2017
Monday
Sl. No. | Module | Hours | Man Days | LMS-Phone
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 32 | 4 | Designer | 1 | 5 | 5
2 | Functional Specification | 32 | 4 | Sr Developer | 1 | 29 | 29 | 79 | 83
3 | Project Management | 56 | 7 | Jr Developer | 1 | 54 | 54
4 | Complete running prototype | 40 | 5 | QA | 2 | 15.8 | 31.6
| Development | 0 |  | Total |  |  | 119.6
| Registration | 0
5 | Student profile | 8 | 1 | Total Delivery days | 74.8
6 | instructor Profile | 8 | 1 | Total Effort | 119.6
7 | Admin profile | 8 | 1
| Student Workflow | 0
8 | Student Quick Guide (~6 screens) | 8 | 1
9 | Dashboard (My courses, My grades, Favourite instructors, Messages, Preferences, edit profile, Calendar and course schedule) | 24 | 3
10 | Class Selection (Request for class) | 16 | 2
11 | instructor Selection (request for instructor) | 8 | 1
12 | instructor ratings (Comments and stars) | 8 | 1
13 | Submit request | 12 | 1.5
14 | Request Timeout | 8 | 1
15 | Request escalation (to admin and then superadmin) | 24 | 3
16 | Make payment online via payment processor | 32 | 4
17 | Create calender entry and reminders | 16 | 2
18 | Send specific information to instructor | 16 | 2
19 | Attend class online (Record class) | 16 | 2
20 | Request clarification or post questions to instructor | 16 | 2
21 | Rate instructor & add instructor as favourite | 12 | 1.5
22 | Access assignment ( Qizz, Attachments) | 8 | 1
23 | Submit assignment (upload assignments, take quizz etc) | 8 | 1
24 | Assignment history withy grades | 12 | 1.5
25 | Receive Course certificates | 8 | 1
| Instructor Workflow | 0
26 | instructors Quick Guide (~6 screens) | 8 | 1
27 | Dashboard (My Students, Messages, Preferences, edit profile, Calendar and course schedule, Rating) | 32 | 4
28 | CV builder | 32 | 4
29 | Billing information | 8 | 1
30 | References | 8 | 1
31 | Specialization | 8 | 1
32 | Set availability and calendar | 8 | 1
33 | Upload Course content | 8 | 1
34 | Links to external sites for reference material | 8 | 1
35 | Upload Course Video | 8 | 1
36 | Accept Student request | 12 | 1.5
37 | Cancel Request | 8 | 1
38 | Update calendar & create reminders | 8 | 1
39 | Conduct classes (one on One) | 8 | 1
40 | Answer student questions or doubts | 8 | 1
41 | Upload assignments or create quizzes | 8 | 1
42 | Review assigments and assign grade | 8 | 1
43 | Receive payment | 8 | 1
| Admin (principal) Workflow | 0
44 | Admin Quickguide (~6 screens) | 16 | 2
45 | Upload CV | 8 | 1
46 | Add refernces | 16 | 2
47 | Add billing information | 16 | 2
48 | Access and manage student, instructor calenders. | 16 | 2
49 | Reassign instructors | 8 | 1
50 | Reschedule instructor and student classes | 8 | 1
51 | Approve Review | 8 | 1
52 | resolve instructor student issues | 8 | 1
| Parent Workflow | 0
53 | register paent | 8 | 1
54 | Review grades | 16 | 2
55 | View student course schedule | 8 | 1
56 | View Messages from Admin, superadmin, instructor | 16 | 2
57 | View student calendar | 8 | 1
| Reports and Analytics | 0
58 | Student demographics | 0
59 | Inactive users | 0
60 | Student Activity Summary (Most Active Students) | 0
61 | Student grades Compared to Course Average (Compared to Course Average) | 0
62 | Revenue Generation | 0
63 | Demographic report | 0
64 | Revenue by student | 0
65 | Revenue by instructors | 0
66 | Login statistics (by students and instructors) | 0
67 | Available courses and student enrollment | 0
68 | Available courses and staffing | 0
69 | File utilization by student and instructor | 0
70 | Activity stats summary (logins, total course time spent) | 0
71 | Past due assignments | 0
72 | Course utilization report | 0
73 | Incomplete student teacher sessions | 0
74 | Student-teacher reassignments | 0
75 | Teacher review | 0
76 | Create Deployable installshield solution | 0
| Testing & Deployment | 0 |  |  | S
| Testing | 252.8 | 31.6
UAT
| Deployment | 0
| Total Effort | 1044.8 | 130.6
Assumptions
Both mobile and tablet are in same design
Reports and Analytics will be taken care in web part
Live streaming is not considered
Estimated with android default design, Custom design will take more effort