## DrivenShare
| Drive And Share |  | 2017-05-08
Monday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 10 | 10
2 | Functional Specification | 8 | 1 | Sr Developer | 1 | 13 | 13 | 32.75 | 33
3 | Project Management | 8 | 1 | Jr Developer | 1 | 20 | 20
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) | 0 | 0 | PM | 1 | 1 | 1
5 | Complete running prototype | 80 | 10 | BA | 1 | 2 | 2
| Development |  | 0 | QA | 2 | 7.55 | 15.1
1 | Registration + ID Proof | 16 | 2 | Total |  |  | 61.1
2 | Login | 4 | 0.5
3 | Dashboard | 3 | 0.375 | Total Delivery days | 38.55
4 | Car Leasing Service (main Tab) | 4 | 0.5 | Total Effort | 61.1 | (+1 Day deployment)
5 | 10 Months Teachers Deals | 4 | 0.5
6 | Corporate Request Form | 3 | 0.375
7 | 1 Year Lease Special Deal request | 3 | 0.375 | [6 empty] | #REF!
8 | 2 Years lease special Deal request | 3 | 0.375 | [5 empty] | 0
9 | 3 Years lease special Deal request | 3 | 0.375
10 | 10 Months Teachers Deal request | 3 | 0.375
11 | Car Rental Services (Main Tab) | 4 | 0.5
12 | 6 Month Special Rental Rate request | 4 | 0.5
13 | 3 Months Special Rental Rate request | 4 | 0.5
14 | Monthly Special Rental Rate Request | 3 | 0.375
15 | Weekly Special Promos Request | 3 | 0.375
16 | Chauffer / Transfer Request: (Main Tab) | 4 | 0.5
17 | Corporate request form | 4 | 0.5
18 | Individual request form | 4 | 0.5
19 | Corporate request form Submit | 4 | 0.5 | [5 empty] | 0
20 | Individual request form Submit | 4 | 0.5
21 | Online Bookings(Main Tab) | 8 | 1
22 | Excess Special Discounted online rates linked to our website | 4 | 0.5
23 | International car Rental bookings (Main Tab) | 4 | 0.5
24 | Diversion to our site with Dedicated discounted rates | 4 | 0.5
25 | Send Request to our service agent | 4 | 0.5
26 | Car Sharing (Main Tab) | 3 | 0.375
27 | Corporate Sharing Request Form | 3 | 0.375
28 | Individual Sharing Request Form | 3 | 0.375
29 | Drive and share Request Form | 4 | 0.5
30 | Garage services (Main Tab) | 3 | 0.375
31 | Air Condition Repairs Request | 3 | 0.375
32 | Body & Paint Repairs Request | 3 | 0.375
33 | Electrical Repairs Request | 3 | 0.375
34 | Fleet Management request | 3 | 0.375
35 | Lube Services & Quick Repairs Request | 3 | 0.375
36 | Mechanical Service & Repairs Request | 3 | 0.375
37 | Universal Auto Garage Roadside Assistance Request | 4 | 0.5
38 | Used Cars (Main Tab) | 3 | 0.375
39 | Used Cars Search by Make & Model | 12 | 1.5
40 | Drive To Own | 3 | 0.375
41 | Bidding option for dealers | 8 | 1
42 | Online Chat (Main Tab) | 40 | 5
43 | Locations | 6 | 0.75
44 | Request Delivery | 4 | 0.5
45 | Payment processing & integration | 40 | 5
47 | Quality Assurance |  | 0
48 | QA | 104.8 | 13.1
49 | UAT | 16 | 2
50 | Deployment | 8 | 1
51 | Total Effort | 494.8 | 61.85
52 | Estimate Assumptions: 4 hour quote per form is based on a maximum of 10 forms / field. Includes form validation and testing. Mobile App cannot accommodate all of the tabs requested by the client. Redesign expected. Approximately 3 hrs/screen for screen design Online booking API to be provided by the client Payment Gateway and API will be provided by the client Client will provide API to display data in the detail pages ex. 3 month special rental rate Quote does not include web site development or web API development