## Coir Board
| Coir Board |  | Nov 01 2017
Wednesday
Sl. No. | Module | Man Hours | Man Days
| Design |  |  |  | No | Man Hours | Man Days
1 | Finalising and purchase of HTML Theme & Images | 64 | 8 | Designer | 0.5 | 1231.2 | 76.95
2 | Design 2 Joomla homepage responsive templates | 64 | 8 | Sr. PHP developer | 1 | 6.5 | 0.8125 | 3.3125 | 93.5
3 | Design sub pages (min 5) |  | 0 | Junior PHP Developer | 1 | 20 | 2.5
4 | Project Management | 74.8 | 9.35 | QA | 1 | 10.5 | 1.3125
5 | SRS + FS | 32 | 4 | Project Manager | 1 |  | 0
| Development |  | 0 | Total |  |  | 49
6 | Application Setup | 8 | 1
7 | Home page with sections (news, Events, Gallery) | 24 | 3
| Common page features | 0 | 0
8 | Language selector | 24 | 3
9 | Email current page | 24 | 3
10 | PDF of current page | 56 | 7
11 | Print current page | 48 | 6
| Search By | 16 | 2
12 | Documents | 0 | 0
13 | Site content | 0 | 0
| Footer pages and links | 0 | 0
14 | Site Map | 8 | 1
15 | Privacy Policy | 4 | 0.5
16 | T&C | 4 | 0.5
17 | Copyright | 4 | 0.5
18 | Usefull Links | 4 | 0.5
19 | Archives | 16 | 2
| Contact US | 0 | 0
20 | Feedback | 0 | 0
21 | Sub Offices ( added via backend using DB) Below offices are replicated using templates | 24 | 3
| Chirayinkeezhu | 0 | 0
| Kollam | 0 | 0
| Alapuzha | 0 | 0
| North Parur | 0 | 0
| Ponnani | 0 | 0
| Kannur | 0 | 0
| Kayamkilam | 0 | 0
| Thrisur | 0 | 0
| Kozhikode | 0 | 0
| Vaikom | 0 | 0
| About US | 0 | 0
22 | Vision n mission | 8 | 1
23 | Org Structure | 8 | 1
| About Coir | 4 | 0.5
24 | Fibre Extraction | 4 | 0.5
25 | Ratt Spinning | 0 | 0
26 | Hand spinning | 0 | 0
27 | Right to Service | 4 | 0.5
28 | Right to information | 8 | 1
29 | Citizens Charter | 8 | 1
30 | Vital Statistics | 16 | 2
| Page Templates | 0 | 0
31 | News | 12 | 1.5
32 | Events | 8 | 1
33 | Sub Office | 16 | 2
34 | Gallery | 16 | 2
35 | Project Offices | 16 | 2
36 | Allied institutions | 16 | 2
37 | Coir Co-operatives | 16 | 2
38 | Downloads | 16 | 2
39 | Exporters | 16 | 2
| Manufacturers | 16 | 2
40 | Downloads | 8 | 1
41 | Circulars | 0 | 0
42 | Gov Orders | 0 | 0
43 | Various forms and applications | 0 | 0
44 | Tenders | 0 | 0
| Important Orders | 0 | 0
45 | Services | 16 | 2
46 | Plan Schemes | 0 | 0
47 | Career | 0 | 0
48 | Articles | 0 | 0
| Projects | 0 | 0
49 | Admin | 0 | 0
50 | Login | 8 | 1
51 | Manage Users | 16 | 2
52 | Editors | 0 | 0
53 | Publishers | 0 | 0
| Add Submenu / Menu (optional) | 16 | 2
54 | Update | 0 | 0
55 | Add Sub Offices | 16 | 2
56 | Add news | 16 | 2
57 | Add events | 16 | 2
58 | Add gallery | 16 | 2
59 | Add Project Offices | 16 | 2
60 | Add Allied institutions | 8 | 1
61 | Add Coir Co-operatives | 8 | 1
62 | Add Exporters | 16 | 2
63 | Add Manufacturers | 16 | 2
| Add Products | 16 | 2
64 | Upload | 0 | 0
65 | Circulars | 4 | 0.5
66 | Gov Orders | 4 | 0.5
67 | Various forms and applications | 24 | 3
68 | Tenders | 8 | 1
69 | Important Orders | 16 | 2
70 | Products | 8 | 1
| Marketing | 4 | 0.5
71 | Quality Analysis (QA) | 224.4 | 28.05
72 | UAT Support & Implementation | 8 | 1
| Live deployment | 8 | 1
| Total Effort | 1223.2 | 152.9
152.9
Assumption
Client will purchase HTML theme
Only one language - English
R&D / Challenges
Integrated with “Outlook Office365”
Active Directory Integration

## Sheet1
About US
Vision n mission
Org Structure
| About Coir | Fibre Extraction
Ratt Spinning
Hand spinning
Right to Service
Right to information
Vital Statistics
Project Offices
Allied institutions
Coir Co-operatives
Exporters
Manufacturers
Downloads (Placeholder for various items)
Circulars
Gov Orders
Various forms and applications
Tenders
Important Orders
Services? (Does this include services from coirboard)
Plan Schemes
Citizen Charter
Contact us
Feedback
Sub Offices (dynamic?)
Chirayinkeezhu
Kollam
Alapuzha
North Parur
Ponnani
Kannur
Kayamkilam
Thrisur
Kozhikode
Vaikom
News | whats New
Events (planned activities)
General
Copyright
T&C
Privacy policy
Useful Links
Cite map
Archives
Gallery
Picture
Video
Search
site content
Forms
Products
Marketing
Site Features
Context sensitive PDF downloads
Print page
Email Page
Bilingual
Administration
Login
Manage users | Editor
Manage roles | Publisher
Menu | Main menu
sub menu
content | Generic pages (text interspersed with images, tables etc)
Templated pages (create template that can be used to create other pages)
template instance (instance of a templated page for end user)
News banner
gallery uploads
document uploads