## DAMAC
Damac Properties Web Conference | Aug 24 2017
Thursday
Module | Man Hours | Man Days | Phase 1
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 48 | 6 | 6
Functional Specification | 8 | 1 | Web Developer | 1 | 350 | 43.75 | 43.75 | 52 | 52
Project Management | 41.6 | 5.2 | Hybrid App Developer | 1 | 66 | 8.25 | 8.25
Graphic Design (Web & Mobile) | 24 | 3 | PM | 1 | 57.6 | 7.2 | 7.2
Working Prototype | 24 | 3 | QA | 2 | 64.4 | 8.05 | 16.1
Development |  |  | Total |  | 586 |  | 81.3 | 650.4
Client side web integration
Get session ID and token from server | 5 | 0.625 | Total Delivery days | 57.8
Connect to the session using token | 6 | 0.75 | Total Man day Effort | 81.3
Publish audio/video streams | 6 | 0.75
Subscribe to audio video stream | 5 | 0.625
listen for session events | 5 | 0.625
Set Up SDK and framework | 5 | 0.625
0
Server side integration with Web service |  | 0
Set up server side SDK and application framework | 6 | 0.75
create sessions in app cloud | 8 | 1
generate tokens for client (Unique URL invite to join the meeting) | 4 | 0.5
send sessions IDS & tokens for clients | 4 | 0.5
Sessions |  | 0
create chatroom session | 6 | 0.75
Connect clients to one another | 8 | 1
send events to clients | 12 | 1.5
Web Client |  | 0
Authentication / requesting permissions | 8 | 1
connecting to session and creating publisher | 8 | 1
initializing subscriber | 5 | 0.625
CSScustomizations | 12 | 1.5
Publishing streams to subscriber | 4 | 0.5
subscribing to other client streams | 3 | 0.375
Adjusting Audio and video | 8 | 1
Customizing UI | 16 | 2
Session Monitoring | 16 | 2
Moderation | 18 | 2.25
Screen Sharing (HTTPS Mandatory) |  | 0
Checking for screen-sharing publishing support | 3 | 0.375
Publishing a stream with a screen-sharing source | 4 | 0.5
Setting the maximum resolution of the stream | 6 | 0.75
Cropping or letter-boxing screen-sharing videos | 8 | 1
Determining the video type ("screen" or "camera") for a stream | 6 | 0.75
Detecting when video dimensions change | 6 | 0.75
Determining when the user stops sharing the screen | 4 | 0.5
Subscribing to screen-sharing streams | 4 | 0.5
Develop Chrome screen sharing extension | 16 | 2
Distributing extensions | 12 | 1.5
Text Messaging |  | 0
Signalling | 5 | 0.625
signal payloads | 6 | 0.75
Signal delivery | 8 | 1
Other Features |  | 0
Archiving | 16 | 2
SIP Iterconnect Internet telephony (VOIP) | 16 | 2
Integration with CRM Application (Send email invites to leads) | 16 | 2
URL encoded meeting invite that uniquely identifies the lead
Exception Handling | 12 | 1.5
Debugging | 0 | 0
Account management | 12 | 1.5
Security | 12 | 1.5
Hybrid app |  | 0
Configure opentok SDK with Cordova | 16 | 2
Migration of Web Application to Hybrid App @ 4.5 hrs / page (avg 10 pages) | 50 | 6.25
0
0
0
0
0
0
Testing & Deployment
Testing | 124.8 | 15.6
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 658.4 | 82.3
Assumptions
The application will be a responsive web application
Assumptions
SIP Gateway for internet telephony
opentok media router
Archiving @$0.035 per minute
SIP Interconnect @ $0.005 per minute
Opentok F/W cost 9.99 / 2000 minutes
HTTPS provided by client
OpenTok Service acquired by client
Apple and android Store development Licensce

## Phase 2
Module | Man Hours | Man Days
Initiation |  |  | Phase 1
Requirements gathering and documentation (SRS) | 8 | 1 |  | No | Man hours | Man Days | Total Effort
Functional Specification | 8 | 1 | Designer | 1 | 48 | 6 | 6
Project Management | 33.6 | 4.2 | Web Developer | 1 | 224 | 28 | 28 | 42 | 42
Graphic Design (Web & Mobile) | 24 | 3 | Hybrid App Developer | 1 | 112 | 14 | 14
Working Prototype | 24 | 3 | PM | 1 | 49.6 | 6.2 | 6.2
Development |  |  | QA | 2 | 51.04 | 6.38 | 12.76
Mobile + Web integration |  |  | Total |  | 484.64 |  | 66.96 | 535.68
Whiteboard Sharing | 28 | 3.5
Link based push notifications | 16 | 2 | Total Delivery days | 40.38
Screen shot sharing | 28 | 3.5 | Total Man day Effort | 66.96
Dial IP Phone | 24 | 3
Polls & surveys | 32 | 4
backend dashboard with reports for managers | 32 | 4
Automatic logic for call routing | 32 | 4
Sticky routing | 16 | 2
Round robin based call allocation | 16 | 2
calender addition for web conference or invite reminders synched with outlook, google etc | 32 | 4
Sharing of documents and videos over video chat | 16 | 2 | [7 empty] | Phase 2
3 minute Intro video before meeting begins | 16 | 2
Submit feedback | 16 | 2
Unique link to resume conversation in the future | 16 | 2
Enable slide shows or share documents | 16 | 2
Testing & Deployment
Testing | 94.08 | 11.76
UAT | 8 | 0.5
Deployment | 8 | 1
Total Effort | 539.68 | 67.46
Assumptions

## Sheet2
https://support.tokbox.com/hc/en-us/articles/204605054-How-do-I-estimate-my-OpenTok-monthly-usage-