## DAMAC
Damac Properties Web Conference | Aug 24 2017
Thursday
Module | Man Hours | Man Days | Phase 1
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 40 | 5 | 5
Functional Specification | 8 | 1 | Web Developer | 1 | 216 | 27 | 27 | 43.25 | 43.25
Project Management | 34.6 | 4.325 | Sr Web Developer | 1 | 130 | 16.25 | 16.25
Graphic Design | 20 | 2.5 | PM | 1 | 50.6 | 6.325 | 6.325
Working Prototype | 20 | 2.5 | QA | 2 | 50.44 | 6.305 | 12.61
Development |  |  | Total |  | 487.04 |  | 67.185 | 537.48
Client side web integration
Get session ID and token from server | 5 | 0.625 | Total Delivery days | 38.305
Connect to the session using token | 6 | 0.75 | Total Man day Effort | 67.185
Publish audio/video streams | 6 | 0.75
Subscribe to audio video stream | 5 | 0.625 |  |  | 120
listen for session events | 5 | 0.625
Set Up SDK and framework | 5 | 0.625
0
Server side integration with Web service |  | 0
Set up server side SDK and application framework | 6 | 0.75
create sessions in app cloud | 8 | 1
generate tokens for client (Unique URL invite to join the meeting) | 4 | 0.5
send sessions IDS & tokens for clients | 4 | 0.5
Sessions |  | 0
create chatroom session | 6 | 0.75
Connect clients to one another | 8 | 1
send events to clients | 12 | 1.5
Web Client |  | 0
Authentication / requesting permissions | 8 | 1
connecting to session and creating publisher | 8 | 1
initializing subscriber | 5 | 0.625
CSScustomizations | 12 | 1.5
Publishing streams to subscriber | 4 | 0.5
subscribing to other client streams | 3 | 0.375
Adjusting Audio and video | 8 | 1
Customizing UI | 16 | 2
Session Monitoring | 16 | 2
Moderation | 18 | 2.25
Screen Sharing (HTTPS Mandatory) |  | 0
Checking for screen-sharing publishing support | 3 | 0.375
Publishing a stream with a screen-sharing source | 4 | 0.5
Setting the maximum resolution of the stream | 6 | 0.75
Cropping or letter-boxing screen-sharing videos | 8 | 1
Determining the video type ("screen" or "camera") for a stream | 6 | 0.75
Detecting when video dimensions change | 6 | 0.75
Determining when the user stops sharing the screen | 4 | 0.5
Subscribing to screen-sharing streams | 4 | 0.5
Develop Chrome screen sharing extension | 16 | 2
Distributing extensions | 12 | 1.5
Text Messaging |  | 0
Signalling | 5 | 0.625
signal payloads | 6 | 0.75
Signal delivery | 8 | 1
Other Features |  | 0
Archiving | 14 | 1.75
SIP Iterconnect Internet telephony (VOIP) | 14 | 1.75
Integration with CRM Application (Send email invites to leads) | 16 | 2
URL encoded meeting invite that uniquely identifies the lead
Exception Handling | 12 | 1.5
Debugging | 0 | 0
Account management | 12 | 1.5
Security | 12 | 1.5
Hybrid app |  | 0
Configure opentok SDK with Cordova | 0 | 0
Migration of Web Application to Hybrid App @ 4.5 hrs / page (avg 10 pages) | 0 | 0
0
0
0
0
0
0
Testing & Deployment
Testing | 96.88 | 12.11
UAT | 4 | 0.5
Deployment | 8 | 1
Total Effort | 545.48 | 68.185
Assumptions
The application will be a responsive web application
Assumptions
SIP Gateway for internet telephony
opentok media router
Archiving @$0.035 per minute
SIP Interconnect @ $0.005 per minute
Opentok F/W cost 9.99 / 2000 minutes
HTTPS provided by client
OpenTok Service acquired by client
Apple and android Store development Licensce

## Phase 2
Module | Man Hours | Man Days
Initiation |  |  | Phase 1
Requirements gathering and documentation (SRS) | 8 | 1 |  | No | Man hours | Man Days | Total Effort
Functional Specification | 8 | 1 | Designer | 1 | 34 | 4.25 | 4.25
Project Management | 25 | 3.125 | Web Developer | 1 | 160 | 20 | 20 | 31.25 | 31.25
Graphic Design (Web & Mobile) | 18 | 2.25 | Hybrid App Developer | 1 | 90 | 11.25 | 11.25
Working Prototype | 16 | 2 | PM | 1 | 41 | 5.125 | 5.125
Development |  |  | QA | 2 | 39 | 4.875 | 9.75
Web Integration |  |  | Total |  | 364 |  | 50.375 | 403
Whiteboard Sharing | 20 | 2.5
Link based push notifications | 12 | 1.5 | Total Delivery days | 29.125
Screen shot sharing | 20 | 2.5 | Total Man day Effort | 50.375
Dial IP Phone | 18 | 2.25
Polls & surveys | 22 | 2.75
backend dashboard with reports for managers | 22 | 2.75 |  |  | 152
Automatic logic for call routing | 24 | 3
Sticky routing | 12 | 1.5
Round robin based call allocation | 12 | 1.5
calender addition for web conference or invite reminders synched with outlook, google etc | 24 | 3
Sharing of documents and videos over video chat | 12 | 1.5 | [7 empty] | Phase 2
3 minute Intro video before meeting begins | 12 | 1.5
Submit feedback | 16 | 2
Unique link to resume conversation in the future | 12 | 1.5
Enable slide shows or share documents | 12 | 1.5
Testing & Deployment
Testing | 70 | 8.75
UAT | 8 | 0.5
Deployment | 8 | 1
Total Effort | 407 | 50.875
Assumptions

## Sheet2
https://support.tokbox.com/hc/en-us/articles/204605054-How-do-I-estimate-my-OpenTok-monthly-usage-