## DESC
| DESC |  | 2018-06-07
Thursday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 2 | 2
| SRS, FRS, Project Plan, Weekly Status | 16 | 2 | Sr Developer | 1 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5 | 10.5
| Project Management | 8 | 1 | Jr Developer |  |  | 0
| Design and Prototype | 16 | 2 | PM | 1 | 1 | 1
| Development |  |  | BA | 1 | 2 | 2
| Application Basic Setup | 4 | 0.5 | Tech writer | 0 | 0 | 0
| Admin |  |  | QA | 1 | 4.175 | 4.175
1 | Configure and Customizing Jaheziya application – will be change only colors & Logo. Extra effort for layout changing. | 40 | 5 | Total |  |  | 19.675
2 | Budget Analysis | 20 | 2.5
3 | Manage Training certificate | 8 | 1
| System features |  |  | Total Effort | 19.675
27 | Authentication & authorization | 4 | 0.5 | Delivery Time Line | 16.675
28 | Auditing & logging | 4 | 0.5
29 | Exception handling | 4 | 0.5
Quality Assurance
31 | QA & Bug Fixing | 29.4 | 3.675
32 | UAT | 4 | 0.5
33 | Deployment | 4 | 0.5
| Total Effort | 161.4 | 20.175