## Datwyler
Datwyler Design Tool |  | 15/01/2018
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  | Total Hours | Hours/3 phases
Initiation |  |  | Designer | 1 | 12 | 12 |  |  | 96 | 32
Business analysis | 32 | 4 | Sr Developer | 1 | 35 | 35 | 1 | 110 | 280 | 93.3333
Project Management | 3.44 | 0.43 | Jr Developer | 1 | 50 | 50 |  |  | 400 | 133.3333
Design and Prototype | 96 | 12 | Android | 1 | 25 | 25 |  |  | 200 | 66.6667
Development |  |  | PM | 1 | #REF! | #REF! |  |  | #REF! | #REF!
Application basic setup | 8 | 1 | BA | 1 | #REF! | #REF! |  |  | #REF! | #REF!
Login Screen (remember me, Forgot password, authentication, Sign Out, Change Password, email password) |  |  | Tech writer | 1 | 3 | 3 |  |  | 24 | 8
Home page |  |  | QA | 2 | 1.15 | 2.3 |  |  | 18.4 | 6.1333
Menu (Home, design, pricelist, Orders, Media, Admin) |  |  | Total |  |  | #REF!
Latest designs, Latest Orders
Events & Anouncements \w detail pages
View Profile, Edit profile, Update Profile |  |  | Total Delivery days | 63.15
Design |  |  | Total Effort | #REF! | (+1 Day deployment)
Search / Advanced search designs
Paged List Designs
New Design
General Parameters |  |  | Resource Loading
Design Inputs |  |  | Resource/Skill | Phase 1 | Phase 2 | Phase 3
Building Details |  |  | Project Manager | 52 | 40 | 40
Fiber Inputs |  |  | Business Analyst | 48 | 32 | 32
Copper Inputs |  |  | User Experience | 52 | 32 | 32
Floors (# of floors - Dynamic, New floors can be created, # of units per floor-dynamic) |  |  | Application Architect | 24 | 8 | 8
Floor Scenario 1 |  |  | Lead Developer | 94 | 94 | 94
Floor Scenario 2 |  |  | Developer | 134 | 134 | 134
Floor Scenario 3 |  |  | Database Architect | 24 | 8 | 8
Floor Scenario 4 |  |  | IOS Developer | 67 | 67 | 67
Floor Scenario 5 |  |  | QA | 111 | 111 | 111
Floor Scenario 6 |  |  | Tech Writer | 12 | 8 | 8
Schematic Diagrams ( for each building) |  |  | Total Effort | 210.75 |  | 1686 | 200.75
Generate Visio Diagrams (Floor layout, building layouts) |  |  |  | sum(
PDF output of schematic Diagrams
View diagrams
Solution (System Generated) |  |  | lekshmi's Phase wise split
Required Copper Item List (Price, description, qty, ID, etc.) with summary & total |  |  | phase start | Phase end | Days
Required Fiber Item List (Price, description, qty, ID, etc.) with summary & total |  |  | 22-06-2017 | 2017-10-08 | 35
Other Items list (Like above) |  |  | 2017-10-08 | 25/09/2017 | 33
Grand Total, Total Weight, Total volume |  |  | 26/09/2017 | 2017-02-11 | 31
Add Item (Search Part #, other editable or dropdown parameters, selectable parts ), Replace Item, Add to BOQ
Each solution is mapped to each building
Bill Of Quantity (BOQ)
Summary of Copper
Summary of Fibre
Other Items
Apply discounts per line item
Apply Special discount on top
Total amount, weight, volume
Generate Quote from BOQ
Download BOQ , Datasheets, Material submittals, Tender sheets
OverView of BOQ for all buildings
Like BOQ apply individual discounts and special discounts
Summary Information (weight, volume, amount)
Option to change solution and compare with other solutions (only for custom and predefined solns)
Option to retrieve original solution
Download documents (BOQ , Datasheets, Material submittals, Tender sheets)
Quote
Generate Quote (Address, Item list, Contact details, T&C, etc)
Templated Quote
Print Quote
Request Official Quote (email to team with design details)
MAP
Buildings created represented in a map
Map will be labelled with design ID and Design name
Map will have a relative location
Orders
Retrieved from SAP
Keyword search and Advanced Search
Grid view with multiple coulmns (paged) and Order status for each row
Pricelist
Items
basic search and Advanced search of Items
Grid view with Item list
Multiple filters (country, fibre cable types etc)
Predefined Solutions
Solution Search and Advanced search
Search and Display Filters
Item List (Grid View): Select Row Item, Add Item, Download Item
Solution List (Grid View): Select Row Item, Remove solution, Save as draft, Publish
Integration with SAP to fetch Items
Sevice Provider Guideline
Search and Advanced search with filters
Grid List of service Providers
Assign Users to Serviceprovider
View, Add, Edit, Delete SPG
Un-opened SPG's created by Distributers listed first to admin
Add Items to SPG (Create New or edit SPG view)
Add Items to SPG : Grid to select items from, Grid with selected items for SPG
Create Quote
General Parameters
Grid Lists of Items and Items added to Quote
Free Text and advanced serach with filters for items
Add selected items to the quote
Summary page with separate grids lists for copper and Fibre Items
Apply discounts for individual Items and special discounts on top
Download documents
Generate printable Quote
Print Quote
Request Official Quote (email to team with Item details)
Generate Word, Excell and PDF Quotes
Media
Display Media images and videos
Events & Anouncements \w detail pages
Admin
Manage User, Search Users, List Users
Manage roles & permissions
Manage Status
Manage Partners, search partners, List Partners
Manage Events \w rich text, Preview pages
Manage Anouncements \w rich text, Preview pages
Activate and deactivate Events & Anouncements
Master Data (project Type, Customer Type, Building Type, Floor Type, Unit, Service providers)
Pop Ups for outlets in Units
Manage Items (QTY, Price, Volume, Weight, desc etc.), Datasheets,
Manage Item categories
Manage Service provider guidelines
Manage Other solutions
Analytics
Dashboard View (Active users, Top 5 page visits, User access logs)
Application features
Logging and auditing
Exception Handling
folders & file management
Integration with SAP (Create API service layer)
Integration with Visio, Excell, Word & PDF
Quality Assurance
QA & Bug Fixing | 2.4 | 0.3
UAT | 16 | 2
Deployment per instance | 8 | 1
Total Effort | 165.84 | 20.73
Assumptions