## Datwyler
Datwyler Design Tool |  | 15/01/2018
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 17.5 | 17.5
Business analysis | 40 | 5 | Sr Developer | 1 | 55 | 55 | 37.75 | 111 | 111 | 111
Project Management | 88.8 | 11.1 | Jr Developer | 1 | 56 | 56
Design and Prototype | 140 | 17.5 | PM | 1 | 11.1 | 11.1
Development |  |  | BA | 1 | 5 | 5
Application basic setup | 8 | 1 | QA | 2 | 17.5 | 35
Login Screen (remember me, Forgot password, authentication, Sign Out, Change Password, email password) | 16 | 2 | Total |  |  | 179.6
Home page
Menu (Home, design, pricelist, Orders, Media, Admin) | 2 | 0.25 |  | Man Days |  | Man Months
Latest designs, Latest Orders | 4 | 0.5 | Total Delivery days | 91 |  | 4.55
Events & Anouncements \w detail pages | 4 | 0.5 | Total Effort | 179.6 | (+1 Day deployment) | 8.98
View Profile, Edit profile, Update Profile | 4 | 0.5
Design
Search / Advanced search designs | 6 | 0.75
Paged List Designs | 6 | 0.75
New Design
General Parameters | 4 | 0.5
Design Inputs
Building Details | 4 | 0.5
Fiber Inputs | 16 | 2
Copper Inputs | 16 | 2
Floors (# of floors - Dynamic, New floors can be created, # of units per floor-dynamic) | 90 | 11.25
Floor Scenario 1
Floor Scenario 2
Floor Scenario 3
Floor Scenario 4
Floor Scenario 5
Floor Scenario 6
Schematic Diagrams ( for each building)
Generate Visio Diagrams (Floor layout, building layouts) | 56 | 7
PDF output of schematic Diagrams | 16 | 2
View diagrams | 12 | 1.5
Solution (System Generated)
Required Copper Item List (Price, description, qty, ID, etc.) with summary & total | 2 | 0.25
Required Fiber Item List (Price, description, qty, ID, etc.) with summary & total | 2 | 0.25
Other Items list (Like above) | 2 | 0.25
Grand Total, Total Weight, Total volume | 2 | 0.25
Add Item (Search Part #, other editable or dropdown parameters, selectable parts ), Replace Item, Add to BOQ | 16 | 2
Each solution is mapped to each building | 8 | 1
Bill Of Quantity (BOQ)
Summary of Copper | 2 | 0.25
Summary of Fibre | 2 | 0.25
Other Items | 2 | 0.25
Apply discounts per line item | 2 | 0.25
Apply Special discount on top | 1 | 0.125
Total amount, weight, volume | 1 | 0.125
Generate Quote from BOQ | 16 | 2
Download BOQ , Datasheets, Material submittals, Tender sheets | 16 | 2
OverView of BOQ for all buildings
Like BOQ apply individual discounts and special discounts | 4 | 0.5
Summary Information (weight, volume, amount) | 1 | 0.125
Option to change solution and compare with other solutions (only for custom and predefined solns) | 24 | 3
Option to retrieve original solution | 8 | 1
Download documents (BOQ , Datasheets, Material submittals, Tender sheets) | 16 | 2
Quote
Generate Quote (Address, Item list, Contact details, T&C, etc) | 16 | 2
Templated Quote | 80 | 10
Print Quote | 4 | 0.5
Request Official Quote (email to team with design details) | 8 | 1
MAP
Buildings created represented in a map | 12 | 1.5
Map will be labelled with design ID and Design name | 4 | 0.5
Map will have a relative location | 4 | 0.5
Orders
Retrieved from SAP | 8 | 1
Keyword search and Advanced Search | 2 | 0.25
Grid view with multiple coulmns (paged) and Order status for each row | 4 | 0.5
Pricelist
Items
basic search and Advanced search of Items | 8 | 1
Grid view with Item list | 2 | 0.25
Multiple filters (country, fibre cable types etc) | 0 | 0
Predefined Solutions
Solution Search and Advanced search | 8 | 1
Search and Display Filters | 2 | 0.25
Item List (Grid View): Select Row Item, Add Item, Download Item | 20 | 2.5
Solution List (Grid View): Select Row Item, Remove solution, Save as draft, Publish | 4 | 0.5
Integration with SAP to fetch Items | 10 | 1.25
Sevice Provider Guideline
Search and Advanced search with filters | 8 | 1
Grid List of service Providers | 2 | 0.25
Assign Users to Serviceprovider | 8 | 1
View, Add, Edit, Delete SPG | 8 | 1
Un-opened SPG's created by Distributers listed first to admin | 4 | 0.5
Add Items to SPG (Create New or edit SPG view) | 8 | 1
Add Items to SPG : Grid to select items from, Grid with selected items for SPG | 4 | 0.5
Create Quote
General Parameters | 4 | 0.5
Grid Lists of Items and Items added to Quote | 4 | 0.5
Free Text and advanced serach with filters for items | 8 | 1
Add selected items to the quote | 4 | 0.5
Summary page with separate grids lists for copper and Fibre Items | 6 | 0.75
Apply discounts for individual Items and special discounts on top | 4 | 0.5
Download documents | 6 | 0.75
Generate printable Quote | 6 | 0.75
Print Quote | 2 | 0.25
Request Official Quote (email to team with Item details) | 4 | 0.5
Generate Word, Excell and PDF Quotes | 4 | 0.5
Media
Display Media images and videos | 8 | 1
Events & Anouncements \w detail pages | 8 | 1
Admin
Manage User, Search Users, List Users | 8 | 1
Manage roles & permissions | 8 | 1
Manage Status | 2 | 0.25
Manage Partners, search partners, List Partners | 16 | 2
Manage Events \w rich text, Preview pages | 8 | 1
Manage Anouncements \w rich text, Preview pages | 8 | 1
Activate and deactivate Events & Anouncements | 2 | 0.25
Master Data (project Type, Customer Type, Building Type, Floor Type, Unit, Service providers) | 16 | 2
Pop Ups for outlets in Units | 16 | 2
Manage Items (QTY, Price, Volume, Weight, desc etc.), Datasheets, | 8 | 1
Manage Item categories | 4 | 0.5
Manage Service provider guidelines | 4 | 0.5
Manage Other solutions | 4 | 0.5
Analytics
Dashboard View (Active users, Top 5 page visits, User access logs) | 16 | 2
Application features
Logging and auditing | 2 | 0.25
Exception Handling | 4 | 0.5
folders & file management | 1 | 0.125
Integration with SAP (Create API service layer) | 40 | 5
Integration with Visio, Excell, Word & PDF | 24 | 3
Quality Assurance
QA & Bug Fixing | 264 | 33
UAT | 16 | 2
Deployment per instance | 8 | 1
Total Effort | 1444.8 | 180.6
Assumptions