## Estimates
DATWYLER | 14/08/2017
Estimation API/WEB & Android (Landscape & Portrait)
Total Effort | No | Hours | Days | Comments
UI/UX (Android/IOS/Web) | 1 | 60 | 7.5 | UIUX for IOS&Android (Landscape + Portrait) + Web. Tablets not included
Android Portrait Design | 1 | 64 | 8
Android Landscape design | 1 | 51 | 6.375
IOS Portrait Design | 1 | 64 | 8
IOS Landscape design | 1 | 51 | 6.375
IOS DEV | 1 | 92.5 | 11.5625 | IOS Development is typically 1.25 times Android development effort | 8
Android dev | 1 | 74 | 9.25 |  | 6.375
API Development | 1 | 59 | 7.375 | API for mobile application | 9.25
Web Development | 1 | 74 | 9.25 | Responsive Web application that can viewed on tablets | 7.375
QA | 2 | 79.425 | 19.8562 |  | 9.9281
PM | 1 | 58.95 | 7.3688 |  | 7.3688
BA | 1 | 16 | 2 | Mobile + Web | 2
Total |  | 743.875 | 102.9125 |  | 50.2969
Total effort | 102.9125 | Days
Delivery Days | 50.7344 | Days

## Android
| DATWYLER |  | 14/08/2017
Android Design and Development
|  | Design |  | App
|  | Portrait | Landscape | Development | Total effort |  | Comments
# | Description | Hours | Hours | Hours | Hours | Man Days
1 | Basic Setup |  |  | 8 | 8 | 1
2 | Home page
| Search option | 8 | 6 | 4 | 18 | 2.25
| System, category and item selection option |  |  | 6 | 6 | 0.75
| Show list of product |  |  | 6 | 6 | 0.75
| Right side menu(Option menu) |  |  | 6 | 6 | 0.75
Add item,Billing of quantity,Data sheet,Datwyler design tool
3 | Item detail page | 5 | 6 | 4 | 15 | 1.875
4 | Bill of Quantity
| Show list of product | 6 | 4 | 3 | 13 | 1.625
| Right side menu(Option menu) |  |  | 3 | 3 | 0.375
Quotation
Data sheet
Reset
5 | Quotation
| Show list of product | 4 | 4 |  | 8 | 1
| Right side menu(Option menu) |  |  | 1 | 1 | 0.125
Quotation
Data sheet
6 | Datwyler design tool
7 | Selection page for fiber/copper | 4 | 2 | 1 | 7 | 0.875
8 | Basic information input page fiber | 6 | 5 | 4 | 15 | 1.875
11 | Basic information input page copper | 5 | 4 | 4 | 13 | 1.625
12 | Fiber optic solution page
| Show list of product and logistic information(Total gross weight and total volume) | 8 | 6 | 8 | 22 | 2.75
13 | Copper solution page
| Show list of product and logistic information(Total gross weight and total volume) | 6 | 4 | 6 | 16 | 2
14 | Fiber optic and copper solution page
| Show list of product and logistic information(Total gross weight and total volume) | 8 | 6 | 6 | 20 | 2.5
15 | Data sheet |  |  |  |  | 0 | Need clarification
16 | Developer side testing and bug fixing | 4 | 4 | 4 | 12 | 1.5
Quality Assurance
17 | QA |  |  |  | 0 | 0
18 | UAT |  |  |  | 0 | 0
19 | Deployment |  |  |  | 0 | 0
| Total effort | 64 | 51 | 74 | 189 | 23.625
|  |  |  | 23.625 | 23.625
Assumption
The mobile app will be designed to support mobile phones only. Tabs not considered.
This application will support Sdk version 19(kitkat) and above
The mobile app will be work on online. Offline not considered

## Web
# | Web Development | Hours | Days
1 | UI/UX (Android/Web) | 32 | 4
2 | Home Page | 8 | 1
3 | Search Filters | 4 | 0.5
4 | Show product list | 8 | 1
5 | Add to BoQ | 4 | 0.5
6 | Datasheets | 4 | 0.5
7 | Bill of Quantity |  | 0
8 | BOQ List | 8 | 1
9 | Weight & Vol Estimation | 4 | 0.5
10 | Quotation |  | 0
11 | Print | 8 | 1
12 | Export to XLS, PDF | 6 | 0.75
13 | Datwyer Design Tool |  | 0
14 | Navigation |  | 0
15 | Export to XLS, PDF | 2 | 0.25
16 | Datasheets | 2 | 0.25
17 | Computed Item List | 8 | 1
18 | Weight & Vol Estimation | 4 | 0.5
19 | Get Quote | 4 | 0.5
20 | Total Effort | 74 | 9.25 | 9.25
21
22

## API
# | API Development | Hours | Days
1 | Basic Setup |  | 0
2 | Home page |  | 0
3 | Search option |  | 0
4 | System, category and item selection option | 4 | 0.5
5 | Show list of product | 4 | 0.5
6 | Right side menu(Option menu) |  | 0
7 | Add item,Billing of quantity,Data sheet,Datwyler design tool | 4 | 0.5
8 | Item detail page |  | 0
9 | Bill of Quantity | 0 | 0
10 | Show list of product | 3 | 0.375
11 | Right side menu(Option menu) | 0 | 0
12 | Quotation | 3 | 0.375
13 | Data sheet | 3 | 0.375
14 | Reset | 1 | 0.125
15 | Quotation |  | 0
16 | Show list of product | 3 | 0.375
17 | Right side menu(Option menu) | 0 | 0
18 | Quotation | 3 | 0.375
19 | Data sheet | 3 | 0.375
20 | Datwyler design tool | 0 | 0
21 | Selection page for fiber/copper | 2 | 0.25
22 | Basic information input page fiber | 3 | 0.375
23 | Basic information input page copper | 3 | 0.375
24 | Fiber optic solution page | 0 | 0
25 | Show list of product and logistic information(Total gross weight and total volume) | 3 | 0.375
26 | Copper solution page |  | 0
27 | Show list of product and logistic information(Total gross weight and total volume) | 3 | 0.375
28 | Fiber optic and copper solution page |  | 0
29 | Show list of product and logistic information(Total gross weight and total volume) | 3 | 0.375
30 | Data sheet | 3 | 0.375
31 | Developer side testing and bug fixing | 8 | 1
32 | QA
| Total effort | 59 | 7.375