## Quotation Software
| Elissa Fiber Glass |  | Sep 19 2017
Wednesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 2 | 2
2 | Functional Specification | 8 | 1 | Sr Developer | 2 | 7 | 14 | 13.75 | 14
3 | Project Management | 11 | 1.375 | Jr Developer | 0 | 37 | 0
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) |  | 0 | PM | 1 | 1.375 | 1.375
5 | Complete running prototype | 16 | 2 | BA | 1 | 2 | 2
| Development |  |  | QA | 1 | 5.5 | 5.5
| Home page |  |  | Total |  |  | 24.875
6 | New Enquiry | 12 | 1.5
7 | New Client | 12 | 1.5 | Total Delivery days | 14.5
8 | New Quotation | 12 | 1.5 | Total Effort | 24.875
| Home page with menu | 8 | 1
9 | Change Enquiry Status | 6 | 0.75
10 | Change Quotation status | 6 | 0.75 | [6 empty] | #REF!
| Log in / Logout | 6 | 0.75 | [5 empty] | 0
| Quotation view mode for clients with URL or link | 6 | 0.75
11 | Report |  | 0
12 | Enquiries | 6 | 0.75
13 | Quotations | 6 | 0.75
14 | Admin |  | 0
15 | Manage Users (New/ delete/ alter) | 6 | 0.75
16 | Manage Quotations | 6 | 0.75
17 | Manage Enquiry | 6 | 0.75
18 | Systems |  | 0
19 | Roles / Entitlements | 6 | 0.75
20 | Logging / Auditing | 6 | 0.75 | [5 empty] | 0
Testing & Deployment
| Testing | 33 | 5.5
| UAT | 0
| Deployment | 0
| Total Effort | 197 | 24.625
| Estimate Assumptions: |  | 1. Recording will not be a column for the report (student , Teacher & Admin), not included in filter. 2. Tutorial for Admin, Teachers & Students - static content 3. Request (teacher) workflow escalation period is hardcoded in DB 4. "Wait for the review different admin to receive the fees" in the admin worflow - Need clarification 5. Technology not considered 6. Customer will procure templates, SSL certificates & Payement processor 7. UI development is 2-4 hrs per screen 8. Effort for deployment not considered 9. Reporting and analytics for mobile devices will be imported from the web 10. Both mobile and tablet have similar design 11. Estimated with default Android and IOS design, Custom design will take more effort 12. Testing will be done in 2 Android Mobiles 13. Testing will be done in 2 Android Tablets 14. Testing will be done in latest versions of Google Chrome, Mozilla Firefox & IE web browsers only 15. Verbat will capture billing information, but will not process the salary payment for tutors or admins
| Out of Scope |  | 1. Zoom integration 2. Payment processing for Teacher 3. Quiz assignmets for students by teacher 4. Documentation & Project planning