## Dubizzle
| Dubizzle |  | Sep 19 2017
Wednesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 5 | 5
2 | Functional Specification | 16 | 2 | Sr Developer | 1 | 40 | 40 | 87.125 | 88
3 | Project Management | 69.7 | 8.7125 | Jr Developer | 1 | 48 | 48
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) |  | 0 | PM | 1 | 8.7125 | 8.7125
5 | Complete running prototype | 40 | 5 | BA | 1 | 4 | 4
| Development |  | 0 | QA | 2 | 12.4062 | 24.8125
| Home page |  | 0 | Total |  |  | 130.525
6 | Location selection and redirect to sub domain | 8 | 1
7 | Login via facebook | 6 | 0.75 | Total Delivery days | 74.1188 | +1 Delivery
8 | Profile display (name and image) | 6 | 0.75 | Total Effort | 130.525
9 | Dropdown to select city (change) | 6 | 0.75 | Factoring Arabic | 110*1.25= | 163.1562
10 | Trending on Dubizzle (upto 6) | 6 | 0.75
11 | Popular categories (upto 6) with count | 6 | 0.75 | [6 empty] | #REF!
12 | Popular subcategories with count and view all | 6 | 0.75
| Chat | 12 | 1.5
13 | About US | 6 | 0.75
Advetrising (min 10 sub pages)
14 | Adspecs (category in page) |  | 0
15 | Standard Ad units subpage | 8 | 1
16 | Wall paper Ad Unit | 8 | 1
17 | Mobile Rich media | 8 | 1
18 | Rich media | 8 | 1
19 | Ad Specs | 8 | 1
20 | Solutions (category in page) |  | 0
21 | BillBoard | 8 | 1
22 | Filmstrip | 8 | 1 | [5 empty] | 0
23 | Native | 8 | 1
24 | Mobile | 8 | 1
25 | Standard Ad units subpage | 8 | 1
26 | Wallpaper | 8 | 1
27 | Case Studies | 8 | 1
28 | Blog with Articles | 40 | 5
29 | Advertising Guidelines | 6 | 0.75
30 | Dubizzle Best practices | 6 | 0.75
31 | Creative Accptance policy | 6 | 0.75
32 | Terms and conditions | 4 | 0.5
33 | Mediakit download | 2 | 0.25
34 | Contactus page with form | 6 | 0.75
35 | Social Media integration (you tube, instagram, facebook, twitter) | 6 | 0.75
36 | Countries list | 6 | 0.75
37 | Help & Support | 6 | 0.75
Search Bar
38 | Universal Bar | 6 | 0.75
39 | Motors | 8 | 1
40 | Classifieds | 8 | 1
41 | property for rent | 8 | 1
42 | property for sale | 8 | 1
43 | jobs | 8 | 1
44 | Community | 8 | 1
Place your Ad
45 | Place your Ad | 12 | 1.5
46 | Motors | 16 | 2
47 | Jobs | 16 | 2
48 | property for sale | 12 | 1.5
49 | property for rent | 12 | 1.5
50 | community | 12 | 1.5
51 | classifieds | 16 | 2
52 | Locate address on map (map full view with auto location) | 12 | 1.5
53 | Upload CV | 12 | 1.5
| Home Page Menu |  | 0
54 | Motors with submenu and count | 8 | 1
55 | classifieds with submenu and count | 6 | 0.75
56 | property fpr sale (Similar to above) | 6 | 0.75
57 | property for rent (similar to 55) | 6 | 0.75
58 | jobs (similar to 55) | 6 | 0.75
59 | community (similar to 55) | 6 | 0.75
| Search Results page |  | 0
60 | Advanced Search on left (different for each category) | 36 | 4.5
61 | Advertisements ( 3-4 on page ) | 6 | 0.75
62 | Subcategory List with count (if applicable) | 6 | 0.75
63 | Promoted listings listed first followed by others | 8 | 1
64 | Filters | 4 | 0.5
65 | Sorting | 2 | 0.25
66 | Save Searches | 6 | 0.75
67 | Product Detailed pages (layout completely different for different pages X 6) | 16 | 2
68 | Adverticement framework | 24 | 3
| Profile |  | 0
69 | My ads | 6 | 0.75
70 | My Favourites | 6 | 0.75
71 | My searches | 6 | 0.75
72 | My Profile | 8 | 1
73 | My chats | 4 | 0.5
74 | Change Avatar | 4 | 0.5
75 | Account settings | 6 | 0.75
76 | Signout | 2 | 0.25
77 | Signin | 2 | 0.25
78 | Register | 6 | 0.75
79 | captcha | 3 | 0.375
80 | Know Your rights | 4 | 0.5
81 | Receive personalized emails for saved searches | 6 | 0.75
82 | Educational articles | 8 | 1
| Admin |  | 0
83 | Approve Ads | 6 | 0.75
84 | Manage Users | 8 | 1
85 | Create Categories | 4 | 0.5
86 | Create Sub categories | 4 | 0.5
87 | Create Advertisements ( Time bound Ads, Context Sensitive ads, Integration with Ad networks) | 32 | 4
88 | Countries and cities | 6 | 0.75
Testing & Deployment
| Testing | 190.5 | 23.8125
| UAT | 8 | 1
| Deployment | 8 | 1
| Total Effort | 1045.2 | 130.65
Estimate Assumptions:
6.5325
Out of Scope