## Web
Electronic Document Center
# | Activity | Hours | Days
1 | Business Analysis & Documentation( SRS, FS, User Manuals, Weekly Reports) | 32 | 4
2 | UI/UX | 32 | 4
3 | Project Management | 4 | 0.5
UI Design
4 | Page Design (developer) | 40 | 5
Development
Customer Portal
Customer Registration
5 | Splash Screen |  | 0
6 | Login / Registration (with billing Address, delivery Address etc.) |  | 0
7 | OTP Verification |  | 0
8 | E-mail Id verification |  | 0
9 | Push notification in mobile to verify registration |  | 0
10 | I am not a Robot CAPTCHA checking process |  | 0
11 | Bilingual (Arabic & English) |  | 0
12 | Manage Profile |  | 0
13 | DashBoard |  | 0
Order Management
14 | Product Search |  | 0
15 | Filter and Sort products |  | 0
16 | Add to cart |  | 0
17 | Photo Print options |  | 0
18 | Upload Pics from gallery |  | 0
19 | Product Customization |  | 0
20 | Upload Printable Documents (PDF format) |  | 0
21 | Load photos into Azure web drive (Cloud) |  | 0
22 | Select photos from cloud |  | 0
23 | Edit the album, rearrange the photos according to the selected option |  | 0
24 | Select the type of Print |  | 0
25 | Preview the album/photo |  | 0
26 | List cart |  | 0
27 | Modify Cart |  | 0
28 | Cart Check Out |  | 0
29 | Pickup Options |  | 0
30 | Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) |  | 0
31 | Collect credit card details |  | 0
32 | Process Payment / Cash on Delivery Option |  | 0
33 | Push notification to mobile regarding txn |  | 0
34 | Email Transaction Details |  | 0
Notifications
35 | Order Status changes |  | 0
General features
36 | Feedback/Contact Us |  | 0
37 | Contributions to album through invitation |  | 0
38 | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) |  | 0
39 | View App in guest mode |  | 0
40 | Social Media Integration ( FB, Instagram, PinInterest, Google +) |  | 0
41 | Connecting People |  | 0
42 | Display & import Contacts from social network |  | 0
43 | Services Listing |  | 0
44 | Subscription Listing |  | 0
45 | Subscribe to service |  | 0
Admin Portal
46 | Manage Orders
47 | Manage products
48 | Manage promotions
49 | Manage Discounts (Volume, Paper Quality, Size)
50 | Manage Application users
51 | Manage roles
52 | Manage customers
53 | Manage bilingual product headings
54 | Image management (resolution, Content, legal, Quality) and moderation
55 | Manage subscriptions
56 | Manage Payment gateway
57 | ERP Jobs management
58 | Reports Management
59 | Manage Invoices (Print, Email option)
60 | Manage Deliveries
61 | Manage Couriers
62 | Manage Vat, tax calculations
Generic App (Mobile & Web) features
63 | Mobile Menu
64 | Dashboard (Home Screen)
65 | Social media Linking
66 | Generate Order ID for order fulfillment
67 | order id (reference #) for admin
68 | Payment Gateway Integration with EDC specified vendor
69 | Dashboard for monitoring Order status
70 | Bilingual ( Arabic/ English)
71 | Automatic App Updates
72 | Azure cognitive service for image classification, legality, description and tagging
73 | Image storage limits limited by subscription package
System
74 | Discounts based on Order Volume
75 | Discounts based on size
76 | Discounts based on paper matererial
77 | Maintain Vat charges based on product type
78 | Automatic Price change based on discounts
79 | integration with Courier Vendor for AWB
80 | Azure Cloud storage integration with encryption
81 | ERP Integration (Jobs)
82 | Payment G/W with multi currency option
83 | Azure cognitive service API integration
84 | SMS Gateway Integration
85 | Social Media Integration
86 | Print Queue
87 | Print Service
| Mobile API Services |  | 0
88 | Mobile API Integration |  | 0
| QA |  | 0
89 | Functional testing | 0 | 0
90 | UAT | 8 | 1
| Deployment |  | 0
91 | Package & Deployment | 8 | 1

## Mobile
Electronic Document Center
Android/iOS
Arabic & English
# | Activity | Hours | Days
1 | Business Analysis & Documentation( SRS, FS, User Manuals, Weekly Reports) | 32 | 4
2 | UI/UX | 40 | 5
3 | Project Management | 7.2 | 0.9
UI Design
4 | Page Design (developer) | 72 | 9
Mobile App Features
Customer Registration
5 | Splash Screen |  | 0
6 | Login / Registration (with billing Address, delivery Address etc.) |  | 0
7 | OTP Verification |  | 0
8 | E-mail Id verification |  | 0
9 | Push notification in mobile to verify registration |  | 0
10 | I am not a Robot CAPTCHA checking process |  | 0
11 | Bilingual (Arabic & English) |  | 0
12 | Manage Profile |  | 0
13 | DashBoard |  | 0
Order Management
14 | Product Search |  | 0
15 | Filter and Sort products |  | 0
16 | Add to cart |  | 0
17 | Photo Print options |  | 0
18 | Upload Pics from gallery |  | 0
19 | Product Customization |  | 0
20 | Upload Printable Documents (PDF format) |  | 0
21 | Load photos into Azure web drive (Cloud) |  | 0
22 | Select photos from cloud |  | 0
23 | Edit the album, rearrange the photos according to the selected option |  | 0
24 | Select the type of Print |  | 0
25 | Preview the album/photo |  | 0
26 | List cart |  | 0
27 | Modify Cart |  | 0
28 | Cart Check Out |  | 0
29 | Pickup Options |  | 0
30 | Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) |  | 0
31 | Collect credit card details |  | 0
32 | Process Payment / Cash on Delivery Option |  | 0
33 | Push notification to mobile regarding txn |  | 0
34 | Email Transaction Details |  | 0
Notifications
35 | Order Status changes |  | 0
General features
36 | Feedback/Contact Us |  | 0
37 | Contributions to album through invitation |  | 0
38 | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) |  | 0
39 | View App in guest mode |  | 0
40 | Social Media Integration ( FB, Instagram, PinInterest, Google +) |  | 0
41 | Connecting People |  | 0
42 | Display & import Contacts from social network |  | 0
43 | Services Listing |  | 0
44 | Subscription Listing |  | 0
45 | Subscribe service |  | 0
| Api Integration |  | 0
46 | Api Integration |  | 0
| Testing |  | 0
47 | Developer side testing & debugging |  | 0
| QA |  | 0
48 | Functional testing | 0 | 0
49 | UAT | 8 | 1
| Deployment |  | 0
50 | Package & Deployment | 8 | 1

## Image
Features of Mobile Application module |  | Web Application Module | System | `
| Customer Registration | Customer Registration | Discounts based on Order Volume
| Splash Screen | Login / Registration (with billing Address, delivery Address etc.) | Discounts based on size
| Login / Registration (with billing Address, delivery Address etc.) | OTP Verification | Discounts based on paper matererial
| OTP Verification | E-mail Id verification | Maintain Vat charges based on product type
| E-mail Id verification | Push notification in mobile to verify registration | Automatic Price change based on discounts
| Push notification in mobile to verify registration | I am not a Robot CAPTCHA checking process | integration with Courier Vendor for AWB
| I am not a Robot CAPTCHA checking process | Bilingual (Arabic & English) | Azure Cloud storage integration with encryption
| Bilingual (Arabic & English) | Manage Profile | ERP Integration (Jobs)
| Manage Profile | Dashboard | Payment G/W with multi currency option
| DashBoard | Order Management | Azure cognitive service API integration
| Order Management | Product Search | SMS Gateway Integration
| Product Search | Filter and Sort products | Social Media Integration
| Filter and Sort products | Add to cart | Print Queue
| Add to cart | Photo Print options | Print Service
| Photo Print options | Upload Pics from desktop or google drive, dropbox, one drive, social media
| Upload Pics from gallery | Product Customization
| Product Customization | Upload Printable Documents (PDF format) | Generic App (Mobile & Web) features
| Upload Printable Documents (PDF format) | Load photos into Azure web drive (cloud) | Mobile Menu
| Load photos into Azure web drive (Cloud) | Select photos from cloud | Dashboard (Home Screen)
| Select photos from cloud | Edit the album, rearrange the photos according to the selected option | Social media Linking
| Edit the album, rearrange the photos according to the selected option | Select the type of Print | Generate Order ID for order fulfillment
| Select the type of Print | Preview the album/photo | order id (reference #) for admin
| Preview the album/photo | List cart | Payment Gateway Integration with EDC specified vendor
| List cart | Modify Cart | Dashboard for monitoring Order status
| Modify Cart | Cart Check Out | Bilingual ( Arabic/ English)
| Cart Check Out | Pickup Options | Automatic App Updates
| Pickup Options | Fee Calculation (based on package, paper, size, discounts, promotions, vat etc.) | Azure cognitive service for image classification, legality, description and tagging
| Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) | Collect credit card details | Image storage limits limited by subscription package
| Collect credit card details | Process Payment / Cash on Delivery Option
 | Process Payment / Cash on Delivery Option | Push notification to mobile regarding txn
 | Push notification to mobile regarding txn | Email Transaction Details
 | Email Transaction Details | Notifications
• | Notifications | Order Status changes
• | Order Status changes | General features
• | General features | Feedback/Contact Us
• | Feedback/Contact Us | Contributions to album through invitation | Admin
• | Contributions to album through invitation | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | Manage Orders
• | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | View Web App in Guest mode | Manage products
• | View App in guest mode | Social Media Integration ( FB, Instagram, PinInterest, Google +) | Manage promotions
• | Social Media Integration ( FB, Instagram, PinInterest, Google +) | Connecting People | Manage Discounts (Volume, Paper Quality, Size)
• | Connecting People | Display & import Contacts from social network | Manage Application users
| Display & import Contacts from social network | Services Listing | Manage roles
• | Services Listing | Subscription Listing | Manage customers
• | Subscription Listing | Subscribe service | Manage bilingual product headings
• | Subscribe service |  | Image management (resolution, Content, legal, Quality) and moderation
• |  |  | Manage subscriptions
• |  |  | Manage Payment gateway
• |  |  | ERP Jobs management
• |  |  | Reports Management
• |  |  | Manage Invoices (Print, Email option)
• |  |  | Manage Deliveries
 |  |  | Manage Couriers
Manage Vat, tax calculations

## Sheet3
Assumptions
Customer will procure SMS gateway
Customer will procure payment gateway
Customer will procure Azure cognitive servicesz
Customer will procure Azure cloud storage
Customer will provide detailed documentation related to integration with courier service, delivery service & ERP
Customer will procure libraries/API related to report generation and charts (if needed)
Integration with social media accounts subject to media company policies
Mobile app integration with device hardware is subject to explicit user approval
Application shall not store information related to user credit/debit cards
Uploaded Zip files may not be automatically unzipped unless Azure supports it
Application shall be bilingual (English & Arabic only)
Features of Web Portal Application:
a. Login
b. Dashboard
c. Admin settings
d. Customer management
e. Order management
f. Reports
g. Invoice Management (View, Print)
h. Special Promotion management
i. Delivery Management (View Delivery Mode, Update Delivery Status, Generate AWB)
j. Courier Vendor Management (Add / Edit / Delete Vendor)
k. Contact Us
Web application process flow
A web portal needs to be developed for the client’s digital print unit for order management.
· Web Portal shall get a notification on the order placed by the user with order reference number.
· Additional modules to monitor and process the order placed by customers
· Application will get updated automatically
· Application will auto generate an invoice for each order
· Client shall download the photos related to the order from the cloud / server and does the print fulfillment.
· Integration of website with courier vendor application
· Client to generate / enter an AWB Number if the delivery mode is by courier.
· Client to update the job completion for the order reference number along with the AWB number if the delivery mode is by courier
· Once updated, a notification to be triggered to the user’s mobile app with the AWB number details or notification for pickup timing.
· On delivery of the booklet, the details to be updated across the order reference number
· Custom Vision- to reduce mammography image quality issues
· Content Moderator- for controlling explicit or offensive contents
· Image storage based on subscription package
· Website development using Microsoft Azure cognitive
· Client should be able to update the special promotion page with products and different pricing which needs to be integrated and reflected in the mobile app for the end user.
· Customer should be able to upload from DropBox, Google Drive, local hard drive, one drive accounts and SD card also
Connecting people page in web app