## Android_iOS
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
UI Design
| Page Design | 116 | 14.5
Development
1 | Basic Setup | 12 | 1.5
2 | Splash Screen | 6 | 0.75
3 | Login page | 6 | 0.75
4 | Registration page | 6 | 0.75
5 | Manage profile (delivery address, credit card details) | 8 | 1
6 | Model type listing | 8 | 1
7 | Subscription Model | 8 | 1
8 | On the Pay As You Go Model | 8 | 1
9 | Menu List | 6 | 0.75
10 | Menu List Details page | 6 | 0.75
11 | Home Screen with photo print options | 10 | 1.25
12 | Add and Order | 44 | 5.5
13 | - Select the type of Print
14 | - Load photos from gallery
15 | - Select photos from Gallery
16 | - Edit the album, rearrange the photos according to the selected option Preview the album/photo
17 | - Add to Cart
18 | Cart listing | 8 | 1
19 | Cart list details page | 6 | 0.75
20 | Checkout, Pricing | 10 | 1.25
21 | Delivery Options (subscription, pay as you go, cash on delivery) | 6 | 0.75
22 | Payment gateway integration | 40 | 5
23 | Push notification based on order status | 32 | 4
24 | Settings page | 8 | 1
25 | Feedback/Contact Us | 6 | 0.75
26 | Multiple Currency/ Bilingual | 16 | 2
27 | Inner Pages like About Us, Terms and Conditions, How to Use, FAQ etc | 8 | 1
Api Integration
28 | Api Integration | 32 | 4
Testing
29 | Developer side testing | 24 | 3
| Total effort |  | 55
Assumption
This application will support Android Sdk version 19(kitkat) and above, iOS 9.0 and above
cloud hosting of pics
multicurrency based on payment gateway

## WEB
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
UI Design
1 | Business Analysis + Project documentation | 16 | 2
2 | Project Management | 23.8 | 2.975
3 | UI/UX (WEB + Mobile) | 38 | 4.75
Development
4 | Basic Setup | 8 | 1
5 | Auditing + logging + exception handling | 12 | 1.5
6 | Dashboard | 16 | 2
2 | Manage subscription models | 8 | 1
3 | Manage delivery options | 8 | 1
4 | Manage prices (delivery + print/image etc.) | 8 | 1
5 | Manage users (Web users + Authentication + authorization) | 10 | 1.25
7 | Customer management | 10 | 1.25
8 | Order management | 16 | 2
9 | Manage special promotions | 16 | 2
10 | Update job status changes | 6 | 0.75
11 | SMS / email messages | 8 | 1
12 | Generate Order reference numbers & AWB | 6 | 0.75
13 | Mobile Api Development | 38 | 4.75
Testing
14 | QA (IOS + Android + Web) | 68 | 8.5
| Total effort |  | 39.475