## Effort Estimate
Resource | # | Man Hours | Man Days
project Management | 1 | 23.8 | 2.975
Business Analysis | 1 | 16 | 2
UI/UX + Working prototypes | 2 | 88 | 22
IOS | 1 | 324 | 40.5
Android | 1 | 324 | 40.5
WEB | 1 | 170 | 21.25
QA | 2 | 34 | 8.5
Total Effort |  |  | 137.725
Man Days
Total Effort | 137.725
Delivery Days | 57.75 | 38
1. Web:
Admin setting
Reports management
invoice management
Courier vendor management
Contact us
2. Android / iOS:

## Android_iOS
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
UI Design
| Page Design | 72 | 9
Development
1 | Basic Setup | 12 | 1.5
2 | Splash Screen | 6 | 0.75
3 | Login page | 6 | 0.75
4 | DashBoard
5 | Registration page | 6 | 0.75
6 | Manage profile (delivery address, credit card details) | 8 | 1
7 | Model type listing | 8 | 1
8 | Subscription Model | 8 | 1
9 | On the Pay As You Go Model | 8 | 1
10 | Menu List | 6 | 0.75
11 | Menu List Details page | 6 | 0.75
12 | Home Screen with photo print options | 10 | 1.25 | dashboard
13 | Add and Order | 44 | 5.5 | order management
14 | - Select the type of Print |  |  | Contributions to album through invitation
15 | - Load photos from gallery
16 | - Select photos from Gallery
17 | - Edit the album, rearrange the photos according to the selected option Preview the album/photo
18 | Contribution to album through invitation
19 | - Add to Cart
20 | Order Management
21 | Cart listing | 8 | 1
22 | Cart list details page | 6 | 0.75
23 | Checkout, Pricing | 10 | 1.25
24 | Delivery Options (subscription, pay as you go, cash on delivery) | 6 | 0.75
25 | Payment gateway integration | 40 | 5
26 | Push notification based on order status | 32 | 4
27 | Settings page | 8 | 1
28 | Feedback/Contact Us | 6 | 0.75
29 | Multiple Currency/ Bilingual | 16 | 2
30 | Inner Pages like About Us, Terms and Conditions, How to Use, FAQ etc | 8 | 1
Api Integration
31 | Api Integration | 32 | 4
Testing
32 | Developer side testing | 24 | 3
| Total effort |  | 49.5
Assumption
This application will support Android Sdk version 19(kitkat) and above, iOS 9.0 and above
cloud hosting of pics
multicurrency based on payment gateway

## WEB
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
UI Design
1 | Business Analysis + Project documentation | 16 | 2
2 | Project Management | 23.8 | 2.975
3 | UI/UX (WEB + Mobile) | 32 | 4
Development
4 | Basic Setup | 8 | 1
5 | Auditing + logging + exception handling | 12 | 1.5
6 | Dashboard | 16 | 2
2 | Manage subscription models | 8 | 1
3 | Manage delivery options | 8 | 1
4 | Manage prices (delivery + print/image etc.) | 8 | 1
5 | Manage users (Web users + Authentication + authorization) | 10 | 1.25
7 | Customer management | 10 | 1.25
8 | Order management | 16 | 2
9 | Manage special promotions | 16 | 2
10 | Update job status changes | 6 | 0.75
11 | SMS / email messages | 8 | 1
12 | Generate Order reference numbers & AWB | 6 | 0.75
13 | Mobile Api Development | 38 | 4.75
Testing
14 | QA (IOS + Android + Web) | 68 | 8.5
| Total effort |  | 38.725