## Effort Estimate
Resource | # | Man Hours | Man Days
project Management | 1 | 33.88 | 4.235 | Mobile Development ‐ Breakup Details | Number of Man Days for Each Process
Business Analysis | 1 | 32 | 4 | Brand Logo Designing, and Promotion | 2
UI/UX + Working prototypes | 2 | 88 | 22 | Detailed Analysis and Design | 1
IOS | 1 | 364 | 45.5 | Mobile Page Design, Define Navigation and Implementation | 20
Android | 1 | 364 | 45.5 | Web Service Extension | 5
WEB | 1 | 242 | 30.25 | Android Development | 39
QA | 2 | 48.4 | 12.1 | IOS Development | 40
Total Effort |  |  | 163.585 | Quality Assurance, Quality Control, Integration Testing, Unit Testing | 6
|  |  |  | Deployment | 1
| Man Days |  |  | Total Mobile Development Days | 114
Total Effort | 163.585
Delivery Days | 66.55
|  |  |  | Web Development ‐ Breakup Details | Number of Man Days for Each Process
|  |  |  | Detailed Analysis and Design | 11 | 163
|  |  |  | Web Design, Define Navigation and Implementation | 1
|  |  |  | Web Site Development | 30
|  |  |  | Quality Assurance, Quality Control, Integration Testing, Unit Testing | 6
|  |  |  | Deployment | 1
|  |  |  | Total Web Site Development Days | 49

## Android_iOS
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
| UI Design |  |  | Mobile Application Module Requirements | Importance | Design Possibilities | Charges Included in proposal | Additional Cost If applicable
| Page Design | 72 | 9 | Login Page | Mandatory | YES | YES | NO
| Development |  |  | Manage Profile | Mandatory | YES | YES | NO
1 | Basic Setup | 12 | 1.5 | Subscription Model | Mandatory | YES | YES | NO
2 | Splash Screen | 6 | 0.75 | Menu List | Mandatory | YES | YES | NO
3 | Login page | 6 | 0.75 | Dash Board | Mandatory | YES | YES | NO
4 | DashBoard | 12 | 1.5 | Order Management | Mandatory | YES | YES | NO
5 | Registration page | 6 | 0.75 | Cart Listing | Mandatory | YES | YES | NO
6 | Manage profile (delivery address, credit card details) | 8 | 1 | Payment Gateway Integration | Mandatory | YES | YES | NO
7 | Model type listing | 8 | 1 | Push Notifications | Mandatory | YES | YES | NO
8 | Subscription Model | 8 | 1 | General App Configuration settings | Mandatory | YES | YES | NO
9 | On the Pay As You Go Model | 8 | 1 | Feedback / Contact Page | Mandatory | YES | YES | NO
10 | Menu List | 6 | 0.75 | Terms and Conditions , FAQ , How to Use App pages | Mandatory | YES | YES | NO
11 | Menu List Details page | 6 | 0.75 | Contributions to album through invitation | Mandatory | YES | YES | NO
12 | Home Screen with photo print options | 10 | 1.25 | SMS Gateway Integration | Mandatory | YES | YES | NO
13 | Add and Order | 44 | 5.5 | Logo Designing | Mandatory | YES | YES | NO
14 | - Select the type of Print |  | 0 | Promotions in Social Media of the Product | Mandatory | YES | YES | NO
15 | - Load photos from gallery |  | 0 | Any Limitation in Number of Pages or Forms in mobile app | Mandatory | YES | YES | NO
16 | - Select photos from Gallery |  | 0
17 | - Edit the album, rearrange the photos according to the selected option Preview the album/photo |  | 0
18 | - Contribution to album through invitation | 12 | 1.5
19 | - Add to Cart |  | 0 | Mobile Application (IOS) | Software & System | Comments
20 | Order Management | 16 | 2 | Language(s) | Obj-C
21 | Cart listing | 8 | 1 | Development Environment
22 | Cart list details page | 6 | 0.75 | Application Version Minimum Compatibility | Any
23 | Checkout, Pricing | 10 | 1.25 | Back End Database
24 | Delivery Options (subscription, pay as you go, cash on delivery) | 6 | 0.75 | Mobile Application (Android)
25 | Payment gateway integration | 40 | 5 | Language(s) | Java
26 | Push notification based on order status | 32 | 4 | Development Environment | Android Studio
27 | Settings page | 8 | 1 | Application Version Minimum Compatibility | Kitkat and above
28 | Feedback/Contact Us | 6 | 0.75 | Back End Database | Any
29 | Multiple Currency/ Bilingual | 16 | 2
30 | Inner Pages like About Us, Terms and Conditions, How to Use, FAQ etc | 8 | 1
Api Integration
31 | Api Integration | 32 | 4
Testing
32 | Developer side testing | 24 | 3
| Total effort | 364 | 45.5
Assumption
This application will support Android Sdk version 19(kitkat) and above, iOS 9.0 and above
cloud hosting of pics
multicurrency based on payment gateway

## WEB
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
| UI Design |  |  | Web Application Module Requirements | Importance | Design Possibilities | Charges Included in proposal | Additional Cost If applicable
1 | Business Analysis + Project documentation (SRS,FS, Weekly Reports, Usermanuals) | 32 | 4 | Web Login Page | Mandatory | Yes | Yes | NO
2 | Project Management | 33.88 | 4.235 | Web Dash Board | Mandatory | Yes | Yes | NO
3 | UI/UX (WEB + Mobile) | 32 | 4 | Admin Settings | Mandatory | Yes | Yes | NO
| Development |  |  | Customer Management | Mandatory | Yes | Yes | NO
4 | Basic Setup | 8 | 1 | Order Management | Mandatory | Yes | Yes | NO
5 | Admin Settings | 16 | 2 | Reports Management | Mandatory | Yes | Yes | NO
6 | Auditing + logging + exception handling | 12 | 1.5 | Invoice Management | Mandatory | Yes | Yes | NO
7 | Contact US | 4 | 0.5 | Promotions Management | Mandatory | Yes | Yes | NO
8 | Dashboard | 16 | 2 | Delivery Management | Mandatory | Yes | Yes | NO
9 | Manage subscription models | 8 | 1 | Courier Vendor Management | Mandatory | Yes | Yes | NO
10 | Manage delivery options | 8 | 1 | Contact Us | Mandatory | Yes | Yes | NO
11 | Manage prices (delivery + print/image etc.) | 8 | 1
12 | Manage users (Web users + Authentication + authorization) | 10 | 1.25 | Web Application | Software & System | Comments
13 | Customer management | 10 | 1.25 | Language(s) | PHP, CodeIgnitor
14 | invoice management | 12 | 1.5 | Development Environment | Eclipse
15 | Courier vendor management | 16 | 2 | Application Version Minimum Compatibility | Modern Web Browser
16 | Order management | 16 | 2 | Back End Database | MySQL
17 | Reports management (4 reports @ 6 Hrs) | 24 | 3
18 | Manage special promotions | 16 | 2
19 | Update job status changes | 6 | 0.75
20 | SMS / email messages | 8 | 1
21 | Generate Order reference numbers & AWB | 6 | 0.75
22 | Mobile Api Development | 38 | 4.75
Testing
| QA (IOS + Android + Web) | 96.8 | 12.1
| Total effort | 436.68 | 54.585

## Sheet1
Mobile Application Module Requirements | Importance | Design Possibilities | Charges Included in proposal | Additional Cost If applicable | Mobile Application (IOS) | Software & System | Comments
Login Page | Mandatory | YES | YES | NO | Language(s) | Obj-C
Manage Profile | Mandatory | YES | YES | NO | Development Environment
Subscription Model | Mandatory | YES | YES | NO | Application Version Minimum Compatibility | Any
Menu List | Mandatory | YES | YES | NO | Back End Database
Dash Board | Mandatory | YES | YES | NO | Mobile Application (Android)
Order Management | Mandatory | YES | YES | NO | Language(s) | Java
Cart Listing | Mandatory | YES | YES | NO | Development Environment | Android Studio
Payment Gateway Integration | Mandatory | YES | YES | NO | Application Version Minimum Compatibility | Kitkat and above
Push Notifications | Mandatory | YES | YES | NO | Back End Database | Any
General App Configuration settings | Mandatory | YES | YES | NO
Feedback / Contact Page | Mandatory | YES | YES | NO
Terms and Conditions , FAQ , How to Use App pages | Mandatory | YES | YES | NO
Contributions to album through invitation | Mandatory | YES | YES | NO
SMS Gateway Integration | Mandatory | YES | YES | NO
Logo Designing | Mandatory | YES | YES | NO
Promotions in Social Media of the Product | Mandatory | YES | YES | NO
Any Limitation in Number of Pages or Forms in mobile app | Mandatory | YES | YES | NO