## Effort Estimate
New | [5 empty] | Old
Resource | # | Man Hours | Man Days | Total |  | Resource | # | Man Hours | Man Days
Project Management | 1 | 180.8 | 22.6 | 22.6 | Mobile + Web | project Management | 1 | 33.88 | 4.235
Business Analysis | 1.5 | 42.6667 | 8 | 12 | Mobile + Web | Business Analysis | 1 | 32 | 4
UI/UX + Working prototypes | 2 | 44 | 11 | 22 | IOS + Android + Web | UI/UX + Working prototypes | 2 | 88 | 22
IOS | 1.5 | 344.6667 | 64.625 | 96.9375 | IOS Dev | IOS | 1 | 364 | 45.5
Android | 1.5 | 344.6667 | 64.625 | 96.9375 | Android Dev | Android | 1 | 364 | 45.5
WEB | 2 | 443 | 110.75 | 221.5 | Web Dev only | WEB | 1 | 242 | 30.25
QA | 2 | 157.1 | 39.275 | 78.55 | (IOS + Android + Web) | QA | 2 | 48.4 | 12.1
Total Effort |  |  | 320.875 |  |  | Total Effort |  |  | 163.585
| Man Days | Man Months |  |  |  |  | Man Days
Total Effort | 320.875 | 16.0437 |  |  |  | Total Effort | 163.585
Delivery Days | 78 | 3.9 |  |  |  | Delivery Days | 66.55
QA +Dev + UI/UX
17+55+6

## Web
Electronic Document Center
# | Activity | Hours | Days
1 | Business Analysis & Documentation( SRS, FS, User Manuals, Weekly Reports) | 32 | 4
2 | UI/UX | 48 | 6
3 | Project Management | 88.6 | 11.075
| UI Design | 0
4 | Page Design (developer) | 0 | 0
| Development | 0
| Customer Portal | 0
Customer Registration
6 | Login / Registration (with billing Address, delivery Address etc.) | 16 | 2
7 | OTP Verification | 6 | 0.75
8 | E-mail Id verification | 6 | 0.75
9 | Push notification in mobile to verify registration | 6 | 0.75
10 | I am not a Robot CAPTCHA checking process | 4 | 0.5
11 | Bilingual (Arabic & English) | 20 | 2.5
12 | Manage Profile | 8 | 1
13 | DashBoard | 16 | 2
Order Management
14 | Product Search | 8 | 1
15 | Filter and Sort products | 6 | 0.75
16 | Add to cart | 12 | 1.5
17 | Photo Print options | 8 | 1
18 | Upload Pics from gallery | 8 | 1
19 | Product Customization | 12 | 1.5
20 | Upload Printable Documents (PDF format) | 8 | 1
21 | Load photos into Azure web drive (Cloud) | 12 | 1.5
22 | Select photos from cloud | 8 | 1
23 | Edit the album, rearrange the photos according to the selected option | 8 | 1
24 | Select the type of Print | 4 | 0.5
25 | Preview the album/photo | 4 | 0.5
26 | List cart | 8 | 1
27 | Modify Cart | 12 | 1.5
28 | Cart Check Out | 8 | 1
29 | Pickup Options | 6 | 0.75
30 | Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) | 4 | 0.5
31 | Collect credit card details | 8 | 1
32 | Process Payment / Cash on Delivery Option | 12 | 1.5
33 | Push notification to mobile regarding txn | 4 | 0.5
34 | Email Transaction Details | 4 | 0.5
| Notifications | 0
35 | Order Status changes | 8 | 1
General features
36 | Feedback/Contact Us | 8 | 1
37 | Contributions to album through invitation | 12 | 1.5
38 | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | 16 | 2
40 | Social Media Integration ( FB, Instagram, PinInterest, Google +) | 12 | 1.5
41 | Connecting People | 12 | 1.5
42 | Display & import Contacts from social network | 12 | 1.5
43 | Services Listing | 8 | 1
44 | Subscription Listing | 8 | 1
45 | Subscribe to service | 8 | 1
Admin Portal
| Manage Orders | 12 | 1.5
| Manage products | 12 | 1.5
| Manage promotions | 12 | 1.5
| Manage Discounts (Volume, Paper Quality, Size) | 8 | 1
| Manage Application users | 20 | 2.5
| Manage roles | 12 | 1.5
| Manage customers | 12 | 1.5
| Manage bilingual product headings | 16 | 2
| Image management (resolution, Content, legal, Quality) and moderation | 28 | 3.5
| Manage subscriptions | 8 | 1
| Manage Payment gateway | 24 | 3
| ERP Jobs management | 8 | 1
| Reports Management | 24 | 3
| Manage Invoices (Print, Email option) | 20 | 2.5
| Manage Deliveries | 16 | 2
| Manage Couriers | 16 | 2
| Manage Vat, tax calculations | 16 | 2
Generic App (Mobile & Web) features
Mobile Menu
| Dashboard (Home Screen) | 16 | 2
| Social media Linking | 4 | 0.5
| Generate Order ID for order fulfillment | 4 | 0.5
| order id (reference #) for admin | 4 | 0.5
| Payment Gateway Integration with EDC specified vendor | 8 | 1
| Dashboard for monitoring Order status | 8 | 1
| Bilingual ( Arabic/ English) | 0
| Automatic App Updates | 0
| Azure cognitive service for image classification, legality, description and tagging | 24 | 3
| Image storage limits limited by subscription package | 4 | 0.5
System
| Discounts based on Order Volume | 4 | 0.5
| Discounts based on size | 4 | 0.5
| Discounts based on paper matererial | 4 | 0.5
| Maintain Vat charges based on product type | 4 | 0.5
| Automatic Price change based on discounts | 4 | 0.5
| integration with Courier Vendor for AWB | 8 | 1
| Azure Cloud storage integration with encryption | 24 | 3
| ERP Integration (Jobs) | 0
| Payment G/W with multi currency option | 8 | 1
| Azure cognitive service API integration | 16 | 2
| SMS Gateway Integration | 20 | 2.5
| Social Media Integration | 8 | 1
| Print Queue | 16 | 2
| Print Service | 16 | 2
| Api Integration | 0 |  |  |  | Time with 2 developers
46 | Mobile Api Integration | 64 | 8 | Dev | 886 | 55.375
| QA | 0
48 | Functional testing | 265.8 | 33.225
49 | UAT | 0
Deployment
50 | Package & Deployment
| Total | 1151.8 | 143.975
For image verification - need to purchase the Google Vision API

## WebOld
Electronic Document Center
WEB
Arabic & English
# | Modules | Hours | Days
| UI Design |  |  | Web Application Module Requirements | Importance | Design Possibilities | Charges Included in proposal | Additional Cost If applicable
1 | Business Analysis + Project documentation (SRS,FS, Weekly Reports, Usermanuals) | 32 | 4 | Web Login Page | Mandatory | Yes | Yes | NO
2 | Project Management | 33.88 | 4.235 | Web Dash Board | Mandatory | Yes | Yes | NO
3 | UI/UX (WEB + Mobile) | 32 | 4 | Admin Settings | Mandatory | Yes | Yes | NO
| Development |  |  | Customer Management | Mandatory | Yes | Yes | NO
4 | Basic Setup | 8 | 1 | Order Management | Mandatory | Yes | Yes | NO
5 | Admin Settings | 16 | 2 | Reports Management | Mandatory | Yes | Yes | NO
6 | Auditing + logging + exception handling | 12 | 1.5 | Invoice Management | Mandatory | Yes | Yes | NO
7 | Contact US | 4 | 0.5 | Promotions Management | Mandatory | Yes | Yes | NO
8 | Dashboard | 16 | 2 | Delivery Management | Mandatory | Yes | Yes | NO
9 | Manage subscription models | 8 | 1 | Courier Vendor Management | Mandatory | Yes | Yes | NO
10 | Manage delivery options | 8 | 1 | Contact Us | Mandatory | Yes | Yes | NO
11 | Manage prices (delivery + print/image etc.) | 8 | 1
12 | Manage users (Web users + Authentication + authorization) | 10 | 1.25 | Web Application | Software & System | Comments
13 | Customer management | 10 | 1.25 | Language(s) | PHP, CodeIgnitor
14 | invoice management | 12 | 1.5 | Development Environment | Eclipse
15 | Courier vendor management | 16 | 2 | Application Version Minimum Compatibility | Modern Web Browser
16 | Order management | 16 | 2 | Back End Database | MySQL
17 | Reports management (4 reports @ 6 Hrs) | 24 | 3
18 | Manage special promotions | 16 | 2
19 | Update job status changes | 6 | 0.75
20 | SMS / email messages | 8 | 1
21 | Generate Order reference numbers & AWB | 6 | 0.75
22 | Mobile Api Development | 38 | 4.75
Testing
| QA (IOS + Android + Web) | 96.8 | 12.1
| Total effort | 436.68 | 54.585

## Mobile
Electronic Document Center
|  | Android |  | iOS
|  | Arabic & English |  | Arabic & English
# | Activity | Hours | Days | Hours | Days
1 | Business Analysis & Documentation( SRS, FS, User Manuals, Weekly Reports) | 32 | 4 |  | 0
2 | UI/UX | 40 | 5 | 40 | 5
3 | Project Management | 60.2 | 7.525
UI Design
4 | Page Design (developer) | 85 | 10.625 | 85 | 10.625
Development
Customer Registration
5 | Splash Screen | 4 | 0.5 | 4 | 0.5
6 | Login / Registration (with billing Address, delivery Address etc.) | 8 | 1 | 8 | 1
7 | OTP Verification | 4 | 0.5 | 4 | 0.5
8 | E-mail Id verification | 4 | 0.5 | 4 | 0.5
9 | Push notification in mobile to verify registration | 12 | 1.5 | 12 | 1.5
10 | I am not a Robot CAPTCHA checking process | 8 | 1 | 8 | 1
11 | Bilingual (Arabic & English) | 48 | 6 | 48 | 6
12 | Manage Profile | 12 | 1.5 | 12 | 1.5
13 | DashBoard | 16 | 2 | 16 | 2
| Order Management |  | 0 |  | 0
14 | Product Search | 12 | 1.5 | 12 | 1.5
15 | Filter and Sort products | 6 | 0.75 | 6 | 0.75
16 | Add to cart | 12 | 1.5 | 12 | 1.5
17 | Photo Print options | 10 | 1.25 | 10 | 1.25
18 | Upload Pics from gallery | 6 | 0.75 | 6 | 0.75
19 | Product Customization | 6 | 0.75 | 6 | 0.75
20 | Upload Printable Documents (PDF format) | 12 | 1.5 | 12 | 1.5
21 | Load photos into Azure web drive (Cloud) | 24 | 3 | 24 | 3 |  |  | time with 1.5 developers
22 | Select photos from cloud | 12 | 1.5 | 12 | 1.5 | Dev And | 517 | 43.0833
23 | Edit the album, rearrange the photos according to the selected option | 16 | 2 | 16 | 2 | Dev IOS | 517
24 | Select the type of Print | 8 | 1 | 8 | 1
25 | Preview the album/photo | 6 | 0.75 | 6 | 0.75
26 | List cart | 6 | 0.75 | 6 | 0.75
27 | Modify Cart | 6 | 0.75 | 6 | 0.75
28 | Cart Check Out | 8 | 1 | 8 | 1
29 | Pickup Options | 6 | 0.75 | 6 | 0.75
30 | Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) | 12 | 1.5 | 12 | 1.5
31 | Collect credit card details | 8 | 1 | 8 | 1
32 | Process Payment / Cash on Delivery Option | 32 | 4 | 32 | 4
33 | Push notification to mobile regarding txn | 6 | 0.75 | 6 | 0.75
34 | Email Transaction Details | 6 | 0.75 | 6 | 0.75
| Notifications |  | 0 |  | 0
35 | Order Status changes | 6 | 0.75 | 6 | 0.75
| General features |  | 0 |  | 0
36 | Feedback/Contact Us | 8 | 1 | 8 | 1
37 | Contributions to album through invitation | 6 | 0.75 | 6 | 0.75
38 | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | 35 | 4.375 | 35 | 4.375
39 | View App in guest mode | 16 | 2 | 16 | 2
40 | Social Media Integration ( FB, Instagram, PinInterest, Google +) | 24 | 3 | 24 | 3
41 | Connecting People | 8 | 1 | 8 | 1
42 | Display & import Contacts from social network | 8 | 1 | 8 | 1
43 | Services Listing | 4 | 0.5 | 4 | 0.5
44 | Subscription Listing | 4 | 0.5 | 4 | 0.5
45 | Subscribe service | 4 | 0.5 | 4 | 0.5
| Api Integration |  | 0 |  | 0
46 | Api Integration | 42 | 5.25 | 42 | 5.25
| Testing |  | 0 |  | 0
47 | Developer side testing & debugging | 16 | 2 | 16 | 2
| QA |  | 0 |  | 0
48 | Functional testing | 155.1 | 19.3875 | 155.1 | 19.3875
49 | UAT | 8 | 1 | 8 | 1
| Deployment |  | 0 |  | 0
50 | Package & Deployment | 8 | 1 | 8 | 1
| Total | 773.1 | 96.6375 | 773.1 | 96.6375

## MobileOld
Electronic Document Center
Android/iOS
Arabic & English
# | Modules | Hours | Days
| UI Design |  |  | Mobile Application Module Requirements | Importance | Design Possibilities | Charges Included in proposal | Additional Cost If applicable
| Page Design | 72 | 9 | Login Page | Mandatory | YES | YES | NO
| Development |  |  | Manage Profile | Mandatory | YES | YES | NO
1 | Basic Setup | 12 | 1.5 | Subscription Model | Mandatory | YES | YES | NO
2 | Splash Screen | 6 | 0.75 | Menu List | Mandatory | YES | YES | NO
3 | Login page | 6 | 0.75 | Dash Board | Mandatory | YES | YES | NO
4 | DashBoard | 12 | 1.5 | Order Management | Mandatory | YES | YES | NO
5 | Registration page | 6 | 0.75 | Cart Listing | Mandatory | YES | YES | NO
6 | Manage profile (delivery address, credit card details) | 8 | 1 | Payment Gateway Integration | Mandatory | YES | YES | NO
7 | Model type listing | 8 | 1 | Push Notifications | Mandatory | YES | YES | NO
8 | Subscription Model | 8 | 1 | General App Configuration settings | Mandatory | YES | YES | NO
9 | On the Pay As You Go Model | 8 | 1 | Feedback / Contact Page | Mandatory | YES | YES | NO
10 | Menu List | 6 | 0.75 | Terms and Conditions , FAQ , How to Use App pages | Mandatory | YES | YES | NO
11 | Menu List Details page | 6 | 0.75 | Contributions to album through invitation | Mandatory | YES | YES | NO
12 | Home Screen with photo print options | 10 | 1.25 | SMS Gateway Integration | Mandatory | YES | YES | NO
13 | Add and Order | 44 | 5.5 | Logo Designing | Mandatory | YES | YES | NO
14 | - Select the type of Print |  | 0 | Promotions in Social Media of the Product | Mandatory | YES | YES | NO
15 | - Load photos from gallery |  | 0 | Any Limitation in Number of Pages or Forms in mobile app | Mandatory | YES | YES | NO
16 | - Select photos from Gallery |  | 0
17 | - Edit the album, rearrange the photos according to the selected option Preview the album/photo |  | 0
18 | - Contribution to album through invitation | 12 | 1.5
19 | - Add to Cart |  | 0 | Mobile Application (IOS) | Software & System | Comments
20 | Order Management | 16 | 2 | Language(s) | Obj-C
21 | Cart listing | 8 | 1 | Development Environment
22 | Cart list details page | 6 | 0.75 | Application Version Minimum Compatibility | Any
23 | Checkout, Pricing | 10 | 1.25 | Back End Database
24 | Delivery Options (subscription, pay as you go, cash on delivery) | 6 | 0.75 | Mobile Application (Android)
25 | Payment gateway integration | 40 | 5 | Language(s) | Java
26 | Push notification based on order status | 32 | 4 | Development Environment | Android Studio
27 | Settings page | 8 | 1 | Application Version Minimum Compatibility | Kitkat and above
28 | Feedback/Contact Us | 6 | 0.75 | Back End Database | Any
29 | Multiple Currency/ Bilingual | 16 | 2
30 | Inner Pages like About Us, Terms and Conditions, How to Use, FAQ etc | 8 | 1
Api Integration
31 | Api Integration | 32 | 4
Testing
32 | Developer side testing | 24 | 3
| Total effort | 364 | 45.5
Assumption
This application will support Android Sdk version 19(kitkat) and above, iOS 9.0 and above
cloud hosting of pics
multicurrency based on payment gateway

## Image
Features of Mobile Application module |  | Web Application Module | System | `
| Customer Registration | Customer Registration | Discounts based on Order Volume
| Splash Screen | Login / Registration (with billing Address, delivery Address etc.) | Discounts based on size
| Login / Registration (with billing Address, delivery Address etc.) | OTP Verification | Discounts based on paper matererial
| OTP Verification | E-mail Id verification | Maintain Vat charges based on product type
| E-mail Id verification | Push notification in mobile to verify registration | Automatic Price change based on discounts
| Push notification in mobile to verify registration | I am not a Robot CAPTCHA checking process | integration with Courier Vendor for AWB
| I am not a Robot CAPTCHA checking process | Bilingual (Arabic & English) | Azure Cloud storage integration with encryption
| Bilingual (Arabic & English) | Manage Profile | ERP Integration (Jobs)
| Manage Profile | Dashboard | Payment G/W with multi currency option
| DashBoard | Order Management | Azure cognitive service API integration
| Order Management | Product Search | SMS Gateway Integration
| Product Search | Filter and Sort products | Social Media Integration
| Filter and Sort products | Add to cart | Print Queue
| Add to cart | Photo Print options | Print Service
| Photo Print options | Upload Pics from desktop or google drive, dropbox, one drive, social media
| Upload Pics from gallery | Product Customization
| Product Customization | Upload Printable Documents (PDF format) | Generic App (Mobile & Web) features
| Upload Printable Documents (PDF format) | Load photos into Azure web drive (cloud) | Mobile Menu
| Load photos into Azure web drive (Cloud) | Select photos from cloud | Dashboard (Home Screen)
| Select photos from cloud | Edit the album, rearrange the photos according to the selected option | Social media Linking
| Edit the album, rearrange the photos according to the selected option | Select the type of Print | Generate Order ID for order fulfillment
| Select the type of Print | Preview the album/photo | order id (reference #) for admin
| Preview the album/photo | List cart | Payment Gateway Integration with EDC specified vendor
| List cart | Modify Cart | Dashboard for monitoring Order status
| Modify Cart | Cart Check Out | Bilingual ( Arabic/ English)
| Cart Check Out | Pickup Options | Automatic App Updates
| Pickup Options | Fee Calculation (based on package, paper, size, discounts, promotions, vat etc.) | Azure cognitive service for image classification, legality, description and tagging
| Fee Calculation (based on package, paper, size, discounts, promotions, Vat etc.) | Collect credit card details | Image storage limits limited by subscription package
| Collect credit card details | Process Payment / Cash on Delivery Option
 | Process Payment / Cash on Delivery Option | Push notification to mobile regarding txn
 | Push notification to mobile regarding txn | Email Transaction Details
 | Email Transaction Details | Notifications
• | Notifications | Order Status changes
• | Order Status changes | General features
• | General features | Feedback/Contact Us
• | Feedback/Contact Us | Contributions to album through invitation | Admin
• | Contributions to album through invitation | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | Manage Orders
• | Additional Pages like About Us, Terms and Conditions, How to Use, FAQ (maximum of 5 pages) | View Web App in Guest mode | Manage products
• | View App in guest mode | Social Media Integration ( FB, Instagram, PinInterest, Google +) | Manage promotions
• | Social Media Integration ( FB, Instagram, PinInterest, Google +) | Connecting People | Manage Discounts (Volume, Paper Quality, Size)
• | Connecting People | Display & import Contacts from social network | Manage Application users
| Display & import Contacts from social network | Services Listing | Manage roles
• | Services Listing | Subscription Listing | Manage customers
• | Subscription Listing | Subscribe service | Manage bilingual product headings
• | Subscribe service |  | Image management (resolution, Content, legal, Quality) and moderation
• |  |  | Manage subscriptions
• |  |  | Manage Payment gateway
• |  |  | ERP Jobs management
• |  |  | Reports Management
• |  |  | Manage Invoices (Print, Email option)
• |  |  | Manage Deliveries
 |  |  | Manage Couriers
Manage Vat, tax calculations

## Sheet3
Assumptions
Customer will procure SMS gateway
Customer will procure payment gateway
Customer will procure Azure cognitive servicesz
Customer will procure Azure cloud storage
Customer will provide detailed documentation related to integration with courier service, delivery service & ERP
Customer will procure libraries/API related to report generation and charts (if needed)
Integration with social media accounts subject to media company policies
Mobile app integration with device hardware is subject to explicit user approval
Application shall not store information related to user credit/debit cards
Uploaded Zip files may not be automatically unzipped unless Azure supports it
Application shall be bilingual (English & Arabic only)
Features of Web Portal Application:
a. Login
b. Dashboard
c. Admin settings
d. Customer management
e. Order management
f. Reports
g. Invoice Management (View, Print)
h. Special Promotion management
i. Delivery Management (View Delivery Mode, Update Delivery Status, Generate AWB)
j. Courier Vendor Management (Add / Edit / Delete Vendor)
k. Contact Us
Web application process flow
A web portal needs to be developed for the client’s digital print unit for order management.
· Web Portal shall get a notification on the order placed by the user with order reference number.
· Additional modules to monitor and process the order placed by customers
· Application will get updated automatically
· Application will auto generate an invoice for each order
· Client shall download the photos related to the order from the cloud / server and does the print fulfillment.
· Integration of website with courier vendor application
· Client to generate / enter an AWB Number if the delivery mode is by courier.
· Client to update the job completion for the order reference number along with the AWB number if the delivery mode is by courier
· Once updated, a notification to be triggered to the user’s mobile app with the AWB number details or notification for pickup timing.
· On delivery of the booklet, the details to be updated across the order reference number
· Custom Vision- to reduce mammography image quality issues
· Content Moderator- for controlling explicit or offensive contents
· Image storage based on subscription package
· Website development using Microsoft Azure cognitive
· Client should be able to update the special promotion page with products and different pricing which needs to be integrated and reflected in the mobile app for the end user.
· Customer should be able to upload from DropBox, Google Drive, local hard drive, one drive accounts and SD card also
Connecting people page in web app