## Sheet1
Project Name : MyFX
Inputs |  | Estimation Summary (Hours and Business days)
| Requirement gathering | 16
| Research and analysis | 12
Design | Splash screen | 5
| Login Page | 5
| Registration Page | 5
| Home page | 5
| Map view | 3
| Popup Page(Requst sending) | 2
| Curency detail page | 5
| Qrcode Showing Page | 3
Development | Login api integration | 3
| Registration api integration | 5
| Home page api integration | 5
| Map integration | 8
| Map customization | 8
| Curency detail page Api integration | 6
| Qrcode Showing Page Api integration | 6
| Qrcode Saving Localy | 8
| Push notification | 16
| Google store cofiguration | 16
| Social media sdk integration for face book | 16
| Scocial media google integration | 16
| Scocial media signup(Facebook) Api integration | 5
| google signup Api integration | 4
Basic setup | Library integration | 5
| Project creation and basic setup | 4
| Total Hours | 192
| Total Days | 24