## Estimate
Project Name : Crowd Invest Mobile Development Estimate ( Android )
Inputs |  | Estimation Summary (Hours and Business days)
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 10 | Optimistic hours | 442.8 | 31.6286 |  | 36.9
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 10 | Most likely hours** | 509.22 | 36.3729 | 3200 | 36.9
Average productive hours per day | 7 | Pessimistic hours* | 575.64 | 41.1171 |  | 132.84 | Holidays in 2016 | Date
Estimation parameters | Hours | [5 empty] | New Year's Day | 2016-01-01
Requirement gathering | 16 | Expected Duration |  | Hours |  |  | Republic Day | 2016-01-26
Research and analysis | 8 | Triangular distribution method |  | 36.3729 |  |  | Monty Thursday | 2016-03-24
Development | 220 | Beta distribution (PERT technique) |  | 36.3729 |  |  | Good Friday | 2016-03-25
Design | 40 | [5 empty] | Vishu | 2016-04-14
Testing | 44 | Finish Date |  |  |  |  | May Day | 2016-05-01
Training | 0 | Earliest start date | 07/01/2016 |  |  |  | Assembly Elections | 2016-05-16
Documentation | 8 | Earliest completion date | 2016-08-15 | Optimistic |  |  | Onam | 2016-09-13
Meetings | 16 | Earliest completion date | 2016-08-22 | Most likely |  |  | Onam | 2016-09-14
Migration (data or content) | 0 | Earliest completion date | 2016-08-29 | Pessimistic |  |  | Onam | 2016-09-15
Project management | 11 | [5 empty] | Gandhu Jayanthi | 2016-10-02
Reports | 0 | Latest start date | 2016-08-01 |  |  |  | Deepavali | 2016-10-29
UAT | 0 | Latest completion date | 2016-09-16 | Optimistic |  |  | Christmas | 2016-12-26
Accessibility test | 0 | Latest completion date | 2016-09-23 | Most likely
Pre deployment process | 1 | Latest completion date | 2016-09-30 | Pessimistic
Deployment | 4
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 30
Knowledge transfer/ Service transition | 1 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 2
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 369
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Hybrid App
| Crowdinvest Mobile app | 2016-06-01
Sl. No. | Product Log | Days | Comments
1 | Authentication / Authorization | 2
Consumer
Money Changer
Administrator
2 | Application Server and Application Setup | 1
Webserver
Rabbit MQ
SQL Server
3 | Constomer WebTop | 7
Map Integration
Preferences
Consumer Interaction Workflow
Registration, login, Fogot PW
Transaction History
Request for Quote
Landing Page (Map View)
Multiple Money Changer View (Map View and left panel view)
Filter (Distance, MC rate, Currency etc)
Sort (Address, Currency, Rate etc)
Place Order
Send Order
AML
KYC
5 | Money Changer WebTop | 7
Office Setup (Map Cordinates, address etc)
Maintain Prices (Commisions and fees)
Maintain Prices (bands and thresholds)
Money Changer Workflow
New Order
Order History
Pending Order
6 | Static pages | 1.5
About Us
Team
FAQ
Contact US
7 | API Services | 4
Integration with Live Quote service for exchange rates
Integration with Message Q's
Integration with AML, KYC
8 | Administrator | 3
Setup base Currency
Setup Money Changer
Manage Customers
Setup Default Language
| Hybrid Android App | 2
conversion of Web App to Hybrid mobile App using PhoneGap and Cordova
| Total | 27.5
| Cumulative Total | 220