## Slide 1
June 28, 2016
Proposal for MyFX
Web and Mobile App Development
V1.1

## Slide 2
Table of Contents
Background & Scope
Solution Overview
Phase 1 – Requirements Gathering and Definition
Phase 2 - Implementation
Future Upgrades in MyFX
Technology Specifications
Commercials and Deliverables
Out of Scope
General Terms & Conditions

## Slide 3
Background & Scope
Eduworks intends to develop a Web and Mobile App product called MyFX aimed at helping individuals to get a faster access to money exchangers across Singapore and Malaysia without any hassles of long queues and calls
The “Money Changers” use a web interface to provide currency exchange services, while the “Consumers” will conduct their transactions using a mobile/tablet interface tailored to meet their needs
As per the initial understanding, MyFX needs two major things:
  Web App – for Money Exchangers
  iOS and Android Mobile App – for Consumers
There will be three major stakeholders in this application, they are:
Super Admin
Money Changers
Consumers
Besides delivery of a working demonstrable version of MyFX, Eduworks has also requested for relevant documentation, manuals and training aids
Verbat proposes its services to engage as Eduworks’ strategic technology partner for the Web and Mobile App development
This document outlines Verbat’s approach towards software development for MyFX, as requested by the client

## Slide 4
Solution Overview
Verbat proposes to conduct the project across two phases:
Phase 1 – Requirements Gathering and Definition
Phase 2 – Implementation
The engagement has been structured such that Phase 2 will build on the information and technical code from Phase 1.
The business process will follow the workflow as per the diagram across 6 steps:
Client searches for FX rates
Application retrieves a list of money changers and displays it in a map with reference to the user’s current location
Client submits his or her RFQ to the money exchanger
Money exchanger either accepts (including “Auto-accept”), modifies or can ignore the request placed by the client
Client confirms and accepts the rates specified. A QR code is generated for authenticating the client
Lastly, client’s identity is verified using QR code and the transaction is complete

## Slide 5
Discovery Phase – Requirements Gathering and Definition
A dedicated phase for Verbat and Eduworks to discuss the detailed business and technical requirements, define the solution approach and deliverables, document these and obtain mutual sign-off
Verbat proposes to deploy a senior Technical Architect and a senior Business Analyst for this phase
The phase will be completed over 10 working days
Deliverables:
  Detailed requirement specifications
  Wireframes for the key screens for the proposed web and mobile apps
  High level technical design
Dependencies:
  Availability of key stakeholders for meetings to discuss requirements and validate findings and deliverables
  Written sign-off for completion, prior to commencement of the next phase

## Slide 6
Phase 1 - Implementation
Money Changer Web functionality :
User authentication and entitlement
Online money changer on-boarding / registration with Business/company name & registration number, MSB license details, address, contact numbers, emails, business hours etc.
Manage daily board rates, soft and hard limit, Threshold levels for buy and Sell Per Currency.
To have a threshold table for auto response to consumer’s Request for Quotation (RFQ)
Ability for money changers to set Auto-acceptance of RFQ’s
Have popup feature for confirmed QR code transaction.
Live dashboard with cancelled, Pending and completed transaction along with notification for incoming transactions
Generate customer invoices.
Incentives for featured customers
Accept a placed order to complete transaction
View transaction history including quotations which are ignored, expired, missed or cancelled and successful transactions
Able to view best buy/Sell, Last Buy/Sell for entire platform, money changers last but=y and sell rate
Money changer registration as functional, featured and listed
Manage money changer’s daily board rate, Hard/Soft Limit
SMS alerts for upcoming transactions.
Ability to complete KYC details at the Money changer
Money Changer Web functionality (Phase 2):
Ability to request for featured listing
Ability to request advertisements
Advanced reporting of commission revenues
MyKad Integration

## Slide 7
Phase 1 - Implementation
Money Changer Mobile App:
Local database to capture user preferences
QR-Code scanner
QR-Code transaction confirmation integration.

## Slide 8
Constomer Mobile App (iOS and Android) Functionality (Phase 1):
User authentication and entitlement (social media login integration)
Ability to view money changers’ lists based on preferences (distance, exchange rate etc.)
Ability to switch views from map based listing to list based.
Ability to request forex rate from money changer’s board rate
Ability to place Request for Quotation (RFQ) from one or more money changers
Place an order on quoted forex and specify the collection time
Retrieve a placed order to complete transaction
Cancel an order
Ability to maintain consumers’ profiles
QR Code integration and authentication (encrypted)
General settings for the app
View money changer’s profile such as name, address, contact numbers, business hours, geolocation
Online consumer on-boarding / registration
Progressive capture of customers KYC details.
Ability transact using online banking.
Consumer Mobile App (iOS and Android) Functionality (Phase 2):
Advertisements
Featured listings
Phase 1 - Implementation

## Slide 9
Web Portal Administration Functionalities : Support (Phase 1):
Functions around user management including authentication and entitlement for entire platform
Money changer management
Manage money changer profiles
Ability to customize trading currency
Manage money changer’s threshold table for auto response to consumer’s RFQ
View transaction history including quotations which are ignored, expired, missed or cancelled and successful transactions
View best buy, last buy and sell for entire platform
Online money changer on-boarding / registration
Audit logs of changes in board rates, cancelled/completed transactions, threshold settings, changes in Hard/Soft Limit
Upgrade moneychanger tiers (Gold, silver, bronze).
Manage Money changer tiers based on functionality offered (e.g. online banking, delivery service, buy back, duration – order forward)
Manage advertisements (start date, end date, priority etc.)
Web Portal Super Admin (Phase 2):
View invoices by money changer
View Commissions earned by money changer
View debtors
Manage content for messages, alerts and terms
Phase 1 - Implementation

## Slide 10
MyFX System Features:
Secure and encrypted communication
QR code encryption
Provision for payment gateway integration
Provision for leveraging and using Market rate (FX)
Phase 1 - Implementation

## Slide 11
In future, upgrades for MyFX’s core engine could include functionalities like:
Financial Institutions Integration (trust account etc)
Loyalty
Mobile Wallet
Instant Transfers
Instant Messaging
Card Issuing / Integration
Bots and others
Future upgrades in MyFX

## Slide 12
Technology Stack:
  Control Panel – cPanel 11.42
  Frameworks – CodeIgniter
  Language - PHP
  Database - MySQL
  Server - Apache 2.4.9
  Operating System – Linux
  Native Mobile apps – iOS and Android
  Server and Hosting Recommendation
  Memory – 4 GB
  Processors: Intel Xeon Dual core 2.3GHz
  HDD Quota - 10 GB
  Monthly Transfer (Bandwidth) – 500 GB/ month
Technology Specifications

## Slide 13
Commercials and Deliverables
In this project we are going ahead with a fixed price option. Verbat will be developing a Web Application and Native Mobile Apps in both iOS and Android for MyFX.
The total price for Phase 1 will be £2,000 and the indicative price for Phase 2, based on Verbat’s current understanding, will be £27,100, with a payment schedule as per the table below.
July | July-Aug | Aug-Sept | Sept
Phase 1 | Phase 2a | Phase 2a | Phase 2b
Requirements Gathering and Definition | Implementation | Implementation | Implementation
Deliverables | Deliverables |  | 
Detailed Requirement Specification | Admin Web modules | Android App | Android App Updates
High level Design Specification | Consumer Web App | iOS App | iOS App Updates
Wireframes | APIs for Mobile Apps | Consumer App updates | Reporting in Web Apps
Advance Amount (100%) | Advance Amount (25%) | On Delivering Phase 2a (50%) | On Delivering Phase 2b (25%)
£2,000 | £6,775 | £13,550 | £6,775
+ pre-approved expenses at actuals |  |  | 
Note: Eduworks’ initial commitment is only for Phase 1. The final composition of Phase 2 is dependent on the findings at the end of Phase 1 and, therefore, subject to change. Verbat will provide its final recommendation for Phase 2 along with the Phase 1 deliverables.

## Slide 14
Following details will be out of scope from the current project
Web hosting
Domain name purchase and registration
Any form of content or image procurement
Manual Data Entry
Any Third Party Software Licenses
Printing formatted output
Out of Scope

## Slide 15
An average of 20 working days are assumed in a month
Payment for Phase 1 will be in advance against invoice to Verbat’s nominated bank account by wire transfer
Payment for Phase 2 will be as per payment schedule against invoice to Verbat’s nominated bank account by wire transfer
This proposal and all technical/ functional specifications have been derived or concluded from the data shared via email / information transferred during the initial requirement analysis meetings and conversations. Verbat reserves the right to amend the terms of this proposal, should the SOW terms, application features and functionalities change during the course of the project
The application will be built as per the specifications agreed mutually. Any changes will be executed through a defined change management process between Eduworks and Verbat
All Source Code and other project artifacts would adhere to the Verbat document templates and internal coding standards
Since the deployment will be done on hardware owned and maintained by Eduworks, Verbat cannot be held responsible for any performance issues arising due to hardware malfunctions
Verbat will provide a bug fix warranty at no additional cost for 30 days from the date of acceptance of the project, for correction of any errors in the developed application that may be attributed to Verbat
General Terms & Conditions

## Slide 16
Thank You
+44 20 8090 1461
sales.uk@verbat.com
3rd Floor 207 Regent Street London W1B 3HH
UAE
217, Sheikh Rashid Bldg.,
P.O Box 56272 Dubai
India
Level 3, PTC Tower
Nanthancode
Trivandrum – 695003
Kerala
USA
2033 Gateway Place
Suite 500
San Jose
CA 95110