## EGMA
2018-01-06
Friday
EGMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 64 | 8 | 8
Functional Specification | 12 | 1.5 | Web Developer | 1 | 192 | 24 | 24 | 0 | 48 | 1.6
Project Management | 0 | 0 | Web Developer | 1 | 192 | 24 | 24
Graphic Design (Android App + Web application) | 32 | 4 | Android Developer | 0 | 0 | 0 | 0
Working Prototype (Web) | 32 | 4 | PM | 1 | 36 | 4.5 | 4.5
Development |  |  | QA | 2 | 3 | 0.375 | 0.75 | 490
Optometrist Portal |  |  | Technical Writer | 0 | 0 | 0 | 0
Add / Edit Delete Customers |  | 0 | Total |  | 487 |  | 61.25
Create Customer Profile |  | 0
Manage Photos |  | 0 | Total Delivery days | 32.375 | 1.6187
Manage Cases |  | 0 | Total Man day Effort | 61.25
Manage Customer Documents |  | 0
Manage Referrals |  | 0
Customer Consent |  | 0
Repeat customer reminders |  | 0
Create Appointments |  | 0
Doctors Portal
Verify Customer Eye Condition |  | 0
create Appointments |  | 0 |  |  |  |  | notify customer
Create customer report |  | 0
Create medical history |  | 0
Create Eye test results |  | 0
View customer reports |  | 0
Admin Portal
Admin Dashboard |  | 0
Outlet / Brand management (Outlet Master) |  | 0
Manage doctors office within Outlets |  | 0
Coutry and City Master
Manage Optometrist shops within Outlets (Store Master) |  | 0
Create & Manage Users |  | 0
Create & manage Roles |  | 0
News broardcast module |  | 0
Bulk data upload for outlets (Shops, doctors offices, users) |  | 0
Portal admin Access to all stores , doctors offices |  | 0
Upload & manage documents |  | 0
Manage Referrals |  | 0
BI Reports (Outletwise, storewise, Doctors officewise, Regionwise, customerwise) |  | 0
preformatted templates |  | 0
Manage Referrals and Prospects |  | 0
System
SMS & Emails |  | 0
Desktop Notification |  | 0
Mobile push notifications |  | 0
Image and file management (Document Management) |  | 0
Scheduling |  | 0
Authentication and authorization |  | 0
Logging and auditing |  | 0
Exception handling |  | 0
Smart Notifications based on triggers |  | 0
Storefront workflow |  | 0
Doctors Office Workflow |  | 0
Batch Processes
Security (SQL, Web) |  | 0
Adminsitrative |  | 0
Data Migration |  | 0
Documentation (User manuals) |  | 0
Testing & Deployment
Testing | 0 | 0
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 112 | 14
14
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application