## EGMA
2018-01-06
Friday
EGMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 24 | 3 | Designer | 1 | 48 | 6 | 6
Functional Specification | 12 | 1.5 | Web Developer | 1 | 192 | 40 | 40 | 81 | 81 | 1.6
Project Management | 63.6 | 7.95 | Web Developer | 1 | 192 | 41 | 41
Graphic Design (Android App + Web application) | 24 | 3 | Android Developer | 1 | 1 | 12.2 | 12.2
Working Prototype (Web) | 24 | 3 | PM | 1 | 99.6 | 12.45 | 12.45
Development |  |  | QA | 2 | 90 | 11.25 | 22.5 | 1073.2
Optometrist Portal |  |  | Technical Writer | 0 | 0 | 0 | 0
Register / Login / forgot Password / remember password | 12 | 1.5 | Total |  | 622.6 |  | 134.15
Manage Customer Profile | 16 | 2
Create Customer Profile (Identify Prospects from Clients) | 8 | 1 | Total Delivery days | 58.25 | 2.9125
Receive notifications (on the portal) | 6 | 0.75 | Total Man day Effort | 134.15
Manage Photos | 16 | 2
Manage Cases (Optometrist report, Opthalmologist report, related invoice) | 16 | 2
Manage Customer Documents | 16 | 2
Manage Referrals | 8 | 1
Customer Consent | 4 | 0.5
Repeat customer reminders (Repeat business: Part of smart notification) | 12 | 1.5
Create Appointments | 8 | 1
Send customer email link for appointment | 6 | 0.75
View customer reports (summary and detail) | 16 | 2
Customer Portal
Register / Login / forgot Password / remember password | 12 | 1.5
Eye Scan Results (Doctors Note) | 6 | 0.75
Create Appointments from email links (Acknowledge or accept) | 6 | 0.75
Reschedule Appointment | 6 | 0.75
View Order details | 6 | 0.75
View Bill (invoice) | 6 | 0.75
Receive notifications (on the portal) | 6 | 0.75
Send message (Opthalmologist & optometrist) | 6 | 0.75
Doctors Portal
Login / Forgot password/ Remember password | 12 | 1.5
Manage Client Profile | 6 | 0.75
Verify Customer Eye Condition (manage Cases) | 8 | 1
Manage Appointments | 12 | 1.5
Manage Referrals | 6 | 0.75
Manage Documents | 6 | 0.75
Manage Cases (Optometrist report, Opthalmologist report, related invoice) | 8 | 1
Send Custmer email link for apppointment | 6 | 0.75
Create customer report | 8 | 1
Create medical history | 12 | 1.5
Create Eye test results | 8 | 1
View customer reports (summary and detail) | 16 | 2
Receive notifications (on the portal) | 6 | 0.75
Admin Portal
Admin Dashboard | 16 | 2
Outlet / Brand management (Outlet Master) | 12 | 1.5
Manage doctors office within Outlets | 16 | 2
Coutry, City & Store Master | 8 | 1
Manage Optometrist shops within Outlets (Store Master) | 12 | 1.5
Create & Manage Users | 8 | 1
Create & manage Roles | 8 | 1
News broardcast module (To Portals Not SMS) | 16 | 2
Bulk data upload for outlets (Shops, doctors offices, users) | 16 | 2
Portal admin Access to all stores , doctors offices | 8 | 1
Upload & manage documents | 8 | 1
Manage Referrals | 8 | 1
BI Reports (Outletwise, storewise, Doctors officewise, Regionwise, customerwise) | 24 | 3
Preformatted templates | 8 | 1
Manage Referrals and Prospects | 8 | 1
System
SMS & Emails | 8 | 1
Desktop Notification | 8 | 1
Image and file management (Document Management) | 12 | 1.5
Scheduling | 12 | 1.5
Authentication and authorixzation | 4 | 0.5
Logging and auditing | 4 | 0.5
Exception handling | 4 | 0.5
Smart Notifications based on triggers | 4 | 0.5
Storefront workflow | 16 | 2
Doctors Office Workflow | 16 | 2
Security (SQL, Web) | 16 | 2
Web API | 8 | 1
Adminsitrative |  | 0
Data Migration | 24 | 3
Documentation (User manuals) | 24 | 3
Testing & Deployment
Testing | 174 | 21.75
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 981.6 | 122.7
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application

## Mobile App
EGMA
# | Modules | Hours | Days
Android
Ui Design
| Page Design | 16 | 2
0
Development
1 | Basic setup | 6 | 0.75
2 | Login Page | 6 | 0.75
3 | Details page | 8 | 1
4 | Search page | 8 | 1
5 | Signature pad | 4 | 0.5
Api Integration
| Json Data | 8 | 1
| Api Integration | 8 | 1
Testing
| Developer side testing | 8 | 1
| Testing | 25.6 | 3.2
| Total effort |  | 12.2
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode