## EGMA
2018-01-06
Friday
EGMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 20 | 2.5 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 192 | 29 | 29 | 58 | 58 | 1.6
Project Management | 45.2 | 5.65 | Web Developer | 1 | 192 | 29 | 29
Graphic Design (Android App + Web application) | 16 | 2 | PM | 1 | 73.2 | 9.15 | 9.15
Working Prototype (Web) | 16 | 2 | QA | 2 | 66 | 8.25 | 16.5
Development |  |  | Technical Writer | 0 | 0 | 0 | 0 | 701.2
Optometrist Portal |  |  | Total |  | 555.2 |  | 87.65
Register / Login / forgot Password / remember password | 12 | 1.5
Manage Customer Profile | 12 | 1.5 | Total Delivery days | 41.25 | 2.0625
Create Customer Profile (Identify Prospects from Clients) | 4 | 0.5 | Total Man day Effort | 87.65
Receive notifications (on the portal) | 6 | 0.75
Manage Photos | 8 | 1
Manage Cases (Optometrist report, Opthalmologist report, related invoice) | 8 | 1
Manage Customer Documents | 8 | 1
Manage Referrals | 6 | 0.75
Customer Consent | 4 | 0.5
Repeat customer reminders (Repeat business: Part of smart notification) | 8 | 1
Manage Appointments | 6 | 0.75
Send customer email link for appointment | 6 | 0.75
View customer reports (summary and detail) | 16 | 2
Customer Appointment
Create Appointments from email links (Acknowledge or accept) | 8 | 1
Doctors Portal
Login / Forgot password/ Remember password | 12 | 1.5
Manage Client Profile | 6 | 0.75
Verify Customer Eye Condition (manage Cases) | 6 | 0.75
Manage Appointments | 6 | 0.75
Manage Referrals | 6 | 0.75
Manage Documents | 6 | 0.75
Manage Cases (Optometrist report, Opthalmologist report, related invoice) | 8 | 1
Send Custmer email link for apppointment | 6 | 0.75
Create customer report | 8 | 1
Create medical history | 8 | 1
Create Eye test results | 8 | 1
View customer reports (summary and detail) | 8 | 1
Receive notifications (on the portal) | 6 | 0.75
Admin Portal
Admin Dashboard | 16 | 2
Outlet / Brand management (Outlet Master) | 8 | 1
Manage doctors office within Outlets | 8 | 1
Coutry, City & Store Master | 8 | 1
Manage Optometrist shops within Outlets (Store Master) | 8 | 1
Create & Manage Users | 8 | 1
Create & manage Roles | 8 | 1
News broardcast module (To Portals Not SMS) | 12 | 1.5
Bulk data upload for outlets (Shops, doctors offices, users) | 12 | 1.5
Portal admin Access to all stores , doctors offices | 6 | 0.75
Upload & manage documents | 6 | 0.75
Manage Appointments | 6 | 0.75
BI Reports (Outletwise, storewise, Doctors officewise, Regionwise, customerwise) | 16 | 2
Preformatted templates | 8 | 1
Manage Referrals and Prospects | 8 | 1
System
SMS & Emails | 8 | 1
Desktop Notification | 8 | 1
Image and file management (Document Management) | 8 | 1
Scheduling | 8 | 1
Authentication and authorization | 6 | 0.75
Logging and auditing | 6 | 0.75
Exception handling | 6 | 0.75
Notifications based on triggers | 6 | 0.75
Storefront workflow | 12 | 1.5
Doctors Office Workflow | 12 | 1.5
Security (SQL, Web) | 8 | 1
Adminsitrative |  | 0
Data Migration | 16 | 2
Documentation (User manuals) | 16 | 2
Testing & Deployment
Testing | 126 | 15.75
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 707.2 | 88.4
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application

## Mobile App
EGMA
# | Modules | Hours | Days
Android
Ui Design
| Page Design | 16 | 2
0
Development
1 | Basic setup | 6 | 0.75
2 | Login Page | 6 | 0.75
3 | Details page | 8 | 1
4 | Search page | 8 | 1
5 | Signature pad | 4 | 0.5
Api Integration
| Json Data | 8 | 1
| Api Integration | 8 | 1
Testing
| Developer side testing | 8 | 1
| Testing | 25.6 | 3.2
| Total effort |  | 12.2
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode