## EGMA
31/05/2018
Thursday
EGMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 192 | 24 | 24 | 47.75 | 48 | 1.6
Project Management | 38.2 | 4.775 | Web Developer | 1 | 192 | 24 | 24
Graphic Design (Android App + Web application) | 0 | 0 | Android Developer | 0 | 0 | 0 | 0
Working Prototype (Web) | 32 | 4 | PM | 1 | 62.2 | 7.775 | 7.775
Development |  |  | QA | 2 | 60.3 | 7.5375 | 15.075 | 598.8
New Order |  |  | Technical Writer | 0 | 0 | 0 | 0
Spectacle Lenses (refraction, Centering, Types, Material, Index, Category, Progression) | 16 | 2 | Total |  | 538.5 |  | 74.85
Individual Parameters | 16 | 2
EyeLT | 16 | 2 | Total Delivery days | 35.5375 | 1.7769
Frame & Centering Data | 16 | 2 | Total Man day Effort | 74.85
Lens Calculation | 16 | 2
Search by User | 16 | 2
Edging vs Glazing | 16 | 2
Order Data | 16 | 2
Order Browser
Open Orders | 8 | 1
Archived Orders | 6 | 0.75
Recycle Bin Orders | 6 | 0.75
Print Orders | 12 | 1.5
Fax Orders | 6 | 0.75
All Orders | 6 | 0.75
Order List | 6 | 0.75
Order Details (Frame, lens, Individual, Shape, Status, Pickup) | 12 | 1.5
Email Orders | 6 | 0.75
Options
Settings |  | 0
Personal Data | 6 | 0.75
Application Data | 6 | 0.75
Printer Configuration | 6 | 0.75
Language | 0 | 0
Update Area | 8 | 1
Service Area | 8 | 1
Price Calculation | 8 | 1
Help
Hotline | 8 | 1
Remote Support | 8 | 1
Measurement (Common, Progressive, Bifocal, Sport) | 12 | 1.5
Manual | 8 | 1
Information | 8 | 1
Other Pages
Home Page | 8 | 1
About | 8 | 1
Privacy | 8 | 1
Legal | 8 | 1
Additional Static Pages (6 hrs / page) | 6 | 0.75
Admin
Master Data |  | 0
lense Types | 4 | 0.5
Lense Material | 4 | 0.5
Lense Index | 4 | 0.5
Lense Category | 4 | 0.5
Lense Progression | 4 | 0.5
Tint | 4 | 0.5
AR Coating | 4 | 0.5
Diameter | 4 | 0.5
Other Master Data (2 hrs/data element) |  | 0
System Features
Auditing & Logging | 6 | 0.75
Authentication & Authorization | 6 | 0.75
Email | 6 | 0.75
Exception handling | 6 | 0.75
Reporting (6 Hrs / Report) | 6 | 0.75
Testing & Deployment
Testing | 114.6 | 14.325
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 602.8 | 75.35
75.35
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application