## EGMA
31/05/2018
Thursday
EGMA
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 16 | 2 | Designer | 1 | 32 | 4 | 4
Functional Specification | 8 | 1 | Web Developer | 1 | 192 | 19 | 19 | 38.5 | 39 | 1.6
Project Management | 30.8 | 3.85 | Web Developer | 1 | 192 | 20 | 20
Graphic Design (Android App + Web application) | 0 | 0 | Android Developer | 0 | 0 | 0 | 0
Working Prototype (Web) | 32 | 4 | PM | 1 | 54.8 | 6.85 | 6.85
Development |  |  | QA | 2 | 49.2 | 6.15 | 12.3 | 497.2
New Order |  |  | Technical Writer | 0 | 0 | 0 | 0
Spectacle Lenses (refraction, Centering, Types, Material, Index, Category, Progression) | 12 | 1.5 | Total |  | 520 |  | 62.15
Individual Parameters | 12 | 1.5
EyeLT | 12 | 1.5 | Total Delivery days | 30.15 | 1.5075
Frame & Centering Data | 12 | 1.5 | Total Man day Effort | 62.15
Lens Calculation | 12 | 1.5
Search by User | 12 | 1.5
Edging vs Glazing | 12 | 1.5
Order Data | 12 | 1.5
Order Browser
Open Orders | 8 | 1
Archived Orders | 6 | 0.75
Recycle Bin Orders | 6 | 0.75
Print Orders | 12 | 1.5
Fax Orders | 6 | 0.75
All Orders | 6 | 0.75
Order List | 6 | 0.75
Order Details (Frame, lens, Individual, Shape, Status, Pickup) | 12 | 1.5
Email Orders | 6 | 0.75
Options
Settings |  | 0
Personal Data | 6 | 0.75
Application Data | 6 | 0.75
Printer Configuration | 6 | 0.75
Language | 0 | 0
Update Area | 8 | 1
Service Area | 8 | 1
Price Calculation | 8 | 1
Help
Hotline | 8 | 1
Remote Support | 8 | 1
Measurement (Common, Progressive, Bifocal, Sport) | 8 | 1
Manual | 8 | 1
Information | 8 | 1
Admin
Master Data |  | 0
lense Types | 4 | 0.5
Lense Material | 4 | 0.5
Lense Index | 4 | 0.5
Lense Category | 4 | 0.5
Lense Progression | 4 | 0.5
Tint | 4 | 0.5
AR Coating | 4 | 0.5
Diameter | 4 | 0.5
Other Master Data (2 hrs/data element) |  | 0
System Features
Auditing & Logging | 6 | 0.75
Authentication & Authorization | 6 | 0.75
Email | 6 | 0.75
Exception handling | 6 | 0.75
Reporting (6 Hrs / Report) | 6 | 0.75
Testing & Deployment
Testing | 92.4 | 11.55
UAT | 6 | 0.75
Deployment Support | 6 | 0.75
Total Effort | 499.2 | 62.4
62.4
Assumptions
The application would be tested in the Google Pixel
The promotions, offers and products will be entered through the custom web application