## Quotation Software
| Elissa Fiber Glass |  | Sep 19 2017
Wednesday
| Module | Hours | Man Days | Web Development
| Initiation |  |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 2 | 2
2 | Functional Specification | 8 | 1 | Sr Developer | 1 | 10 | 10 | 21.125 | 22
3 | Project Management | 16.9 | 2.1125 | Jr Developer | 1 | 12 | 12
4 | Finalising and purchase of HTML Theme & Images (~20 - ~30 Screens) |  | 0 | PM | 1 | 2.1125 | 2.1125
5 | Complete running prototype | 16 | 2 | BA | 1 | 2 | 2
| Development |  |  | QA | 2 | 3.6687 | 7.3375
| Home page |  |  | Total |  |  | 35.45
6 | New Enquiry | 12 | 1.5
7 | New Client | 20 | 2.5 | Total Delivery days | 17.6687 | +1 deployment
8 | New Quotation | 20 | 2.5 | Total Effort | 35.45 | +1 deployment
9 | Home page with menu | 10 | 1.25
10 | Change Enquiry Status | 8 | 1
11 | Change Quotation status | 8 | 1 | [6 empty] | #REF!
12 | Log in / Logout | 6 | 0.75 | [5 empty] | 0
13 | Quotation view mode for clients with URL or link | 6 | 0.75
Report
13 | Enquiries | 12 | 1.5
14 | Quotations | 12 | 1.5
Admin
15 | Manage Users (New/ delete/ alter) | 6 | 0.75
16 | Manage Quotations | 6 | 0.75
17 | Manage Enquiry | 6 | 0.75
18 | Manage Notes | 5 | 0.625
19 | Manage Products (Description, price , Unit) | 8 | 1
20 | Quotation Templates | 8 | 1 | [5 empty] | 0
21 | Manage terms & Conditions | 4 | 0.5
| Systems |  |  | 6.3375
22 | Roles / Entitlements | 6 | 0.75
23 | Logging / Auditing | 6 | 0.75
Testing & Deployment
| Testing | 50.7 | 6.3375
| UAT | 8 | 1
| Deployment | 8 | 1
| Total Effort | 284.6 | 35.575
Estimate Assumptions:
Out of Scope