## Elite Training
| Elite Training | march 03 2017
Wednesday
Sl. No. | Module | Man Days | Phase 1
| Initiation |  |  | No | Man Days | Total Effort
1 | Requirements gathering and documentation (SRS) | 8 | Designer | 1 | 5 | 5
2 | Functional Specification | 4 | Sr Developer | 2 | 20 | 40 | 88 | 88
3 | Project Management | 8 | Jr Developer | 2 | 24 | 48
4 | Finalising and purchase of HTML Theme & Images | 0 | PM | 1 | 20 | 20
5 | Complete running prototype | 10 | QA | 2 | 17 | 34
| Development |  | Total |  |  | 147
Phase 1
| Admin (organizational setup) | 1 | Total Delivery days | 66
5 | User Management | 1 | Total Effort | 147
6 | User Permissions | 1
8 | Authentication & Authorization | 3 | Phase 2 ( Parallel to Phase 1)
9 | Create Scenarios, | 2 |  | No | Man Days | Total Effort
10 | Create Sessions | 1 | Sr Developer | 1 | 10 | 10 | 30
11 | Create Schedules, | 1 | Jr Developer | 1 | 20 | 20
12 | Scheduling Sessions | 1 | QA | 1 | 10 | 10 |  |  | 60
13 | Manage Equipments | 1 | Total |  |  | 40
14 | Manage Weapons | 1
15 | Manage Trainers | 1 | Total Delivery days | *70
16 | Manage Trainees | 1 | Total Effort | 40
17 | Manage Cameras | 3 | * Extra time needed for product minitiarization and wearability
18 | Manage Attendance | 1
19 | Manage Timesheet | 2 | Phase 3
20 | Manage Training Area | 3 |  | No | Man Days | Total Effort
21 | Management Dashboard | 1 | Designer | 1 | 2 | 2
22 | Training Session Status | 1 | Sr Developer | 2 | 14 | 28 | 56 | 60
23 | List training sessions with search feature | 1 | Jr Developer | 2 | 16 | 32
24 | Individual Trainee reports | 3 | QA | 1 | 16 | 16
| Progress report for trainee, sessions, trainers, scenarios |  | Total |  |  | 78
25 | Trainee | 4
26 | Trainee profile | 5 | Total Delivery days | 34
27 | Trainee Performance evaluation (heartbeat & scenario scores) | 3 | Total Effort | 78
Performance report
| Trainer | 3 | Total Cumulative Effort | 265 | + 1 for deployment
28 | Update profile information of self | 1
29 | Create scenarios & tasks | 2
30 | Update timesheet and availability | 3
31 | Maintain trainee records on performance | 1
32 | Trainee attendance
Attendance Management
33 | Mark leaves for trainees | 2
34 | Automatic re-scheduling of training sessions for absentees | 2
35 | Calculate leave balance & classes to be completed | 2
36 | Email alerts for attendances and scheduled classes | 1
Training Management
37 | Training sessions with scenarios | 2
38 | Record activity of each trainee per scenario | 2
39 | Record performance (heartbeats and scores) | 5
Trainee Health records management
40 | Real time monitoring and alerts for heartbeats if heart beat goes beyond specified range (heartbeat before, during & after scenario) | 4
41 | Record peak heartbeats | 2
Video Management
42 | Establish video naming convention and storage location | 3
43 | Link videos to scenarios, locations, trainees & trainers | 4
44 | Identify videos by angle, channels and feeds | 4
45 | Archive old videos for up to 5 years | 3
Phase 2
| Wireless Heart Beat monitoring Software development effort | 10
| Starting and stopping cameras | 10
| Fingerprint scanner attendance system | 10
Phase 3
Graphical and numerical reports
| Status of training sessions | 2
| Completed training sessions | 2
| Scheduled sessions | 1
| Cancelled/postponed sessions | 1
| Attendance | 1
| Trainee progress | 1
Training Session reporting on
| Participant list and details | 1
| Absentee list and rescheduled dates | 1
| Instructor details and performance | 2
| Scenario wise reports | 1
Trainees Individual report
| Complete history of the trainee | 2
| Session wise and scenario wise performance of trainee | 1
| Heart rate and body vitals of trainee | 2
| Notes/remarks by trainers | 1
| Comparative analysis of trainees’ performance scenario wise | 3
| Graphical representation of trainee performance | 2
Trainee’s overall report
| Report of all trainees in a batch | 2
| Report on high performing trainees and low performing trainees | 1
| Comparative report on heartbeats in a batch | 2
| Attendance report | 1
| Graphical representation of the performance improvement of a batch | 2
| Training deadline & remaining sessions graph | 2
| Login statistics | 1
Instructor’s report
| Session completion details | 2
| Number of students trained | 1
| Scenarios completed | 2
| Leave reports | 3
| Overall progress | 2
| Scenario wise reporting | 2
| Total sessions trained | 2
| Instructors details | 2
| Login statistics | 1
| Create Deployable installshield solution | 4
Testing & Deployment
| Testing | 59.5
| UAT | 1
| Deployment | 1
| Total Effort | 265.5