## ENOC
ENOC |  | 2018-03-09
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 4 | 4
Business analysis | 16 | 2 | Sr Developer | 1 | 4 | 4 | 18.25 | 20.825 | 18.25 | 19
Project Management | 14.6 | 1.825 | Jr Developer | 1 | 15 | 15
Design and Prototype | 32 | 4 | PM | 1 | 1.825 | 1.825
Documentation | 16 | 2 | BA | 1 | 2 | 2
Development |  |  | Tech writer | 1 | 2 | 2
Application basic setup | 8 | 1 | QA | 1 | 8.625 | 8.625
Admin Module |  |  | Total |  |  | 37.45
Login- predefined username, password, forgot password option | 4 | 0.5 | Total Delivery days | 27.625
Employee Management | 8 | 1 | Total Effort | 37.45 | (+1 Day deployment)
Employee Listing with search facility
Activate/Deactivate Employees |  |  |  | 1.3813 | Months
Car Details Management | 8 | 1
Add/Edit/Delete Car details
Manage Car Availability Status
Reports based on employees(viewed by admin) | 32 | 4
Daily Car Booking
Kilometers clocked
Green points earned
Co2/energy saved report
Employee module
Sign Up | 4 | 0.5
Sign in | 4 | 0.5
Dashboard - List all lastest Journey History | 4 | 0.5
Car listing with search options - Registration No, Name, Availability Status | 8 | 1
Car Details | 4 | 0.5
Car Booking Module | 4 | 0.5
Journey Management | 16 | 2
Journey History | 4 | 0.5
System features
Authentication & authorization | 8 | 1
Duration of trip calculation | 10 | 1.25
Computation of Co2 saved(algorithm) | 10 | 1.25
Computation of cerdit points earned & AED(algorithm) | 10 | 1.25
0
Quality Assurance
QA & Bug Fixing | 69 | 8.625
UAT | 3 | 0.375
Deployment per instance |  | 0
Total Effort | 296.6 | 37.075
Assumptions
Website will be static.
Algorithms will be provided
Calculation formulas will be provided
All events - Journey start, stop, end etc should be triggered by the employee