## Facility Management
Facility Management |  | 2018-03-09
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 3 | 3
Business analysis | 16 | 2 | Sr Developer | 1 | 4 | 4 | 18.5 | 20.85 | 8 | 19
Project Management | 14.8 | 1.85 | Jr Developer | 1 | 15 | 15
Design and Prototype | 24 | 3 | IOS Developer
Documentation | 8 | 1 | Android Developer
Development |  |  | PM | 1 | 1.85 | 1.85
Application basic setup | 8 | 1 | BA | 1 | 2 | 2
Registration |  |  | Tech writer | 1 | 1 | 1
Shops | 4 | 0.5 | QA | 1 | 7 | 7
FMC | 8 | 1 | Total |  |  | 33.85
Search |  |  | Total Delivery days | 25
Shop / FMC |  |  | Total Effort | 33.85 | (+1 Day deployment)
Shop Mobile App
Dashboard and Menu | 8 | 1 |  | 1.25 | Months
Request Repairs or new services (Shops) | 8 | 1
Receive information on FMC & Work Req. | 8 | 1
Request permission to conduct work (to the Mall) | 8 | 1 | Search & sent request to multiple FMC
Work Completion report | 8 | 1
FMC Mobile App |  | 0
Dashboard and Menu | 8 | 1
Receive request for repair or new work | 8 | 1
Send Quote | 8 | 1
Receive Work Order | 8 | 1
Completion report | 8 | 1
Corporate Web App
Dashboard for Work requested by shops | 8 | 1
Dashboard for Work progress | 8 | 1
Send request to FMC | 8 | 1
Receive Quotes from FMC | 8 | 1
Send Work Order | 8 | 1
Receive Work Status | 8 | 1
User Management ShopHQ (Super Admin, Manager, Employees) | 8 | 1
User Management Shop (Manager, Owner) | 4 | 0.5
User Management FMC (Manager, Supervisor, Owner) | 4 | 0.5
Mobile API Services | 24 | 3
Quality Assurance
QA & Bug Fixing | 56 | 7
UAT | 1 | 0.125
Deployment per instance |  | 0
Total Effort | 307.8 | 38.475
Assumptions
Website will be static.
Algorithms will be provided
Calculation formulas will be provided
All events - Journey start, stop, end etc should be triggered by the employee