## Facility Management
Facility Management |  | 2018-03-09
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort
Initiation |  |  | Designer | 1 | 3 | 3
Business analysis | 16 | 2 | Sr Developer | 1 | 10.5 | 10.5 | 18.5 | 33.2 | 10.5 | 10.5
Project Management | 14.8 | 1.85 | Jr Developer | 0 | 0 | 0
Design and Prototype | 24 | 3 | IOS Developer | 1 | 11.7 | 11.7
Documentation | 8 | 1 | Android Developer | 1 | 7 | 7
Development |  |  | Developer (API Services) | 1 | 4 | 4
Application basic setup | 0 | 0 | PM | 1 | 1.85 | 2
Registration |  |  | BA | 1 | 2 | 1
Shops | 4 | 0.5 | Tech writer | 1 | 1 | 1
FMC | 8 | 1 | QA | 1 | 8.325 | 8.325
Search |  |  | Total |  |  | 48.525
Shop / FMC | 8 | 1 | Total Delivery days | 25.825
Shop Mobile App |  |  | Total Effort | 48.525 | (+1 Day deployment)
Dashboard and Menu | 8 | 1 |  | 388.2
Request Repairs or new services (Shops) | 8 | 1 |  | 1.2913 | Months
Receive information on FMC & Work Req. | 8 | 1
Request permission to conduct work (to the Mall) | 8 | 1
Work Completion report | 8 | 1 | Search & sent request to multiple FMC
FMC Mobile App |  | 0 | API Development | 4
Dashboard and Menu | 8 | 1 | Web Development | 15.6083
Receive request for repair or new work | 8 | 1 | Android Development | 12.1083
Send Quote | 8 | 1 | IOS Development | 16.8083
Receive Work Order | 8 | 1 |  | 44.525
Completion report | 8 | 1 | Tab IOS | 4
Corporate Web App |  |  | Tab Android | 3
Dashboard for Work requested by shops | 8 | 1
Dashboard for Work progress | 8 | 1
Send request to FMC | 8 | 1
Receive Quotes from FMC | 8 | 1
Send Work Order | 8 | 1
Receive Work Status | 8 | 1
User Management ShopHQ (Super Admin, Manager, Employees) | 8 | 1
User Management Shop (Manager, Owner) | 4 | 0.5
User Management FMC (Manager, Supervisor, Owner) | 4 | 0.5
Mobile API Services | 32 | 4
Quality Assurance
QA & Bug Fixing | 66.6 | 8.325
UAT | 1 | 0.125
Deployment per instance |  | 0
Total Effort | 326.4 | 40.8
Assumptions
Website will be static.
Algorithms will be provided
Calculation formulas will be provided
All events - Journey start, stop, end etc should be triggered by the employee