## Estimate
Project Name : Fisher Mobile (Android +IOS) + Desktop App
Inputs |  | Estimation Summary (Hours and Business days) |  |  | Estimated Amount
Risk and/or "unknown" (25% ; 50% ; 25% ; 10%) | 10 | Optimistic hours | 397.2 | 28.3714 | 3177.6 | 33.1
Project Complexity scale Extreme(100%); high(50%) ; medium(25%) ; low(10%) | 10 | Most likely hours** | 436.92 | 31.2086 | 3495.36 | 33.1
Average productive hours per day | 7 | Pessimistic hours* | 476.64 | 34.0457 | 3813.12 | 79.44 | Holidays in 2016 | Date
Estimation parameters | Hours |  |  |  | Estimated Amount |  | New Year's Day | 2016-01-01
Requirement gathering | 8 | Expected Duration |  | Hours | 206544 |  | Republic Day | 2016-01-26
Research and analysis | 2 | Triangular distribution method |  | 31.2086 | 227198.4 |  | Monty Thursday | 2016-03-24
Development | 236 | Beta distribution (PERT technique) |  | 31.2086 | 247852.8 |  | Good Friday | 2016-03-25
Design | 8 | [5 empty] | Vishu | 2016-04-14
Testing | 47.2 | Finish Date |  |  |  |  | May Day | 2016-05-01
Training | 0 | Earliest start date | 2016-08-15 |  |  |  | Assembly Elections | 2016-05-16
Documentation | 8 | Earliest completion date | 2016-09-27 | Optimistic |  |  | Onam | 2016-09-13
Meetings | 4 | Earliest completion date | 2016-09-30 | Most likely |  |  | Onam | 2016-09-14
Migration (data or content) | 0 | Earliest completion date | 2016-10-05 | Pessimistic |  |  | Onam | 2016-09-15
Project management | 11.8 | [5 empty] | Gandhu Jayanthi | 2016-10-02
Reports | 0 | Latest start date | 2016-09-15 |  |  |  | Deepavali | 2016-10-29
UAT | 0 | Latest completion date | 2016-10-25 | Optimistic |  |  | Christmas | 2016-12-26
Accessibility test | 0 | Latest completion date | 2016-10-28 | Most likely
Pre deployment process | 1 | Latest completion date | 2016-11-02 | Pessimistic
Deployment | 4
Post production testing | 0 | Pessimistic case buffer (in percentage) |  | 20
Knowledge transfer/ Service transition | 1 | No of resources (This will impact the number of business days to complete and finish date calculation.) on average |  | 2
Marketing | 0
Project retrospective | 0
* Pessimistic hours= Best case hours+ Pessimistic case buffer **Most likely=(Optimistic + Pessimistic )/2 ***Excluded Saturdays, Sundays and state holidays
Total | 331
Note on E13: Prashant Thomas: Please enter your estimated start date here

## Effort Details
0
| Fisher Mobile (Android Only) + Desktop App | 2016-08-09
Sl. No. | Product Log | Days | Comments
1 | Splash Screen |  | TBD
2 | Welcome / Home Screen | 1 | Icons will tiled on the home screen
Logo (Common in all screen)
Icon for Application Pictures, Approvals, Product Data, Create Submittal
Menu Items for the same
3 | User Authentication/ Authorization | 2
Login
User Role creation & assignment (sales Man, Consultant, Contractor, System Admin, Approval Manager)
User Registration
4 | Maintain Master Data | 2.5
Application Picture Type
Project Type
Project Sub Type
Products (manufacturer, Supplier)
Location
Country
Document Types ( Schedule of Items, reference drawings e.t.c.)
5 | Application Pictures (Salesman View) | 2
Choose Application Picture type
Name of the Application
Project Name, Project Description, Project Type, Project Sub Type
Consultant Name, Contractor Name (possibility to add more than one), Sub Contractor
Client Name
Location ( Select Location by GPS or specify Manually)
Products used (can be more than one), Date entered
Submit for approval
6 | Approvals (Approval Manager View) | 2.5
Approvals by manager of submitted images with details
Approval Screen
SR NO, Country, Name of project, Contractor, Sub Contractor (If Any)
Consultant, Product, Date of entry, Application Name, Date of approval, Approval button.
7 | Additional Information needed for generating Approval Copy
Contract No, MS. No.
Contract Title, Revision
From , To
| Manufacturer, Local Agent or Supplier | 2
Material description, Descipline, Specification No, attach List of documents
Material required on site date, Expected date of arrival
Raised by, Design Supervision, Contractor signature.
PDF document generation includes attachment of all document types that were uploaded
8 | Product Data | 1 | What is catalog page, loading tables, test reports. Could this be a system admin functionality. Find out the details of the individual items listed????
Product Name, article number, catalogue page, Loading Tables,
International Approvals, test reports, Country of origin
10 | Submittal Creation |  | Done external … why is this included????
Cover page
Company Profile (list fields)
Schedule of proposed material
catalog page
loading tables
| international approvals | 3.5
test reports
compliance statements
calculation (how is this represented)
estimated amt ?????
Country of origin, Previous approvals (how to identify)
Project References (reference by the app or external references)
11 | API Integration | 3
product data submittal
Additional information for approval copy
Create Approvals
Application picture submittal
PDF document generation
12 | General Appliication features | 1
Database Design
Theme Development
Requirements documentation and specification
| Total | 16.5
| Cumulative Total (Android + Desktop) | 132
| Cumulative Total (IOS) | 104
| Total | 236 | 29.5