## ADSC
| ADSC |  | 23/05/2018
Wednesday
| Module | Hours | Man Days |  | No | Man Days | Total Effort
| Initiation |  |  | Designer | 1 | 4 | 4
| Business analysis | 16 | 2 | Sr Developer | 1 | 9.5 | 9.5 | 18.75 | 19 | 18.75 | 19
| Project Management | 15 | 1.875 | Jr Developer | 1 | 9.5 | 9.5
| Design and Prototype | 32 | 4
| Development |  |  | PM | 1 | 1.875 | 1.875
| Application Basic Setup | 8 | 1 | BA | 1 | 2 | 2
| Admin |  |  | Tech writer | 0 | 3 | 0
1 | Add new Clients | 6 | 0.75 | QA | 2 | 3.3125 | 6.625
2 | Add locations for clients | 6 | 0.75 | Total |  |  | 33.5
3 | Add cameras within location | 6 | 0.75
4 | Manage the folder and directory structure to uniquely identify feeds | 6 | 0.75
5 | Add users for clients (Admins & App Users) | 6 | 0.75 | Total Delivery days | 16.8125
| End Customer |  | 0 | Total Effort | 33.5 | (+1 Day deployment)
| Login, Registrations, Forgot password, email validations | 12 | 1.5
| Browse Locations -> Cameras -> Feeds | 12 | 1.5
| Search Feeds using provided metadata on feeds | 12 | 1.5
| Sort and filter feeds | 12 | 1.5
| Web Viewer for images and feeds | 16 | 2
| Download images and feeds | 6 | 0.75
| Reports | 8 | 1
| System Features |  | 0
| Auditing and loggings | 4 | 0.5
| Exception Handling | 4 | 0.5
| Authentication and Authorization | 8 | 1
| Email | 6 | 0.75
| File and folder management | 12 | 1.5
Quality Assurance
| QA & Bug Fixing | 45 | 5.625
| UAT | 8 | 1
| Deployment per instance | 8 | 1
| Total Effort | 274 | 34.25
Onsite inspection (mobile App)
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118