## Sheet2
| No | Hours | Days | Total effort
BA | 1 | 48 | 6 | 6
Android | 1 | 152 | 19 | 19
IOS | 1 | 176 | 22 | 22
QA | 2 | 113.4 | 14.175 | 28.35
Design | 1 | 48 | 6 | 6
PM | 1 | 64.8 | 8.1 | 8.1
Web | 1 | 320 | 40 | 40
Total effort |  |  |  | 129.45
Delivery timeline | 60.175
Total effort | 130

## iOSDev
e-commerce mobile app |  | 2017-11-28
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Registration page
Design,Development and api integration | 8 | 1
Login Page
Design,Development and api integration | 8 | 1
Dashboard
Design,Development and api integration | 16 | 2
Product list(categories, offers and preface)
Design,Development and api integration | 16 | 2
Product Detail Pages
Design,Development and api integration | 8 | 1
Product Cart
Design,Development and api integration | 8 | 1
Chat Page
Design,Development and api integration | 24 | 3
Payment gateway integration
Design,Development ,api integration and Payment gateway integration | 32 | 4
Cart Product delete and add
Development and api integration | 8 | 1
Success, wanning and confirmation Popups
Design,Development and api integration | 8 | 1
User type selection page(Guest, Registered user)
Design,Development and api integration | 4 | 0.5
Shipping Address page
Design,Development and api integration | 8 | 1
Billing Address page
Design,Development and api integration | 6 | 0.75
Contact Us Page
Design,Development and api integration | 4 | 0.5
Agreement page(Payment policy and Company policy)
Design,Development and api integration | 6 | 0.75
Logout
Design,Development and api integration | 4 | 0.5
Developer side testing and bug fixing | 24 | 3
total effort |  | 22
Assumption
This application will support iOS 9.0 and above
This application designed for mobiles only.

## Android
e-commerce mobile app |  | 2017-11-28
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Registration page
Design,Development and api integration | 4 | 0.5
Login Page
Design,Development and api integration | 4 | 0.5
Dashboard
Design,Development and api integration | 16 | 2
Product list(categories, offers and preface)
Design,Development and api integration | 12 | 1.5
Product Detail Pages
Design,Development and api integration | 8 | 1
Product Cart
Design,Development and api integration | 8 | 1
Chat Page
Design,Development and api integration | 16 | 2
Payment gateway integration
Design,Development ,api integration and Payment gateway integration | 32 | 4
Cart Product delete and add
Development and api integration | 4 | 0.5
Success, wanning and confirmation Popups
Design,Development and api integration | 8 | 1
User type selection page(Guest, Registered user)
Design,Development and api integration | 4 | 0.5
Shipping Address page
Design,Development and api integration | 8 | 1
Billing Address page
Design,Development and api integration | 6 | 0.75
Contact Us Page
Design,Development and api integration | 4 | 0.5
Agreement page(Payment policy and Company policy)
Design,Development and api integration | 6 | 0.75
Logout
Design,Development and api integration | 2 | 0.25
Developer side testing and bug fixing | 16 | 2
total effort |  | 19
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles only.