## AndroidDev
Find Your Perfect Surveyor |  | 2018-03-07
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Candidate Module
Candidate Login
Design ,Development and Api integration | 8 | 1
Registration with facebook
Design ,Development and Api integration | 16 | 2
Registration with Linkd in
Design ,Development and Api integration | 16 | 2
Registration with Google
Design ,Development and Api integration | 16 | 2
Remember Me
Design ,Development and Api integration | 2 | 0.25
Forgot Password
Design ,Development and Api integration | 6 | 0.75
Registration/Sign up
Personal Information | 8 | 1
Contact Details | 8 | 1
Education Details | 8 | 1
Work Experience | 8 | 1
Languages | 8 | 1
Achievement and Activities | 8 | 1
Upload your video resume | 8 | 1
Candidate Dashboard
Design ,Development and Api integration | 16 | 2
Notifications:
Design ,Development and Api integration | 8 | 1
Job Listing and search
Design ,Development and Api integration | 8 | 1
Total View:
Design ,Development and Api integration | 4 | 0.5
Interview Schedules
Design ,Development and Api integration | 16 | 2
Short Listed
Design ,Development and Api integration | 8 | 1
Interview Declined
Design ,Development and Api integration | 6 | 0.75
Job Details
Design ,Development and Api integration | 16 | 2
Candidate Forum
Design ,Development and Api integration | 12 | 1.5
Candidate DMS
Design ,Development and Api integration | 12 | 1.5
Employer Login
Design ,Development and Api integration | 8 | 1
Employer Module
Employer Registartion
Design ,Development and Api integration | 16 | 2
Help
Design ,Development and Api integration | 16 | 2
Google Analytics
Development and Api integration | 8 | 1
Membership Plan Details
Design ,Development and Api integration | 8 | 1
Developer side testing | 16 | 2
total effort |  | 38.75
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode

## Sheet1
Mobile Design & Development
Basic Setup
Splash Screen
Candidate Module
Candidate Login
Registration with facebook
Registration with Linkd in
Registration with Google
Remember Me
Forgot Password
Registration/Sign up
Personal Information
Contact Details
Education Details
Work Experience
Languages
Achievement and Activities
Upload your video resume
Candidate Dashboard
Notifications:
Job Listing and search
Total View:
Interview Schedules
Short Listed
Interview Declined
Job Details
Candidate Forum
Candidate DMS
Employer Login
Employer Module
Employer Registartion
Help
Google Analytics
Development and Api integration
Membership Plan Details