## Graduate Surveyors
Graduate Surveyors |  | 2018-03-06
Monday
Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  |  |  | Total Hours | Hours/3 phases
Initiation |  |  | Designer | 1 | 19 | 19 |  |  |  |  | 152 | 50.6667
Business analysis | 32 | 4 | Sr Developer | 1 | 38 | 38 | 15.75 | 120.75 | 82.75 | 82 | 304 | 101.3333
Project Management | 68.6 | 8.575 | Jr Developer | 1 | 44 | 44 |  |  |  |  | 352 | 117.3333
Design and Prototype | 152 | 19 | Android | 1 | 38.75 | 38.75 |  |  |  |  | 310 | 103.3333
Development |  |  | IOS Developer | 1 | 42.625 | [6 empty] | 22.8667
Application basic setup | 8 | 1 | PM | 1 | 8.575 | 8.575 |  |  |  |  | 68.6 | 10.6667
Admin Module |  |  | BA | 1 | 4 | 4 |  |  |  |  | 32 | 8
Admin Login |  |  | Tech writer | 1 | 3 | 3 |  |  |  |  | 24 | 95.7333
Login |  |  | QA | 2 | 17.95 | 35.9 |  |  |  |  | 287.2
Validate the user send email with details | 4 | 0.5 | Total |  |  | 191.225
Registration Verification
Search, Active, In Active, No. of Users, View user details,Activate deleted users | 24 | 3
Job Verification
Add New, Search, Active, In Active, No. of Users, View ,Send notification) | 24
Masters
Qualification Master | 2 | 0.25 | Total Delivery days | 80.95
Category Master | 2 | 0.25 | Total Effort | 191.225 | (+1 Day deployment)
Technology / Skills Master | 2 | 0.25
Language Master | 2 | 0.25
Activity & Achievement Master | 2 | 0.25
Notifications
Email | 4 | 0.5
SMS | 4 | 0.5
Settings
Email Templates | 4 | 0.5
About Us | 4 | 0.5
Terms & Conditions | 4 | 0.5
Candidate Module
Candidate Login
Login, Login with Social Sites, | 16 | 2
Remember Me, Forgot Password, Send Reset Email, Account Highlighted Notification | 16 | 2
Sign Up / Registration
Registration Step 1 | 4 | 0.5
Personal Information
Registration Step 2 | 4 | 0.5
Contact Details
Registration Step 3 | 2 | 0.25
Education Details
Registration Step 4 | 8 | 1
Work Experience
Registration Step 5 | 8 | 1
Languages
Registration Step 5 | 2 | 0.25
Achievement and Activities
Registration Step 6 | 2 | 0.25
Upload your video resume
Registration Step 7 | 4 | 0.5
Employer Registration
Employer Registration form | 6 | 0.75
Help | 12 | 1.5
Email Customer Service
Frequently asked questions
How to create job listing
How to get more candidates
My current membership plan
Integration with Job boards? How does it work?
Integration with social media site? How does it work?
How to search employee
CV details
Candidate Dashboard
Notifications, Search Area, Job Listing, Total View, Interview Schedules, Short Listed, Interview Declined | 16 | 2
Job Details
Job Details, Send Query to Recruiter, Apply | 8 | 1
Candidate DMS
Upload Files, Search by Tags,Preview, Delete | 16 | 2
Candidate Forum |  | 0
lists all form topics, displays total views, posts and subtopics | 8 | 1
Detail page which displays all user post and other details | 8 | 1
Recruiter Module |  | 0
Recruiter Login |  | 0
Remember Me, Forgot Password, Send Reset Email, Account Highlighted Notification
Recruiter Dashboard
Job List | 4 | 0.5
Task & Events | 16 | 2
Job Details / Activity | 4 | 0.5
Job Details / Details | 4 | 0.5
CV | 4 | 0.5
Docs | 4 | 0.5
Upload Files, Search by Tags,Preview, Delete
Job Creation |  | 0
Job entry details | 4 | 0.5
User Profile
My Profile | 6 | 0.75
My Settings & Preferences | 6 | 0.75
My Templates | 6 | 0.75
Users (Manage license user account) | 4 | 0.5
Purchase (Licenses, Payment) | 8 | 1
Other Functions |  | 0
Live Chat | 12 | 1.5
Reports | 4 | 0.5
Transactions Worldwide | 12 | 1.5
Top Performing Account | 4 | 0.5
Today’s Visitors | 2 | 0.25
Number of Support Questions | 1 | 0.125
Number of Employers | 1 | 0.125
Number of Candidates | 1 | 0.125
New Registrations | 1 | 0.125
Advertisement | 16 | 2
API Configuration | 96 | 12
Job Board Integration | 96 | 12
Payment Gateways | 72 | 9
Google Analytics | 20 | 2.5
Membership Plan Details | 48 | 6
Quality Assurance
QA & Bug Fixing | 271.2 | 33.9
UAT | 16 | 2
Deployment per instance | 8 | 1
Total Effort | 1233.8 | 151.225
Note:- The effort might change during a detailed system study
Assumptions
Advertisement:- More details would be required for accurate estimate
API Configuration:- Details to be included in the API, data format etc will be shared
Job Board Integration:- Details to be integrated should be shared for relatively accurate estimate
Payment Gateways :- Payment gateways to be integrated would be shared by the client
Google Analytics:- Details to be captured will be shared by the client
Membership Plan Details:- More details would be shared for accurate estimate
The application would responsive web site
The effort is for template based HTML (theme)

## Mobile
Find Your Perfect Surveyor |  | 2018-03-07
Module | Hours | Man Days
Initiation
Development
Mobile Design and Development
Basic Setup | 8 | 1
Splash Screen
Design and Development | 4 | 0.5
Candidate Module
Candidate Login
Design ,Development and Api integration | 8 | 1
Registration with facebook
Design ,Development and Api integration | 16 | 2
Registration with Linkd in
Design ,Development and Api integration | 16 | 2
Registration with Google
Design ,Development and Api integration | 16 | 2
Remember Me
Design ,Development and Api integration | 2 | 0.25
Forgot Password
Design ,Development and Api integration | 6 | 0.75
Registration/Sign up
Personal Information | 8 | 1
Contact Details | 8 | 1
Education Details | 8 | 1
Work Experience | 8 | 1
Languages | 8 | 1
Achievement and Activities | 8 | 1
Upload your video resume | 8 | 1
Candidate Dashboard
Design ,Development and Api integration | 16 | 2
Notifications:
Design ,Development and Api integration | 8 | 1
Job Listing and search
Design ,Development and Api integration | 8 | 1
Total View:
Design ,Development and Api integration | 4 | 0.5
Interview Schedules
Design ,Development and Api integration | 16 | 2
Short Listed
Design ,Development and Api integration | 8 | 1
Interview Declined
Design ,Development and Api integration | 6 | 0.75
Job Details
Design ,Development and Api integration | 16 | 2
Candidate Forum
Design ,Development and Api integration | 12 | 1.5
Candidate DMS
Design ,Development and Api integration | 12 | 1.5
Employer Login
Design ,Development and Api integration | 8 | 1
Employer Module
Employer Registartion
Design ,Development and Api integration | 16 | 2
Help
Design ,Development and Api integration | 16 | 2
Google Analytics
Development and Api integration | 8 | 1
Membership Plan Details
Design ,Development and Api integration | 8 | 1
Developer side testing | 16 | 2
total effort |  | 38.75
Assumption
This application will support Sdk version 19(kitkat) and above
This application designed for mobiles in portrait mode