## Graduate Surveyors
Graduate Surveyors |  | 2018-03-21
Wednesday
Module | Hours | Man Days |  | No | Man Days | Total Effort |  |  |  |  | Total Hours | Hours/3 phases
Initiation |  |  | Designer | 1 | 19 | 19 |  |  |  |  | 152 | 50.6667
Business analysis | 32 | 4 | Sr Developer | 1 | 38 | 38 | 34 | #REF! | 170.875 | 82 | 304 | 101.3333
Project Management | 136.7 | 17.0875 | Jr Developer | 1 | 44 | 44 |  |  |  |  | 352 | 117.3333
Design and Prototype | 152 | 19 | Android | 1 | #REF! | #REF! |  |  |  |  | #REF! | #REF!
Development |  |  | IOS Developer | 1 | #REF! | [6 empty] | 45.5667
Application basic setup | 8 | 1 | PM | 1 | 17.0875 | 17.0875 |  |  |  |  | 136.7 | 10.6667
Admin Module |  |  | BA | 1 | 4 | 4 |  |  |  |  | 32 | 8
Admin Login |  |  | Tech writer | 1 | 3 | 3 |  |  |  |  | 24 | 186.5333
Login |  |  | QA | 2 | 34.975 | 69.95 |  |  |  |  | 559.6
Validate the user send email with details | 8 | 1 | Total |  |  | #REF!
Registration Verification
Search, Active, In Active, No. of Users, View user details,Activate deleted users | 24 | 3
Job Verification
Add New, Search, Active, In Active, No. of Users, View ,Send notification) | 24 | 3
Masters
Qualification Master | 4 | 0.5 | Total Delivery days | 97.975
Category Master | 4 | 0.5 | Total Effort | #REF! | (+1 Day deployment)
Technology / Skills Master | 4 | 0.5
Language Master | 4 | 0.5
Activity & Achievement Master | 4 | 0.5
Question | 4 | 0.5
Notifications
Email | 8 | 1
SMS | 8 | 1
Settings
Email Templates | 8 | 1
About Us | 8 | 1
Terms & Conditions | 8 | 1
Export Data to Excel or Other
Transfer data to Mocrosoft Excel or Other | 16 | 2
Candidate Module
Candidate Login
Login, Login with Social Sites, | 16 | 2
Remember Me, Forgot Password, Send Reset Email, Account Highlighted Notification | 16 | 2
Sign Up / Registration
Registration Step 1 | 16 | 2
Personal Information
Registration Step 2 | 16 | 2
Contact Details
Registration Step 3 | 16 | 2
Education Details
Registration Step 4 | 16 | 2
Work Experience
Registration Step 5 | 16 | 2
Languages
Registration Step 5 | 16 | 2
Achievement and Activities
Registration Step 6 | 16 | 2
Upload your video resume
Registration Step 7 | 24 | 3
Confirmation Email after Registration
Registration Step 8 | 20 | 2.5
Employer Registration
Employer Registration form | 32 | 4
Help | 24 | 3
Email Customer Service
Frequently asked questions
How to create job listing
How to get more candidates
My current membership plan
Integration with Job boards? How does it work?
Integration with social media site? How does it work?
How to search employee
CV details
Candidate Dashboard
Notifications, Search Area, Job Listing, Total View, Interview Schedules, Short Listed, Interview Declined | 160 | 20
Job Details
Job Details, Send Query to Recruiter, Apply | 56 | 7
Candidate DMS
Upload Files, Search by Tags,Preview, Delete | 28 | 3.5
Candidate Forum |  | 0
Admin
Create form Topics by Admin | 24 | 3
Candidate
lists all form topics, displays total views, posts and subtopics | 8 | 1
Detail page which displays all user post and other details | 24 | 3
Recruiter Module |  | 0
Recruiter Login |  | 0
Login, Login with Social Sites (Google, Facebook, LinkedIn) | 16 | 2
Remember Me, Forgot Password, Send Reset Email | 8 | 1
Account Highlighted Notification | 16 | 2
Recruiter Dashboard
Job List | 24 | 3
Task & Events | 40 | 5
Job Details / Activity | 32 | 4
Job Details / Details | 32 | 4
CV | 16 | 2
Docs |  | 0
Show Uploaded documents [based on filters (All, Documents, Audio, Video)] | 8 | 1
Upload Files | 24 | 3
Search by Tags,Preview, Delete | 12 | 1.5
Job Creation |  | 0
Job entry details | 8 | 1
User Profile
My Profile | 6 | 0.75
My Settings & Preferences | 6 | 0.75
My Templates | 6 | 0.75
Users (Manage license user account) | 5 | 0.625
Purchase (Licenses, Payment) | 24 | 3
Other Functions |  | 0
Live Chat | 40 | 5
Reports | 40 | 5
Transactions Worldwide |  | 0
Top Performing Account |  | 0
Today’s Visitors |  | 0
Number of Support Questions |  | 0
Number of Employers |  | 0
Number of Candidates |  | 0
New Registrations |  | 0
Advertisement | 40 | 5
API Configuration | 40 | 5
Job Board Integration | 96 | 12
Payment Gateways | 72 | 9
Google Analytics | 20 | 2.5
Membership Plan Details | 48 | 6
Quality Assurance
QA & Bug Fixing | 543.6 | 67.95
UAT | 16 | 2
Deployment per instance | 8 | 1
Total Effort | 2255.3 | 281.9125
Note:- The effort might change during a detailed system study
Assumptions
Advertisement:- More details would be required for accurate estimate
API Configuration:- Details to be included in the API, data format etc will be shared by the client
Job Board Integration:- Details to be integrated should be shared for relatively accurate estimate
Payment Gateways :- Payment gateways to be integrated would be shared by the client. Test Account, Test Cards would be shared by the client
Google Analytics:- Details to be captured will be shared by the client
Membership Plan Details:- More details would be shared for accurate estimate
The application would responsive web site
The effort is for template based HTML (theme)