## Employee Satisfaction Effort
Raviz Rewards Card | July 21 2017
Friday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 40 | 5 | 5
Functional Specification | 8 | 1 | Sr.Developer | 1 | 148 | 18.5 | 18.5 | 38.5 | 38
Project Management | 30.8 | 3.85 | Jr Developer | 1 | 156 | 19.5 | 19.5
Solutioning | 8 | 1 | PM | 1 | 54.8 | 6.85 | 6.85
Graphic Design (Android App + Web application) | 24 | 3 | QA | 2 | 48.2 | 6.025 | 12.05
Working Prototype | 16 | 2 | Total |  | 447 |  | 61.9 | 495.2
Development
Inception (MDM) |  |  | Total Delivery days | 30.525
create card series | 8 | 1 | Total Man day Effort | 61.9
Create Coupons | 8 | 1
Reward Card Integration (with reader) | 20 | 2.5
Scan Barcodes | 16 | 2 |  |  | Week1 | Week2 | week 3 | week4 | week5 | week6
Create Properties | 8 | 1 | Designer
Customer (Mobile App + API) |  | 0 | Sr Developer
Customer card registration | 8 | 1 | Jr Developer
Customer dashboard |  | 0 | PM
Points redeemed | 8 | 1 | QA
Rewards availed | 8 | 1
Points available | 8 | 1
Rewatds available | 8 | 1
Soft copy of card | 8 | 1
Coupons | 8 | 1
Discounts | 8 | 1
Feed Back / Complaints | 8 | 1
Compliant resolution / In box | 8 | 1
View Property with details | 8 | 1
Newsletter, Static pages (3) | 6 | 0.75
Front Desk |  | 0
Issue new Card | 6 | 0.75
Issue Duplicate card | 16 | 2
Renew Card | 8 | 1
Resolve Complaints | 6 | 0.75
View Customer Purchase History | 6 | 0.75
Issue Discounts | 8 | 1
Process coupons | 8 | 1
View Purchase History | 4 | 0.5
Recommend services or products based on purchase history | 8 | 1
Upsell / Cross sell | 8 | 1
View Member details + customer look up | 6 | 0.75
Back Office |  | 0
Resolve compliants / Issues | 4 | 0.5
Update customer Information + customer look up | 4 | 0.5
Create Newsletters | 8 | 1
Manage coupons (price, product, discount etc.) | 8 | 1
Manage Properties (Restaurants, menu, Conceirge services, Room types, Banquet facilities, Conference rooms etc) | 16 | 2
Management |  | 0
Parametrized reports to |  | 0
Track purchases | 6 | 0.75
Rewards availed | 6 | 0.75
most Points awarded for category | 6 | 0.75
Customer profiles | 6 | 0.75
Set rewards system | 6 | 0.75
Testing & Deployment |  | 0
Testing | 92.4 | 11.55
UAT | 4 | 0.5
Deployment Support | 4 | 0.5
Total Effort | 503.2 | 62.9
Assumptions
Device/s and required SDK and Test cards will be provided by the client
Merchant ID and other required payment gateway details will be provided by the client
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions