## Employee Satisfaction Effort
e-Dirham Integration Project | July 21 2017 | July 21 2017
| Wednesday | Wednesday
Module | Man Hours | Man Days
Initiation |  |  |  | No | Man hours | Man Days | Total Effort
Requirements gathering and documentation (SRS) | 8 | 1 | Designer | 1 | 24 | 3 | 3
Functional Specification | 8 | 1 | Sr.Developer | 1 | 72 | 9 | 9 | 28.5 | 29
Project Management | 22.8 | 2.85 | Jr Developer | 1 | 160 | 20 | 20
Graphic Design | 8 | 1 | PM | 1 | 38.8 | 4.85 | 4.85
Working Prototype | 16 | 2 | QA | 1 | 76.4 | 9.55 | 9.55
Development |  |  | Total |  | 371.2 |  | 46.4 | 371.2
Bilingual UI | 12 | 1.5
POS Device Integration | 24 | 3 | Total Delivery days | 37.4 |  |  |  |  | 44
Payment Module Service Integratino to e-Dirham | 20 | 2.5 | Total Man day Effort | 46.4 | 34.8 | 85.9259 | 14.0741 |  | 54
Payment Mode - Pay | 12 | 1.5
Payment Mode - Pre-Auth and Capture | 16 | 2
Payment Mode - Refund | 8 | 1
Payment Mode - Reversal | 8 | 1
Payment Response Management | 12 | 1.5
Payment accepting screens and functionality | 16 | 2
Inegration with client application | 24 | 3
Rerouting request for device failure to a new counter | 24 | 3
Web Service layer (Middleware) |  | 0
POS device interface layer | 4 | 0.5
Internal application interface layer | 4 | 0.5
Messsage translation service | 4 | 0.5
Payment Mode - Pay | 6 | 0.75
Payment Mode - Pre-Auth and Capture | 12 | 1.5
Payment Mode - Refund | 4 | 0.5
Payment Mode - Reversal | 6 | 0.75
Payment Response Management | 12 | 1.5
Reporting (avg 6 hrs / report) X 5 | 0 | 0
Testing & Deployment
Testing | 68.4 | 8.55
UAT | 8 | 1
Deployment Support | 8 | 1
Total Effort | 375.2 | 46.9
Assumptions
Device/s and required SDK and Test cards will be provided by the client
Merchant ID and other required payment gateway details will be provided by the client
Required source code of the modules should be provided if it require integration with any existing application
Access to the database will be provided to update the payment transactions